## Chatbot Projects
Client | Chatbot | Industry | Sub Industry | Sales Connect | Bot Type | AI enabled | Vendor | Status | Brief Received Date | Commercials Shared Date | PO Received | PO received Date | Development Start Date | UAT Start Date | Development Days Required (Est.) | Actual Go-Live | Commited Go-Live | Updated Go-Live | Days to Go-Live | Delivery Status | Notes | Date Paused | PO Shared with LimeChat | PO Shared with LimeChat Date | Vendor Development Cost (₹) | Vendor Monthly Rental (₹) | Vendor Base AI Sessions | Vendor AI Session Cost | Vendor Base Bot Sessions | Vendor Bot Fees | Vendor Base Agents | Vendor Per-Agent Cost | Vendor Base Conversations | Vendor Conversation Cost | Netcore Development Cost (₹) | Netcore Monthly Rental (₹) | Netcore Base AI Sessions | Netcore AI Session Cost | Netcore Base Bot Sessions | Netcore Bot Fees | Netcore Base Agents | Netcore Per-Agent Cost | Netcore Base Conversations | Netcore Conversation Cost
Antara Assisted Care Services Limited | Ageasy | Other | General | Shubham Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Antara Assisted Care Services Limited | Antara Bot | Healthcare | Senior Living & Elder Care | Shubham Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Antara Assisted Care Services Limited | Antara Live Chat | BFSI | Fintech | Shubham Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹12,000 | 0 | ₹0.00 | 0 | ₹0.00 | 6 | ₹1,000.00 | 0 | ₹0.00 | ₹0 | ₹18,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 6 |  | ₹0.00 | ₹0.00
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Healthcare | Nutrition & Wellness Consulting | Aman Bothra | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹21,600 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹24,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Healthcare | Senior Living & Elder Care | Aman Bothra | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹22,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Healthcare | Senior Living & Elder Care | Aman Bothra | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Healthcare | Senior Living & Elder Care | Aman Bothra | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹22,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Asian Paints Limited | ap__asian-paints-prod |  |  | Rithika Salian | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 |  | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Atria Convergence Technologies Ltd | ACT Broadband 1 | IT & Technology | General | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Atria Convergence Technologies Ltd | ACT Broadband 2 | IT & Technology | General | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Atria Convergence Technologies Ltd | ACT Report | IT & Technology | General | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹8,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | BFSI | Housing Finance | Unnit Dedhia | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | BFSI | Housing Finance | Unnit Dedhia | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹30,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | BFSI | Housing Finance | Unnit Dedhia | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | BFSI | Housing Finance | Unnit Dedhia | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | BFSI | Housing Finance | Kapil Sharma | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹20,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Bajaj Housing Finance Limited | bh__online_home_loan |  |  | Kapil Sharma | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Bandhan AMC Limited | Bandhanamc__feedback |  |  | Sana Zarar | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
BigHaat Agro Private Limited | Bighaat | Agriculture & FMCG | General | Kunal Purohit | WhatsApp | No | Kevit | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 9 | ₹1,000.00 | 0 | ₹0.00 | ₹0 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 9 | ₹0.00 | ₹0.00 | ₹0.00
Board of Control for Cricket in India | IPL | Media & Entertainment | Sports (Cricket) |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹6,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | BFSI | NBFC | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | BFSI | NBFC | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | BFSI | NBFC (Loan Against Property) | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Classic Legends Private Limited | BSA Motorcycles | Other | General | Kapil Sharma | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹27,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Classic Legends Private Limited | JAWA Bikes | Other | General | Kapil Sharma | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹12,500 | ₹30,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹36,400 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Other | General | Kapil Sharma | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹270,000 | ₹27,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Credila Financial Services Limited | Credilla | BFSI | Education Loans | Utkarsh Bhansali | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹30,000 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Credila Financial Services Limited | hdfc__credila_wa |  |  | Utkarsh Bhansali | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Danone International Pvt Ltd | danone__bebeclub |  |  |  | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Danone International Pvt Ltd | danone__gm |  |  |  | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹72,508 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Danone International Pvt Ltd | danone__nutriclub |  |  |  | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹72,508 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
DCB Bank Ltd. | DCB | BFSI | General | Sana Zarar | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹6,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
DCB Bank Ltd. | DCB bot 2 | BFSI | General | Sana Zarar | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Other | General | Yash Shrisvatava | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹35,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹40,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Epifi Technologies Private Limited | Epify | IT & Technology | General | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 2 | ₹1,000.00 | 0 | ₹0.00 | ₹0 | ₹12,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 2 | ₹0.00 | ₹0.00 | ₹0.00
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod |  |  | Utkarsh Bhansali | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Equitas Small Finance Bank Limited | Equitas__equitaschatbot |  |  | Utkarsh Bhansali | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa |  |  | Paridhi Jain | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Haleon India | Sensodyne | Agriculture & FMCG | Oral Care |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HDFC Asset Management Company Ltd. | HDFC | BFSI | Bank | Rahul Sinha | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹20,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HDFC Asset Management Company Ltd. | HDFC 2 | BFSI | Bank | Rahul Sinha | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HDFC Asset Management Company Ltd. | HDFC Partner | BFSI | Bank | Rahul Sinha | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹20,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HDFC Asset Management Company Ltd. | HDFC Partner UAT | BFSI | Bank | Rahul Sinha | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HDFC Asset Management Company Ltd. | HDFC Development Charges | BFSI | Bank | Rahul Sinha | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹300,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹320,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HeidelbergCement India Limited | Heidelberg Cement | Manufacturing | General | Bijayine Sahoo | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹22,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HGI Industries Limited | HGI - TexZone | Media & Entertainment | Trade Shows & Exhibitions |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹5,400 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹6,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
IGP Commerce Private Limited | IGP | Ecommerce | Gifting |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹5,400 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹6,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Katyayani Organics | a__katyani-organics |  |  | Bijayine Sahoo | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | BFSI | Mutual Fund | Arun Singh | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹36,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹40,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | BFSI | Mutual Fund | Arun Singh | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹7,200 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹8,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Living Media India Ltd | Indiatoday - Magazine | Media & Entertainment | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹5,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 |  |  | Sunil Kumar | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot |  |  | Rahul Pillai | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nuvama Wealth Finance Limited | Nuvama Finance | BFSI | Wealth Management & Broking | Kunal Khatri | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹100,000 | ₹30,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹34,500 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nuvama Wealth Finance Limited | nuvama__meeting_feedback |  |  | Kunal Khatri | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹3,333 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot |  |  | Kunal Khatri | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹3,333 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses |  |  | Kunal Khatri | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹3,333 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Oona Insurance Pte. Ltd. | Oona Insurance | BFSI | General Insurance |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 |  | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Oona Insurance Pte. Ltd. | Oona Insurance 2 | BFSI | General Insurance |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹13,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 |  | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹13,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹28,800 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Porch Technologies Private Limited | Truva (Buyer) | IT & Technology | General | Shubhalaxmi Mohanty | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹6,300 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Porch Technologies Private Limited | Truva (CP) | IT & Technology | General | Shubhalaxmi Mohanty | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹6,300 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Porch Technologies Private Limited | Truva (Seller) | IT & Technology | General | Shubhalaxmi Mohanty | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹6,300 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Relaxo Footwears Ltd. | relaxo__relaxofootwear |  |  | Ankit Jain | WhatsApp | No | Internal | Live | 01/04/2026 |  | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹13,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Reliance General Insurance Co. Ltd | Reliance General Insurance | BFSI | General | Sana Zarar | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹5,400 | 0 | ₹0.00 | 0 | ₹0.00 | 3 | ₹500.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 |  | ₹0.00 |  | 3 |  | ₹0.00 | ₹0.00
Reserve Bank of India | RBI | BFSI | General | Nikhil Singh | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 |  | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | BFSI | General | Rithika Salian | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Shriram General Insurance Company Limited | Shriram General Insurance | BFSI | General | Rithika Salian | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹30,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Shriram General Insurance Company Limited | Shriram General Insurance (WL) |  |  | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 2 | ₹500.00 | 0 | ₹0.00 |  |  | 0 |  | ₹0.00 |  |  |  | ₹0.00 | ₹0.00
Sundaram Asset Management Company Limited | Sundaram Finance | BFSI | NBFC (Vehicle & Equipment Finance) | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹1,80,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | BFSI | NBFC (Vehicle & Equipment Finance) | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | BFSI | NBFC (Vehicle & Equipment Finance) | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹16,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | BFSI | Mutual Fund | Pranav Nand | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
SustLabs Private Limited | Sustlabs | IT & Technology | IoT & Energy Analytics |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹6,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 |  | ₹0.00 |  | 0 |  | ₹0.00 | ₹0.00
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹5,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹5,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Media & Entertainment | General | Apekshit Babaria | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | ZEE - TV | Media & Entertainment | General | Apekshit Babaria | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | Zee Bangla | Media & Entertainment | General | Apekshit Babaria | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | 20/06/2025 | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹5,400 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | Zee Telegu | Media & Entertainment | General | Apekshit Babaria | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | 01/09/2025 | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹10,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | a__zee_kannada |  |  | Apekshit Babaria | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹3,333 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | a__zeetelugu |  |  | Apekshit Babaria | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹3,333 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot |  |  | Apekshit Babaria | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹3,333 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zydus Wellness Products Limited | Zydus | Healthcare | Pharmaceuticals | Bijayine Sahoo | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹11,250 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹7,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
T.V. TODAY NETWORK LIMITED | GNT | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹5,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Netcore Private Limited | Netcore Internal Bot |  |  |  | WhatsApp | No | Kevit | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹4,500 | 0 | ₹0.00 | 0 | ₹0.00 | 9 | ₹1,000.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 9 |  | ₹0.00 | ₹0.00
| curtis__curtisagentchatbot |  |  |  | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 |  | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
| default_goodness |  |  |  | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Netcore Private Limited | Netcore__cspl |  |  |  | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production |  |  | Anand Lakshmanan | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 |  | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support |  |  | Sunil Kumar | WhatsApp | No | Internal | Live | 01/04/2026 | - | - | - | - | - | - | 01/04/2026 | - | - | Live | Live | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CureSkin Healthcare Private Limited | CureSkin | Healthcare | Dermatology & Skincare | Krishna Prasad | WhatsApp | No | Limechat | Lost | 02/04/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Royal International LNC | level-up.gg - Chatbot + CRM | Retail | Gaming & Electronics |  | WhatsApp | No | Limechat | Lost | 10/04/2026 | 13/04/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Time for Nature GmbH | Holzkern | Retail | Fashion Accessories & Watches | François (France-wa) Ismail | WhatsApp | No | Limechat | Lost | 10/04/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Art of Living Foundation | Art Of Living | Wellness & Spirituality | Yoga & Meditation |  | WhatsApp | No | Limechat | Lost | 14/04/2026 | 15/04/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
HT Digital Streams Limited | HT Digital | Media & Entertainment | News & Publishing |  | WhatsApp | No | Limechat | Lost | 14/04/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | Anveshan - 2 Way | Agriculture & FMCG | General | Shubham Jain | WhatsApp | No | Limechat | Lost | 16/04/2026 | 17/04/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
SPICE MONEY LIMITED | Spicemoney | Other | General | Shubham Jain | WhatsApp | No | Limechat | Lost | 22/04/2026 | 23/04/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Total Environment Building Systems Private Limited | Total Environment | Real Estate | Residential Developer |  | WhatsApp | No | Limechat | Lost | 25/04/2026 | 27/04/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Equitas Small Finance Bank Limited | Equitas | BFSI | Small Finance Bank | Harsh Shrivastava | RCS - S2C | No | Kevit | Live | 29/04/2026 | - | - | - | 25/06/2026 | - | 5 | 17/08/2026 | 30/06/2026 | - | Live | Live | Dealy of creatives first then approval to go live from clients end |  |  |  | ₹140,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹284,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
MILES EDUCATION PRIVATE LIMITED | Miles Education - CRM | Education | General | Aman Bothra | WhatsApp | No | Limechat | Lost | 29/04/2026 | 30/04/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Canara HSBC Life Insurance Company Limited | Canara HSBC (GATP, Renewal) | BFSI | General | Nakul Upreti | WhatsApp | No | Limechat | Lost | 01/05/2026 | 04/05/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Apollo Hospitals Enterprise Ltd | Apollo Hospitals | Healthcare | Hospitals | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Paused | 04/05/2026 | - | - | - | 05/05/2026 | - | - | 24/06/2026 | - | - | Live | Paused |  | 28/09/2026 |  |  | ₹200,000 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CredAvenue Private Limited (Yubi) | Yubi (Spocto & Yucollect) - Voice | BFSI | Fintech | Varun B | WhatsApp | No | Limechat | Lost | 04/05/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | ICICI Pru - NPS Feedback | BFSI | Life Insurance | Utkarsh Bhansali | WhatsApp | Yes | Limechat | UAT | 04/05/2026 | 21/06/2026 | Yes | 11/08/2026 | - | - | - |  |  |  |  | Date Missing | PO not received |  | Yes | 11/08/2026 | ₹468,000 | ₹36,000 | 0 | ₹0.00 | 0 | ₹0.00 | 65 | ₹1,061.00 | 0 | ₹0.00 | ₹520,000 | ₹40,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 65 | ₹1,179.00 | ₹0.00 | ₹0.00
AltInvest Online Platform Private Limited | Alt Invest | BFSI | Fintech |  | WhatsApp | No | Limechat | Lost | 08/05/2026 | 08/05/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Credila Financial Services Limited | Credila | BFSI | Education Loans | Utkarsh Bhansali | RCS - S2C | No | Kevit | Live | 08/05/2026 | 08/05/2026 | - | - | - | - | - | 02/07/2026 | - | - | Live | Live | Google took time to activate...bot was live on 29th July and deliver to the client.. |  |  |  | ₹150,000 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Travel & Aviation | Sports & Experiential Travel | Varun B | WhatsApp | No | Limechat | Live | 12/05/2026 | 13/05/2026 | Yes | 15/05/2026 | 18/05/2026 |  |  | 01/04/2026 |  | - | Live | Live |  |  |  |  | ₹0 | ₹2,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹2,500.00 | 0 | ₹0.00 | ₹0 | ₹3,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
TeamLease Services Limited | TeamLease Services | Professional Services | Staffing & HR | Varun B | WhatsApp | No | Limechat | Lost | 12/05/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
TVS Credit Services Ltd. | TVS Credit - CSPL | BFSI | NBFC | Rithika Salian | WhatsApp | No | Kevit | UAT | 14/05/2026 | 20/05/2026 | Yes | 21/07/2026 | 22/07/2026 | - | 10 |  | 01/08/2026 |  | -88 | Delayed | From Vendors end as they started working on it 6 days later.. Also Prod API's delayed from clients end |  |  |  | ₹50,000 | ₹6,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹65,000 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Canara HSBC Life Insurance Company Limited | Canara HSBC (Appointment) | BFSI | General | Nakul Upreti | WhatsApp | No | Limechat | Lost | 15/05/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Magicbricks Realty Services Limited | Magicbricks Home Loan Page & Home Loan | Real Estate | Property Portal | Meghana N | WhatsApp | No | Limechat | Quotes Given | 15/05/2026 | 27/05/2026 | [9 empty] | Date Missing |  |  |  |  | ₹0 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹2,500.00 | 0 | ₹0.00 | ₹0 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 |  | ₹0.00 | ₹0.00
POONAWALLA FINCORP LIMITED | Poonawalla - WhatsApp Calling | Other | General | Utkarsh Bhansali | WhatsApp | No | Limechat | Lost | 19/05/2026 | 20/05/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Skoda Auto Volkswagen India Private Limited | Skoda | Automotive | Auto OEM | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Live | 21/05/2026 | 22/05/2026 | - | - | 16/06/2026 | 03/07/2026 | 5 | 15/08/2026 | 21/06/2026 | - | Live | Live | All delays on receiving required things were from Clients side |  |  |  | ₹75,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Infocom Network Private Limited | Trade India | Ecommerce | B2B Marketplace |  | WhatsApp | No | Limechat | Lost | 25/05/2026 | 26/05/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nikon India Private Limited | Nikon | Manufacturing | Cameras & Imaging |  | WhatsApp | No | Limechat | Lost | 27/05/2026 | 28/05/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Max Life Insurance Co. Ltd. | Axis MaxLife (CTWA) | BFSI | Life Insurance | Rahul Sinha | WhatsApp | No | Limechat | Quotes Given | 29/05/2026 | 23/06/2026 | [9 empty] | Date Missing |  |  |  |  | ₹40,000 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹50,000 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Experian Credit Information Company of India Private Limited | Experian | BFSI | Credit Bureau | Apekshit Babaria | WhatsApp | No | Limechat | UAT | 01/06/2026 | - | Yes | 15/05/2026 | 18/06/2026 | 22/06/2026 | 21 |  | 09/07/2026 |  | -111 | Delayed | Agreement not signed due to 1 clause of data sharing |  |  |  | ₹40,000 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 |  | ₹2,500.00 | 0 | ₹0.00 |  | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Tally Solutions Pvt. Ltd. | Tally Solutions | IT & Technology | General | Kunal Purohit | WhatsApp | No | Limechat | Lost | 01/06/2026 | 01/06/2026 | - | - | - | - | - | - | - | - | Live | Lost | Client has no requirement as of now.. The entire project is on hold |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
INDIFI TECHNOLOGIES PRIVATE LIMITED | Indifi - Voicebot | IT & Technology | General | Paridhi Jain | WhatsApp | No | Limechat | Lost | 02/06/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
| IP Media - CRM | IT & Technology | Digital Agency | Rajiv | WhatsApp | No | Limechat | Lost | 03/06/2026 | 06/03/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Ecommerce | Books & Media | Sunil Kumar | WhatsApp | No | Limechat | Live | 04/06/2026 | 04/07/2026 | Yes | 29/04/2026 | 10/04/2026 | - | - | 01/04/2026 | - | - | Live | Live |  |  |  |  | ₹0 | ₹2,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹2,500.00 | 0 | ₹0.00 | ₹0 | ₹3,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
GRAMSTRONG E-SERVICES PRIVATE LIMITED | Toolsvilla | Agriculture & FMCG | General | Paridhi Jain | WhatsApp | No | Limechat | Lost | 04/06/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | Client wanted to know only about the features |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Muthoot Fincorp Ltd. | Muthoot Finance | BFSI | General | Pranav Nand | WhatsApp | No | Limechat | Discovery | 04/06/2026 | 05/06/2026 | [9 empty] | Date Missing | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  |  | 0 |  | ₹0.00 |  |  |  | ₹0.00 | ₹0.00
ANI TECHNOLOGIES PVT. LTD. | Ola | Travel & Aviation | Ride Hailing & Mobility | Pranav Nand | WhatsApp | No | Limechat | Discovery | 05/06/2026 | [10 empty] | Date Missing | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  |  | 0 |  | ₹0.00 |  |  |  | ₹0.00
MYDESIGNATION ONLINE CLOTHING | MyDesignation | Ecommerce | General | Varun B | WhatsApp | No | Limechat | Lost | 05/06/2026 | 08/06/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Sun TV Network Limited | Sun Bangla | Media & Entertainment | Television Broadcasting | Varun B | WhatsApp | No | Limechat | Live | 09/06/2026 | 02/07/2026 | Yes | 29/06/2026 | 02/07/2026 | - | - | 15/07/2026 | - | - | Live | Live |  |  | Yes |  | ₹27,000 | ₹13,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹2,500.00 | 0 | ₹0.00 | ₹30,000 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Curefit Healthcare Private Limited | Yoga Circle by Cult | Healthcare | Fitness & Wellness | Krishna Prasad | WhatsApp | No | Limechat | Quotes Given | 10/06/2026 | 11/06/2026 | [9 empty] | Date Missing |  |  |  |  | ₹30,000 | ₹30,000 | 0 | ₹0.00 | 2 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 |  | ₹0 | 0 |  | ₹2.00 |  | 0 |  | ₹0.00 | ₹0.00
Emergent Labs Inc | Emergent - CRM | IT & Technology | AI & SaaS | Sunil Kumar | WhatsApp | No | Limechat | Live | 12/06/2026 | 13/06/2026 | Yes | 29/06/2026 | 22/06/2026 | - | - | 30/06/2026 | - | - | Live | Live |  |  | Yes |  | ₹0 | ₹22,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹2,500.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
ION Exchange | Zero B | Manufacturing | Water Purification & Treatment | Krishna Prasad | WhatsApp | No | Kevit | Lost | 13/06/2026 | 13/06/2026 | - | - | - | - | - | - | - | - | Live | Lost | High quotes as he client was getting the same bot with MR of 5K from other vendors |  |  |  | ₹60,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 1 | ₹1,000.00 | 0 | ₹0.00 | ₹75,000 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Asian Paints Limited | Asian Paints (RCS) | Manufacturing | Paints & Chemicals | Rithika Salian | RCS | No | Kevit | Live | 15/06/2026 | - | - | - | 04/06/2026 | 19/08/2026 | 10 | 07/09/2026 | 14/06/2026 |  | Live | Live | Flows have been revised 3 times after being developed.. And delay from the client technical team in reverting back and sharing the API's |  |  |  | ₹5,000 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹12,000 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Asian Paints Limited | Asian Paints | Manufacturing | Paints & Chemicals | Rithika Salian | RCS - S2C | No | Kevit | Live | 15/06/2026 | - | - | - | 01/06/2026 | 19/08/2026 | 10 | 07/09/2026 | 11/06/2026 |  | Live | Live | Flows have been revised 3 times after being developed.. And delay from the client technical team in reverting back and sharing the API's |  |  |  | ₹40,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 |  | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Schloss Bangalore Limited | Leela Hotels | Hospitality | Hotels & Resorts | Unnit Dedhia | WhatsApp | No | Limechat | Discovery | 17/06/2026 | 18/06/2026 | [9 empty] | Date Missing | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  | ₹0 | 0 |  | ₹0.00 |  |  |  | ₹0.00 | ₹0.00
PUMA Sports India Pvt Ltd. | Puma | Retail | Apparel & Footwear | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Live | 19/06/2026 | 22/06/2026 | - | - | 01/07/2026 | 29/07/2026 | 5 | 12/08/2026 | 06/07/2026 | - | Live | Live | Template Issues |  |  |  | ₹50,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Axis Securities Ltd. | Axis Securities | BFSI | Life Insurance | Sana Zarar | WhatsApp | No | Limechat | Quotes Given | 21/06/2026 | 01/07/2026 | [9 empty] | Date Missing |  |  |  |  | ₹60,000 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹70,000 | ₹18,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CRIF High Mark Credit Information Services Private Limited | CRIF | BFSI | Credit Bureau | Sana Zarar | WhatsApp | No | Limechat | Quotes Given | 22/06/2026 | 25/06/2026 | [9 empty] | Date Missing |  |  |  |  | ₹80,000 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹125,000 | ₹50,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Ferns N Petals Pvt. Ltd. | FNP - WhatsApp-Based Complaint Ticket Creation Automation | Retail | Gifting & Flowers | Shubham Jain | WhatsApp | No | Kevit | Quotes Given | 23/06/2026 | 26/06/2026 | [9 empty] | Date Missing |  |  |  |  | ₹75,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹90,000 | ₹20,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Max Life Insurance Co. Ltd. | Axis Max Life (CC Liability video WA) | BFSI | General | Rahul Sinha | WhatsApp | No | Limechat | Quotes Given | 23/06/2026 | 29/06/2026 | Yes | 17/04/2026 | 01/07/2026 | [6 empty] | Date Missing |  |  |  |  | ₹0 | ₹12,000 | 0 | ₹0.00 | 0 |  |  | ₹2,500.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 |  | ₹0.00 |  |  |  | ₹0.00 | ₹0.00
Eternal Limited | Zomato (District Dining) | Ecommerce | Food Delivery | Sunil Kumar | WhatsApp | No | Limechat | On Hold | 25/06/2026 | - | - | - | [7 empty] | On Hold | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  | ₹0 | 0 |  | ₹0.00 |  |  |  | ₹0.00
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | Aditya Birla Sun Life Insurance | BFSI | Life Insurance | Madhusha Bhati | WhatsApp | No | Limechat | On Hold | 29/06/2026 | - | - | - |  |  | 10 |  |  |  |  | On Hold | PO not received | [5 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  | ₹0 | 0 |  | ₹0.00 |  |  |  | ₹0.00
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Automotive | Two-Wheeler OEM | Shubham Jain | RCS - S2C | No | Kevit | Live | 30/06/2026 |  | - | - | 13/08/2026 | 08/09/2026 | 7 | 11/09/2026 | 20/08/2026 | 21/05/2153 | Live | Live | RCS panel was not created and client delayed in sharing the BRD and then template creation took time |  |  |  | ₹150,000 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Porch Technologies Private Limited | Truva | IT & Technology | General | Shubhalaxmi Mohanty | WhatsApp | No | Kevit | On Hold | 30/06/2026 | - | - | - |  |  | 10 |  |  |  |  | On Hold | [6 empty] | 0 | ₹0.00 | 0 |  | 0 |  | 0 | ₹0.00 |  | ₹0 | 0 |  | ₹0.00 |  | 0 |  | ₹0.00
Max Life Insurance Co. Ltd. | Axis MaxLife DSF Bot Flow | BFSI | General | Rahul Sinha | WhatsApp | No | Limechat | Development | 01/07/2026 |  | No | 13/08/2026 | 13/08/2026 |  | 5 |  | 18/08/2026 |  | -71 | Delayed | PO not received from Sales |  | Yes |  | ₹0 | ₹22,500 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Shriram Asset Management Company Limited | Shriram Finance - RCS & Whatsapp | BFSI | General | Rithika Salian | WhatsApp | No | Kevit | Quotes Given | 01/07/2026 | 02/07/2026 | [9 empty] | Date Missing |  |  |  |  | ₹30,000 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹50,000 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
NARAYANA HRUDAYALAYA LIMITED | Narayan Group | Healthcare | Hospitals | Krishna Prasad | WhatsApp | No | Limechat | Discovery | 02/07/2026 | [10 empty] | Date Missing | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  | ₹0 | 0 |  | ₹0.00 |  |  |  | ₹0.00
Shadowfax Technologies Private Limited | Shadowfax | IT & Technology | General | Krishna Prasad | WhatsApp | No | Limechat | Lost | 04/07/2026 | 14-04-2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
FINO PAYMENTS BANK LIMITED | Fino Payments Bank | BFSI | Payments Bank | Bbijal Panchmmattya | RCS - S2C | No | Kevit | UAT | 09/07/2026 | 15/07/2026 | - | - | 12/09/2026 | 22/09/2026 | 6 |  | 18/09/2026 |  | -40 | Delayed | Client Internal Compliance Issues |  |  |  | ₹45,000 | ₹9,900 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | 0.00 | ₹0.00
Tally Solutions Pvt. Ltd. | Tally Solutions - WhatsApp Calling | IT & Technology | General | Kunal Purohit | WhatsApp | No | Limechat | Lost | 10/07/2026 | 24/07/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | BFSI | Mutual Fund | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Live | 12/07/2026 | 13/07/2026 | - | - | 07/08/2026 |  | 10 | 24/09/2026 | 17/08/2026 |  | Live | Live | BRD and RCS enabling took time |  |  |  | ₹180,000 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | BFSI | Mutual Fund | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Live | 12/07/2026 | 13/07/2026 | - | - | 07/08/2026 | 11/09/2026 | 10 | 24/09/2026 | 17/08/2026 | 06/06/2153 | Live | Live | BRD and RCS enabling took time |  |  |  | ₹0 | ₹7,272 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Indian Bank | Indian Bank | BFSI | Bank | Aman Bothra | WhatsApp | No | Kevit | Quotes Given | 13/07/2026 | 14/07/2026 | [9 empty] | Date Missing |  |  |  |  | ₹500,000 | ₹40,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹625,000 | ₹60,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Anjali Mukerjee Health Total Private Limited | Health Total | Healthcare | Nutrition & Wellness Consulting | Narayanan Iyer | WhatsApp | No | Kevit | Live | 15/07/2026 | 16/07/2026 | - | - | 17/07/2026 | 28/07/2026 | 5 | 22/09/2026 | 22/07/2026 |  | Live | Live | Awaiting update from Narayanan. New whatsapp number needs to be enabled...Whatsapp numbers got onboarded on 24 Aug. Demo scheduled for 27 Aug. |  |  |  | ₹50,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹60,000 | ₹12,000 | 0 |  | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Bajaj Housing Finance Limited | Bajaj Housing Finance (BHFL) - Service Bot - 5 Numbers | BFSI | Housing Finance | Kapil Sharma | WhatsApp | No | Kevit | Quotes Given | 15/07/2026 | 22/07/2026 |  |  |  |  | 20 |  |  |  |  | Date Missing |  |  |  |  | ₹160,000 | ₹50,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹220,000 | ₹75,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Magicbricks Realty Services Limited | Magic Bricks | Real Estate | Property Portal | Meghana N | RCS | No | Kevit | Quotes Given | 15/07/2026 | 24/07/2026 |  |  |  |  | 20 |  |  |  |  | Date Missing |  |  |  |  | ₹180,000 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹220,000 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Mahindra First Choice Wheels | Mahindra First Choice | Automotive | Used Vehicles | Narayanan Iyer | WhatsApp | No | Kevit | Lost | 15/07/2026 | 15/07/2026 | - | - | - | - | - | - | - | - | Live | Lost | Clients ask for somethg else..currently they dont want to build the chatbot |  |  |  | ₹8,000 | ₹35,000 | 10,000 | ₹0.00 | 0 | ₹0.00 | 0 | ₹1,000.00 | 0 | ₹0.00 | ₹10,000 | ₹45,000 | 15,000 | ₹0.00 | ₹0.00 | ₹0.00 | 1 | ₹1,250.00 | ₹0.00 | ₹0.00
Perfios Account Aggregation Services Pvt Ltd | Anumati | BFSI | Fintech | Krishna Prasad | WhatsApp | No | Limechat | Lost | 15/07/2026 | 16/07/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹50,000 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹65,000 | ₹18,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
TVS Credit Services Ltd. | TVS Credit - Insta PL | Retail | Fashion & Lifestyle Marketplace | Rithika Salian | WhatsApp | No | Kevit | Quotes Given | 15/07/2026 | 16/07/2026 |  |  |  |  | 45 |  |  |  |  | Date Missing |  |  |  |  | ₹300,000 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹400,000 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nilkamal Limited | Nilkamal | Manufacturing | Furniture | Narayanan Iyer | WhatsApp | No | Kevit | Quotes Given | 16/07/2026 | 20/07/2026 | [9 empty] | Date Missing |  |  |  |  | ₹250,000 | ₹35,000 | 10,000 | ₹2.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹300,000 | ₹42,000 | 10,000 | ₹2.50 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Sharekhan Ltd | Sharekhan | BFSI | Broking & Financial Services | Sana Zarar | WhatsApp | No | Kevit | Quotes Given | 17/07/2026 | 21/07/2026 | [9 empty] | Date Missing |  |  |  |  | ₹20,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹35,000 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Media & Entertainment | General | Apekshit Babaria | WhatsApp | No | Consense | Live | 17/07/2026 | 20/07/2026 | - | - | 20/07/2026 | - | - | 31/07/2026 | - | - | Live | Live | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  |  | 0 |  | ₹0.00 |  |  |  | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | ZEE5 ¦ Whatsapp Subscription Native Journey | Media & Entertainment | General | Apekshit Babaria | WhatsApp | No | Kevit | Lost | 20/07/2026 | 20/07/2026 | - | - | - | - | - | - | - | - | Live | Lost | No update from the client yet..Upon follow up AM ask to drop it as client is not revreting back |  |  |  | ₹35,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹75,000 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Bandhan AMC Limited | Bandhan AMC - Investors | BFSI | Broking & Financial Services | Sana Zarar | WhatsApp | No | Kevit | Quotes Given | 20/07/2026 | 03/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹117,000.00 | ₹18,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹150,000 | ₹50,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Bandhan AMC Limited | Bandhan AMC - VRM | BFSI | Broking & Financial Services | Sana Zarar | WhatsApp | No | Kevit | Quotes Given | 20/07/2026 | 03/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹27,000.00 | ₹18,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 1 | ₹1,260.00 | 0 | ₹0.00 | ₹40,000 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 1 | ₹1,500.00 | ₹0.00 | ₹0.00
Bandhan AMC Limited | Bandhan AMC - Distributor | BFSI | Broking & Financial Services | Sana Zarar | WhatsApp | No | Kevit | Quotes Given | 20/07/2026 | 03/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹63,000.00 | ₹18,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹80,000 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Gulf Oil Lubricants India Limited | Gulf Oil Lubricants | Manufacturing | Lubricants | Arun Singh | WhatsApp | No | Limechat | Discovery | 20/07/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  |  |  | ₹0.00 |  |  |  | ₹0.00
Poh Kong Holdings Berhad | Poh Kong (Malaysia) | Retail | Jewellery | Stallon Rego | WhatsApp | No | Limechat | Quotes Given | 20/07/2026 | 05/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹23,623 | ₹23,623 | 0 | ₹0.00 | 0 | ₹1.89 | 0 | ₹0.00 | 0 | ₹0.00 | ₹37,796 | ₹30,709 | 0 | ₹0.00 | ₹0.00 | ₹3.78 | 0 | ₹0.00 | ₹0.00 | ₹0.00
SBI Life Insurance Company Limited | SBI Life Insurance | BFSI | Life Insurance | Arun Singh | WhatsApp | No | Talk.ai | Discovery | 20/07/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  |  |  | ₹0.00 |  |  |  | ₹0.00
Credila Financial Services Limited | Credila NPS - 3 Journey | BFSI | Education Loans | Utkarsh Bhansali | WhatsApp | No | Kevit | Live | 22/07/2026 | 23/07/2026 | - | - | - | - | - | 01/07/2027 | - | - | Live | Live | - |  |  |  | ₹50,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Credila Financial Services Limited | Credila NPS - Disbursement+Form Changes | BFSI | Education Loans | Utkarsh Bhansali | WhatsApp | No | Kevit | Live | 22/07/2026 | 23/07/2026 | - | - | - | - | - | 01/07/2027 | - | - | Live | Live | - |  |  |  | ₹38,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Astitva Tech Labs Pvt Ltd | Platinum Love Bands | Retail | Jewellery (Wedding Bands) | Bbijal Panchmmattya | WhatsApp | No | Kevit | Lost | 22/07/2026 | 27/07/2026 | - | - | - | - | - | - | - | - | Live | Lost | Too high price as per the client. |  |  |  | ₹100,000 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹150,000 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Atria Convergence Technologies Ltd | ACT Fibernet - EB Customers | IT & Technology | General | Pranav Nand | WhatsApp | No | Kevit | Lost | 22/07/2026 | 24/07/2025 | - | - | - | - | - | - | - | - | Live | Lost | Client has put everything on hold for now as they dont have this requirement as of now |  |  |  | ₹40,000 | ₹10,000 | 600 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹60,000 | ₹20,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | BFSI | Education Loans | Utkarsh Bhansali | WhatsApp | No | Kevit | Live | 22/07/2026 | 23/07/2026 | Yes | 30/07/2026 | 31/07/2026 | 06/08/2028 | 10 | 10/08/2026 | 10/08/2026 | - | Live | Live |  |  |  |  | ₹80,000 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹100,000 | ₹12,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
GRT Jewellers (India) Pvt. Ltd. | GRT Jewels | Other | General | Kunal Purohit | WhatsApp | No | Limechat | Discovery | 22/07/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  |  |  | ₹0.00 |  |  |  | ₹0.00
Asian Paints Limited | Asian Paints - Offline Customers - Whatsapp | Manufacturing | Paints & Chemicals | Rithika Salian | WhatsApp | No | Kevit | UAT | 23/07/2026 | 01/08/2026 | - | - | 04/08/2026 | 19/08/2026 | 9 |  | 13/08/2026 |  | -76 | Delayed | Whatsapp new number onbaording pending from clients end. |  |  |  | ₹72,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹110,000 | ₹25,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CheQ Digital Private limited | Cheq - AI Power Journey for CC | BFSI | Fintech | Krishna Prasad | WhatsApp | No | Limechat | Quotes Given | 23/07/2026 | 21/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹50,000 | ₹30,000 |  | ₹0.00 | 0 |  |  | ₹2,000.00 | 0 | ₹0.00 | ₹60,000 | ₹36,000 |  | ₹0.00 | ₹0.00 |  |  | ₹2,500.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | BFSI | NBFC (Loan Against Property) | Pranav Nand | WhatsApp | No | Kevit | Live | 23/07/2026 | 23/07/2026 | - | - | 24/07/2026 | - | 0 | 24/07/2026 | 24/07/2026 | - | Live | Live |  |  |  |  | ₹0 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | BFSI | General | Kunal Khatri | WhatsApp | No | Kevit | Live | 23/07/2026 | 24/07/2026 | - | - | 31/07/2026 | - | 7 | 05/08/2026 | 07/08/2026 | - | Live | Live |  |  |  |  | ₹90,000 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹100,000 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | BFSI | NBFC (Home Loans) | Pranav Nand | WhatsApp | No | Kevit | Live | 24/07/2026 | 24/07/2026 | - | - | 27/07/2026 | - | 0 | 27/07/2026 | 27/07/2026 | - | Live | Live |  |  |  |  | ₹0 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | BFSI | NBFC (SME Loans) | Pranav Nand | WhatsApp | No | Kevit | Live | 24/07/2026 | 24/07/2026 | - | - | 27/07/2026 | - | 0 | 27/07/2026 | 27/07/2026 | - | Live | Live |  |  |  |  | ₹0 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | BFSI | NBFC (Loan Against Property) | Pranav Nand | WhatsApp | No | Kevit | Live | 24/07/2026 | 24/07/2026 | - | - | 27/07/2026 | - | 0 | 31/07/2026 | 27/07/2026 | - | Live | Live | As no was not onboarded |  |  |  | ₹0 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
SidsFarm Pvt Limited | SidsFarm - Whatsapp Survey | Agriculture & FMCG | Dairy & Milk Delivery | Varun B | WhatsApp | No | Limechat | Discovery | 25/07/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  |  |  | ₹0.00 |  |  |  | ₹0.00
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Agriculture & FMCG | Sugar Substitutes & Health Foods | Bbijal Panchmmattya | WhatsApp | No | Kevit | Live | 27/07/2026 | 28/07/2026 | Yes | 30/07/2026 | 30/07/2026 | 03/08/2026 | 5 | 04/08/2026 | 04/08/2026 | - | Live | Live |  |  |  |  | ₹16,000 | ₹6,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹30,000 | ₹6,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
AAKASH EDUCATIONAL SERVICES LIMITED | Akash - AESL - Chatbot Flows & Response Logging for 5 numbers | Retail | Fashion & Lifestyle / E-commerce | Tejasvi Heer | WhatsApp | No | Limechat | Quotes Given | 28/07/2026 | 31/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹40,000.00 | ₹30,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹55,000 | ₹40,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Channel Packaging Pvt Ltd | Channel Packaging Pvt Ltd – Food Packaging Solutions | Manufacturing | Packaging | Dhiraj Shivrati | WhatsApp | No | Limechat | Quotes Given | 28/07/2026 | 30/07/2026 | [9 empty] | Date Missing |  |  |  |  | - | ₹25,000 | 0 | ₹2.00 | 0 | ₹0.00 | 0 | ₹2,500.00 | 0 | ₹0.00 | - | ₹35,000 | 0 | ₹3.00 | ₹0.00 | ₹0.00 | 0 | ₹3,500.00 | ₹0.00 | ₹0.00
FABINDIA LIMITED | Fabindia - Chatbot & Inbox Commerce | Other | General | Tejasvi Heer | WhatsApp | No | Limechat | Quotes Given | 28/07/2026 | 31/07/2026 | [9 empty] | Date Missing |  |  |  |  | ₹25,000 | ₹15,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹25,000 | ₹20,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 |  | ₹0.00 | ₹0.00
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | BFSI | Mutual Fund | Pranav Nand | WhatsApp | No | Kevit | Live | 28/07/2026 | 28/07/2026 | Yes | 31/07/2026 | 20/07/2026 | 22/07/2026 | - | 07/08/2026 | - | - | Live | Live |  |  |  |  | ₹31,500 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹35,000 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Battery Smart Private Limited | Battery Smart - Whatsapp Flow | Automotive | EV Battery Swapping | Sunil Kumar | WhatsApp | No | Limechat | Development | 30/07/2026 | 31/07/2026 | Yes | 15/09/2026 | 17/09/2026 |  | 7 |  | 24/09/2026 |  | -34 | Delayed |  |  | Yes | 16/09/2026 | ₹22,000 | ₹25,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹1,500.00 | 0 | ₹0.00 | ₹30,000 | ₹28,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹2,000.00 | ₹0.00 | ₹0.00
Fave Group Pte. Ltd. | Fave - Chatbot BRD | BFSI | Fintech | Sunil Kumar | WhatsApp | No | Limechat | Discovery | 30/07/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  |  |  | ₹0.00 |  |  |  | ₹0.00
Ethniq Ayush Exports LLP | Ethniq | Retail | Food Products | Rithika Thakur | WhatsApp | No | Kevit | Discovery | 03/08/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  |  |  | ₹0.00 |  |  |  | ₹0.00
HSBC Asset Management India Private Limited | HSBC MF | BFSI | General | Harsh Shrivastava | RCS - S2C | No | Kevit | Live | 03/08/2026 | 10/08/2026 | - | - | 07/09/2026 | 11/09/2026 | 3 | 16/09/2026 | 10/09/2026 | 29/05/2153 | Live | Live |  |  |  |  | ₹54,000 | ₹9,900 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | BFSI | Broking & Financial Services | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Live | 03/08/2026 | 05/08/2027 | - | - | 06/08/2026 |  | 10 | 24/09/2026 | 16/08/2026 |  | Live | Live | BRD and RCS enabling took time |  |  |  | ₹60,000 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit - Dealer One Window | BFSI | Housing Finance | Unnit Dedhia | WhatsApp | No | Kevit | UAT | 04/08/2026 | 05/08/2026 |  |  | 07/08/2026 | 11/08/2028 | 5 |  | 12/08/2026 |  | -77 | Delayed | changes as the data that was passed was not reflecting correctly for modifying the API's at client end to reflect correct data..plus the client kept testing the bot for more than 20 days in UAT mode |  |  |  | 276000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ₹0.00 | 300000 | 0 | 0 | 0 | ₹0.00 | 0 | 0 | 0 | ₹0.00 | 0
Savaari Car Rentals Pvt Ltd | Savaari Car Rentals | Other | General | Pranav Nand | WhatsApp | No | Limechat | Discovery | 04/08/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  |  |  | ₹0.00 |  |  |  | ₹0.00
IIFL Finance Limited | IIFL Finance - Voicebot | BFSI | NBFC | Madhusha Bhati | WhatsApp | No | Limechat | Lost | 05/08/2026 | 05/08/2026 | - | - | - | - | - | - | - | - | Live | Lost | - |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
TVS Credit Services Ltd. | TVS Credit - Vernacular Bot | Travel & Aviation | Airline | Rithika Salian | WhatsApp | No | Kevit | Quotes Given | 05/08/2026 | 06/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹18,000 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹2,000.00 | 0 | ₹0.00 | ₹25,000 | ₹15,000 | 0 | ₹5.00 | ₹0.00 | ₹3.00 | 0 | ₹2,500.00 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | Zee5 Chatbot & AI voice Agent | Media & Entertainment | General | Apekshit Babaria | WhatsApp | No | Limechat | On Hold | 05/08/2026 | - | - | - | [7 empty] | On Hold | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  |  | 0 |  | ₹0.00 |  |  |  | ₹0.00
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | BFSI | Fintech | Kapil Sharma | RCS - S2C | No | Kevit | Live | 06/08/2026 | 11/08/2026 | - | - | 12/08/2026 | 08/09/2026 | 20 | 11/09/2026 | 01/09/2026 | 21/05/2153 | Live | Live | Delayed reverts from clients end |  |  |  | ₹45,000 | ₹10,800 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Bajaj Finserv Direct Ltd | BFDL | BFSI | NBFC | Kapil Sharma | RCS - S2C | No | Kevit | Live | 06/08/2026 | 11/08/2026 | - | - | 07/09/2026 | 08/09/2026 | 3 | 11/09/2026 | 10/09/2026 | 21/05/2153 | Live | Live |  |  |  |  | ₹180,000 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Exotic Mile Private Limited | Boult Audio | Retail | Consumer Electronics & Audio | Sammaskh Nayyar | WhatsApp | No | Limechat | Quotes Given | 06/08/2026 | 10/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹50,000 | ₹25,000 | 0 | ₹0.00 | 0 | ₹2.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹60,000 | ₹28,000 | 0 | ₹0.00 | ₹0.00 | ₹2.50 | 0 | ₹0.00 | ₹0.00 | ₹0.00
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | Tata 1MG | Healthcare | General | Shubham Jain | RCS - S2C | No | Kevit | Quotes Given | 06/08/2026 | 12/08/2028 | - | - |  |  | 15 |  |  |  |  | Date Missing | Google unable to cater to Healthcare brands |  |  |  | 200000 | 20000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹1,200.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | 0.00 | ₹0.00
Max Life Insurance Co. Ltd. | Axis Max Life - Cross sell bot | BFSI | Life Insurance | Rahul Sinha | WhatsApp | No | Limechat | Quotes Given | 09/08/2026 | 09/08/2026 | [9 empty] | Date Missing | [6 empty] | 0 | ₹0.00 | 0 |  |  |  | 0 | ₹0.00 |  |  | 0 |  | ₹0.00 |  |  |  | ₹0.00 | ₹0.00
CAPRI GLOBAL CAPTIAL LIMITED | Capri Loans | BFSI | NBFC | Unnit Dedhia | WhatsApp | No | Kevit | Quotes Given | 10/08/2026 | 11/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹162,000 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 | 1 | ₹1,080.00 | 0 | ₹0.00 | ₹200,000 | ₹22,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 1 | ₹1,350.00 | ₹0.00 | ₹0.00
People Interactive (India) Private Limited | People Interactives - Shaadi.com | IT & Technology | Matrimonial Platform | Bbijal Panchmmattya | RCS - S2C | No | Kevit | UAT | 10/08/2026 | 12/08/2026 | - | - | 07/09/2026 | 24/09/2026 | 3 |  | 10/09/2026 |  | -48 | Delayed |  |  |  |  | ₹45,000.00 | ₹9,900.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
PROSPERR.IO PRIVATE LIMITED | Prosperr.io | Other | General | Meghana N | Other | No | Kevit | Lost | 10/08/2026 | 11/08/2026 | - | - | - | - | - | - | - | - | Live | Lost | The requirement was for whatsapp calling charges and not bot creation |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Simk Labels Private Limited | Kopara Clean |  |  | Yash Shrivastava | WhatsApp | No | Talk.ai | Lost | 11/08/2026 | 25/08/2026 | [9 empty] | Lost |  |  |  |  | ₹270,000 | ₹36,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹4.00 | 0 | ₹0.00 | ₹330,000 | ₹44,000 | 0 | ₹0.00 | ₹0.00 | ₹5.00 | 0 |  | ₹0.00
Star Health and Allied Insurance Company Limited | Star Health | BFSI | Health Insurance | Harsh Shrivastava | RCS - S2C | No | Kevit | Lost | 11/08/2026 | 12/08/2026 | - | - | [7 empty] | Lost |  |  |  |  | ₹63,000 | ₹10,800 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
| Ekke - Whatsapp Commerce | Retail | Fashion & Lifestyle Marketplace | Subhalaxmi Mohanty | WhatsApp | No | Kevit | Discovery | 11/08/2026 | [10 empty] | Date Missing | [8 empty] | 0 | ₹0.00 |  |  | 0 | ₹0.00 | ₹861,709 |  |  |  | ₹0.00 | ₹0.00 |  |  | ₹0.00
5paisa Capital Limited | 5Paisa – WhatsApp AI Outbound Calls | BFSI | Broking & Financial Services | Kapil Sharma | WhatsApp | No | Kevit | Lost | 12/08/2026 | - | - | - | - | - | - | - | - | - | Live | Lost | Client will built eveything by themself currently they need is only whatsapp calling rates |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Rentokil Initial Hygiene India Private Limited | Rentokil India | Business Services | Pest Control & Hygiene Services | Unnit Dedhia | WhatsApp | No | Limechat | Development | 12/08/2026 |  | Yes | 08/04/2026 | 13/08/2026 |  | 5 |  | 18/08/2026 |  | -71 | Delayed | BRD not done. |  | Yes | 24/09/2026 | ₹45,000 | ₹12,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹65,000 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
AIR INDIA EXPRESS LIMITED | Air India Express - Ancillary Upsell on WhatsApp | Other | General | Astha Jain | WhatsApp | No | Limechat | Discovery | 13/08/2026 | [10 empty] | Date Missing |  |  |  |  | ₹140,000.00 | ₹75,000.00 |  | ₹0.00 | 0 | ₹0.00 |  | ₹2,500.00 | 0 | ₹0.00 |  | ₹5,500 |  |  | ₹0.00 |  |  | ₹3,800.00 | ₹0.00
Extramarks Education India Private Limited | Extramarks - WhatsApp Bot | Business Services | Pest Control & Hygiene Services | Tejasvi Heer | WhatsApp | No | Limechat | Quotes Given | 14/08/2026 | 17/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹50,000 | ₹125,000 | 0 | ₹4.50 | 0 | ₹2.50 | 0 | ₹2,000.00 | 0 | ₹0.00 | ₹66,000 | ₹200,000 | 0 | ₹5.00 | ₹0.00 | ₹3.00 | 0 | ₹2,750.00 | ₹0.00 | ₹0.00
TVS Credit Services Ltd. | TVS Credit - OMPL | BFSI | NBFC | Rithika Salian | WhatsApp | No | Kevit | Quotes Given | 14/08/2026 | 14/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹18,000 | ₹9,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹25,000 | ₹15,000 | 0 |  | ₹0.00 | ₹0.00 | 0 |  | ₹0.00 | ₹0.00
Bank of Baroda | Bank of Baroda - BOB Cards | BFSI | Public Sector Bank | Harsh Shrivastava | RCS - S2C | No | Kevit | Development | 17/08/2026 | 01/09/2026 | - | - | 08/09/2026 |  | 2 |  | 10/09/2026 |  | -48 | Delayed |  |  |  |  | ₹45,000.00 | ₹9,900.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹284,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Bharti Airtel Limited | Airtel | IT & Technology | Telecommunications | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Lost | 17/08/2026 |  | - | - | [7 empty] | Lost | [6 empty] | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Haier Appliances India Private Limited | Haier Appliances | Manufacturing | Home Appliances & Consumer Electronics | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Lost | 17/08/2026 |  | - | - | [7 empty] | Lost | [6 empty] | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Razorpay Payments Private Limited | Razorpay | BFSI | Fintech & Digital Payments | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Lost | 17/08/2026 |  | - | - | [7 empty] | Lost | [6 empty] | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Manufacturing | Automotive | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Live | 17/08/2026 |  | - | - | 07/09/2026 | 08/09/2026 | 3 | 24/09/2026 | 10/09/2026 | 03/06/2153 | Live | Live | Went Live |  |  |  | ₹45,000.00 | ₹9,900.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹2,000.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
| Aashni + Co | Retail | Luxury Fashion & Designer Marketplace | Varun B | WhatsApp | No | Limechat | Development | 17/08/2026 | 17/08/2026 | [9 empty] | Date Missing |  |  | Yes |  | ₹30,000 | ₹30,000 | 0 | ₹0.00 | 0 | ₹2.50 | 0 | ₹2,000.00 | 0 | ₹0.00 | ₹35,000 | ₹40,000 | 0 | ₹0.00 | ₹0.00 | ₹3.00 | 0 | ₹2,500.00 | ₹0.00 | ₹0.00
Coronation Insurance Plc | Coronation Insurance – WhatsApp Requirement | BFSI | General Insurance | Kishore Kumar | WhatsApp | No | Kevit | Quotes Given | 18/08/2026 | 19/08/2026 | [9 empty] | Date Missing |  |  |  |  | ₹500,000 | ₹50,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹550,000 | ₹60,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
InCred Financial Services Limited | InCred | BFSI | NBFC & Digital Lending | Harsh Shrivastava | RCS - S2C | No | Kevit | Live | 19/08/2026 | 24/08/2026 | - | - | 07/09/2026 |  | 7 | 24/09/2026 | 14/09/2026 |  | Live | Live |  |  |  |  | ₹45,000 | ₹1,080 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Chegutu Municipality | Municipality of Chegutu | Other | Government & Municipal Administration | Kishore Kumar | WhatsApp | Yes | Kevit | Discovery | 21/08/2026 | 21/08/2026 | [9 empty] | Date Missing | [12 empty] | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Apollo Hospitals Enterprise Ltd | Apollo Hospitals - Template Configuration for Appointment Booking Flow | Healthcare | Hospitals | Aman Bothra | WhatsApp | No | Kevit | Live | 25/08/2026 | 25/08/2026 |  |  | 23/10/2026 |  | 3 | 26/10/2026 | 26/10/2026 |  | Live | Live | Went Live |  |  |  | ₹0 | ₹14,400 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹30,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Nuvama Wealth Finance Limited | Nuvama - New CSAT - Rating Bot on no 7304470488 |  |  | Kunal Khatri | WhatsApp | No | Internal | UAT | 25/08/2026 | 25/08/2026 |  |  | 30/08/2026 |  | 5 |  | 04/09/2026 |  | -54 | Delayed | Awaiting client approval on commercials |  |  |  | ₹0 | ₹0 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹45,000 | ₹0 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
PAYU PAYMENTS PRIVATE LIMITED | PayU | BFSI | General | Bbijal Panchmmattya | RCS - S2C | No | Kevit | UAT | 26/08/2026 | 01/09/2026 | - | - |  | 24/09/2026 | 14 |  |  |  |  | Date Missing |  |  |  |  | ₹54,000.00 | ₹9,900.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
POONAWALLA FINCORP LIMITED | Poonawalla Fincorp - Discovery Call & Commercials | Other | General | Utkarsh Bhansali | WhatsApp | No | Kevit | Discovery | 26/08/2026 | [10 empty] | Date Missing |  |  |  |  | ₹0.00 | ₹0.00 |  | ₹0.00 | 0 | ₹0.00 |  | ₹0.00 | 0 | ₹0.00 |  |  | 0 | ₹0.00 | ₹0.00 | ₹0.00 |  | ₹0.00 | ₹0.00 | ₹0.00
TAJBank Limited | Taj Bank - Whatspp and Website AI Bot | BFSI | Non-Interest Bank | Kishore Kumar | WhatsApp | Yes | Kevit | Discovery | 26/08/2026 | [10 empty] | Date Missing | [8 empty] | 0 |  |  |  | 0 | ₹0.00 |  |  | 0 |  | ₹0.00 |  |  |  | ₹0.00
AAKASH EDUCATIONAL SERVICES LIMITED | Aakash Institute | BFSI | NBFC & Digital Lending | Harsh Shrivastava | RCS - S2C | No | Kevit | UAT | 27/08/2026 | 01/09/2026 | - | - | 07/09/2026 |  | 20 |  | 27/09/2026 |  | -31 | Delayed |  |  |  |  | ₹90,000 | ₹18,000 | 0 | ₹0.00 | 0 | ₹0.00 | 1 | ₹1,080.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Credo Brands Marketing Limited | Mufti Jeans |  |  | Narayanan Iyer | WhatsApp | No | Kevit | Quotes Given | 31/08/2026 | 01/09/2026 | [9 empty] | Date Missing |  |  |  |  | ₹225,000.00 | ₹31,500.00 | 0 | ₹2.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹275,000 | ₹38,500 | 0 | ₹2.50 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Time for Nature GmbH | Holzkern |  |  | François (France-wa) Ismail | WhatsApp | No | Kevit | Quotes Given | 31/08/2026 | 01/09/2026 | [9 empty] | Date Missing |  |  |  |  | ₹225,000.00 | ₹31,500.00 | 0 | ₹2.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹275,000 | ₹40,000 | 0 | ₹2.50 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Xiaomi Corporation | Xiaomi |  |  | Bbijal Panchmmattya | RCS - S2C | No | Kevit | Discovery | 31/08/2026 |  | - | - | [7 empty] | Date Missing | [6 empty] | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Fluidi5 Technologies Private Limited | Voiz |  |  | Krishna Prasad | WhatsApp | No | Kevit | Quotes Given | 03/09/2026 | 03/09/2026 | [9 empty] | Date Missing |  |  |  |  | ₹13,500.00 | ₹9,900.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹22,000 | ₹17,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
GRT Jewellers (India) Pvt. Ltd. | GRT Jewellers |  |  | Aman Bothra | RCS - S2C | No | Kevit | Discovery | 07/09/2026 | [10 empty] | Date Missing | [6 empty] | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹284,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Geojit Technologies (P) Ltd | Geojit ¦ Marketing Lead Qualification Chatbot |  |  | Aman Bothra | WhatsApp | No | Kevit | Quotes Given | 07/09/2026 | 08/09/2026 | [9 empty] | Date Missing |  |  |  |  | ₹45,000.00 | ₹1,080.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | [6 empty] | 0 | ₹0.00 | ₹0.00
BigHaat Agro Private Limited | BigHaat – WhatsApp Quick Reply Feature Requirement - Use Case 1 |  |  | Aman Bothra | WhatsApp | No | Kevit | Lost | 07/09/2026 | 08/09/2026 | [9 empty] | Lost |  |  |  |  | ₹8,000.00 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹10,000 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
BigHaat Agro Private Limited | BigHaat – WhatsApp Quick Reply Feature Requirement - Use Case 2 |  |  | Aman Bothra | WhatsApp | No | Kevit | Lost | 07/09/2026 | 08/09/2026 | [9 empty] | Lost |  |  |  |  | ₹16,000.00 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹20,000 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
| Aditya Birla | BFSI | Broking & Financial Services | Bbijal Panchmmattya | RCS - S2C | No | Kevit | UAT | 07/09/2026 | 08/09/2026 |  |  | 22/09/2026 |  | 7 |  | 15/09/2026 |  | -43 | Delayed |  |  |  |  | ₹45,000.00 | ₹9,900.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹861,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00
Zee Entertainment Enterprises Limited | ZEE Tamil ¦ Coimbatore Event ¦ WhatsApp Blast & Geo-Targeted Status Campaign |  |  | Apekshit Babaria | WhatsApp | No | Consense | Quotes Given | 08/09/2026 | 10/09/2026 | [9 empty] | Date Missing |  |  |  |  | ₹0.00 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Zee Entertainment Enterprises Limited | Zee Telugu Kutumbam Awards 2026 – WhatsApp Chatbot Development & Voting Timelines |  |  | Apekshit Babaria | WhatsApp | No | Kevit | Quotes Given | 09/09/2026 | 10/09/2026 | [9 empty] | Date Missing |  |  |  |  | ₹45,000.00 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹50,000 | ₹10,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360- 7 - 9999912360 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Development | 09/09/2026 | 09/09/2026 |  |  | 10/09/2026 | [6 empty] | Date Missing |  |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
Pathfinder Publishing Pvt. Ltd | Career 360- 8 - 9999989360 | Other | General | Paridhi Jain | WhatsApp | No | Kevit | Development | 09/09/2026 | 09/09/2026 |  |  | 10/09/2026 |  | 0 |  | 11/09/2026 |  | -47 | Delayed |  |  |  |  | ₹0 | ₹10,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Chola Partners Vehicle Finance - 9043005423 | BFSI | NBFC (Loan Against Property) | Pranav Nand | WhatsApp | No | Kevit | Development | 09/09/2026 | 09/09/2026 | - | - | 10/09/2026 |  | 0 |  | 11/09/2026 |  | -47 | Delayed |  |  |  |  | ₹0 | ₹20,000 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹35,000 | 0 | ₹0.00 | ₹0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00 | ₹0.00
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Finance LAP – 6385680808 - 3 Agent logins |  |  | Pranav Nand | WhatsApp | No | Kevit | Live | 11/09/2026 | 11/09/2026 |  |  | 11/09/2026 |  | 0 |  | 11/09/2026 |  | -47 | Delayed |  |  |  |  | ₹0.00 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 3 | ₹1,000.00 | 0 | ₹0.00 | ₹0 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 3 | ₹1,200.00 | ₹0.00
Asian Paints Limited | Sleek Components - Asain Paints - Chatbot |  |  | Rithika Salian | WhatsApp | No | Kevit | Quotes Given | 15/09/2026 | 15/09/2026 |  |  |  |  | 12 |  |  |  |  | Date Missing |  |  |  |  | ₹90,000.00 | ₹13,500.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹115,000 | ₹17,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
BigHaat Agro Private Limited | BigHaat – New whatsApp Chatbot requirement |  |  | Aman Bothra | WhatsApp | No | Kevit | Quotes Given | 16/09/2026 | 16/09/2026 |  |  |  |  | 5 |  | 11/09/2026 |  | -47 | Delayed |  |  |  |  | ₹40,500.00 | ₹9,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹50,000 | ₹11,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
| Quick Ride - Whatsapp |  |  | Dhiraj Shivrati | WhatsApp | No | Kevit | Lost | 17/09/2026 | 17/09/2026 | [9 empty] | Lost | The quotes were too high for the client. He is getting zero MR and only 20K subscribtion yearly from double tick and gupshup |  |  |  | ₹0.00 | ₹10,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹0 | ₹15,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
| VLCC - Bot Migration |  |  | Rahul Pillai | WhatsApp | No | Kevit | Quotes Given | 18/09/2026 | 18/09/2026 |  |  | 28/09/2026 |  | 4 |  |  |  |  | Date Missing | One time development cost is paid thru CEE deal. |  |  |  | ₹36,000.00 | ₹9,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 50 | ₹420.00 | 0 | ₹0.00 | ₹0 | ₹12,500 | 0 | ₹0.00 | 0.00 | ₹0.00 | 50 | ₹450.00 | ₹0.00
| Shriram Life Insurance | BFSI | NBFC & Digital Lending | Harsh Shrivastava | RCS - S2C | No | Kevit | Development | 18/09/2026 | 21/09/2026 |  |  | 28/09/2026 |  | 7 |  |  |  |  | Date Missing |  |  |  |  | ₹45,000.00 | ₹9,900.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹284,709 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
| St Francis |  |  | Unnit Dedhia | WhatsApp | No |  | Quotes Given | 22/09/2026 | 22/09/2026 | [9 empty] | Date Missing | [12 empty] | 0 | ₹0.00 | [8 empty] | ₹0.00
| Zee Cinema - Bhoot Bangla Movie |  |  | Apekshit Babaria | WhatsApp | No | Kevit | Quotes Given | 22/09/2026 | 23/09/2026 |  |  |  |  | 7 |  |  |  |  | Date Missing |  |  |  |  | ₹45,000.00 | ₹9,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 | ₹50,000 | ₹0 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00 | ₹0.00
| Axio |  |  | Krishna Prasad | WhatsApp | No | Kevit | Discovery | 10/09/2026 | [10 empty] | Date Missing | [12 empty] | 0 | ₹0.00 | [8 empty] | ₹0.00
| Jaro Education |  |  | Unnit Dedhia | WhatsApp | No | Kevit | Quotes Given | 22/09/2026 | 23/09/2026 | [9 empty] | Date Missing |  |  |  |  | ₹180,000.00 | ₹18,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹900.00 | 0 | ₹0.00 | ₹220,000 | ₹22,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹1,200.00 | ₹0.00
| Bajaj Housing - CSPL |  |  | Kapil Sharma | RCS | No | Kevit | UAT | 19/06/2026 | 19/06/2026 | [9 empty] | Date Missing |  |  |  |  | ₹24,000.00 | ₹10,000.00 | 0 | ₹0.00 | 0 | ₹0.00 | 2 | ₹1,000.00 |  |  | ₹50,000 | ₹20,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 2 | ₹1,200.00
| Unifi - Telecom Bot |  |  | Mayank Gupta | WhatsApp | Yes | Kevit | Quotes Given | 23/09/2026 | 24/09/2026 |  |  |  |  | 19 |  |  |  |  | Date Missing |  |  |  |  | ₹90,000.00 | ₹31,500.00 | 0 | ₹0.00 | 0 | ₹0.00 | 0 | ₹0.00 |  |  | ₹110,350 | ₹38,000 | 0 | ₹0.00 | 0.00 | ₹0.00 | 0 | ₹0.00

## Chatbot R&M
Live Chatbot Projects (auto-linked) |  |  |  |  | Vendor Commercials | [14 empty] | Netcore Commercials | [14 empty] | Margin |  | Classification
Client | Chatbot | Vendor | Month | Financial Year | Vendor Dev Cost | Vendor Monthly Rental | Vendor AI Session Rate | Vendor AI Base (Monthly Editable) | Vendor AI Session Cost | Vendor Bot Session Rate | Vendor Bot Base (Monthly Editable) | Vendor Bot Session Cost | Vendor Agent Rate | Vendor Agent Base (Monthly Editable) | Vendor Agent Cost | Vendor Conversation Rate | Vendor Conversation Base (Monthly Editable) | Vendor Conversation Cost | Total Vendor Cost | Netcore Dev Revenue | Netcore Monthly Rental | Netcore AI Session Rate | Netcore AI Base (Monthly Editable) | Netcore AI Session Revenue | Netcore Bot Session Rate | Netcore Bot Base (Monthly Editable) | Netcore Bot Session Revenue | Netcore Agent Rate | Netcore Agent Base (Monthly Editable) | Netcore Agent Revenue | Netcore Conversation Rate | Netcore Conversation Base (Monthly Editable) | Netcore Conversation Revenue | Total Netcore Revenue | Margin | Margin % | Industry | Sub Industry
Antara Assisted Care Services Limited | Ageasy | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | May-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Ageasy | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Bot | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | May-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Antara Assisted Care Services Limited | Antara Live Chat | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 6.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 6.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | May-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Appointment | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,600.00 | ₹0.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹24,000.00 | ₹2,400.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | May-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Dr Referrel | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | May-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo - Insurance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹7,000.00 | 28.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | May-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Apollo Hospitals Enterprise Ltd | Apollo Proton Center | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | ap__asian-paints-prod | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 1 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Broadband 2 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | May-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
Atria Convergence Technologies Ltd | ACT Report | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹8,000.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (TA Chatbot) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹10,000.00 | 33.33%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web + WhatsApp) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit (Web UAT Chatbot) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
BAJAJ AUTO CREDIT LIMITED | Bajaj Auto Credit HR Bot | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | May-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | Bajaj Allianz Life Insurance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Housing Finance Limited | bh__online_home_loan | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
Bandhan AMC Limited | Bandhanamc__feedback | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹10,000.00 | 100.00%
BigHaat Agro Private Limited | Bighaat | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | May-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
BigHaat Agro Private Limited | Bighaat | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹1,000.00 | 2.86%
Board of Control for Cricket in India | IPL | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | May-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
Board of Control for Cricket in India | IPL | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | May-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola 3 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | May-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola Lap | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹25,000.00 | 0.00%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | May-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | BSA Motorcycles | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹8,000.00 | 22.86%
Classic Legends Private Limited | JAWA Bikes | Kevit | Apr-26 | 2026-27 | ₹12,500.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹42,500.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | -₹6,100.00 | -16.76%
Classic Legends Private Limited | JAWA Bikes | Kevit | May-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | JAWA Bikes | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹36,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,400.00 | ₹6,400.00 | 17.58%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Apr-26 | 2026-27 | ₹270,000.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹297,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | -₹267,000.00 | -890.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | May-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Classic Legends Private Limited | Jawa Yezdi BSA Motorcycles | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹27,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹27,000.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹3,000.00 | 10.00%
Credila Financial Services Limited | Credilla | Kevit | Apr-26 | 2026-27 | ₹30,000.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹45,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | -₹30,000.00 | -200.00%
Credila Financial Services Limited | Credilla | Kevit | May-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credilla | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | hdfc__credila_wa | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__bebeclub | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Danone International Pvt Ltd | danone__gm | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__gm | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
Danone International Pvt Ltd | danone__nutriclub | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹72,508.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,508.00 | ₹72,508.00 | 100.00%
DCB Bank Ltd. | DCB | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | May-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,000.00 | 40.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
DCB Bank Ltd. | DCB bot 2 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | May-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
EMMA SLEEP INDIA PRIVATE LIMITED | EMMA Sleep | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹5,000.00 | 12.50%
Epifi Technologies Private Limited | Epify | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Epifi Technologies Private Limited | Epify | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 2.00 | ₹2,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 2.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitas__equitaschatbot_banker-on-prod | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas__equitaschatbot | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
GIM INFO SOLUTIONS PRIVATE LIMITED | a__gimbookswa | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Haleon India | Sensodyne | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
Haleon India | Sensodyne | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹15,000.00 | 60.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | May-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC 2 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | May-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹2,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Partner UAT | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | May-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HDFC Asset Management Company Ltd. | HDFC Development Charges | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹300,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹300,000.00 | ₹0.00 | ₹320,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹320,000.00 | ₹20,000.00 | 6.25%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | May-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HeidelbergCement India Limited | Heidelberg Cement | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹7,500.00 | 25.00%
HGI Industries Limited | HGI - TexZone | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | May-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
HGI Industries Limited | HGI - TexZone | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | May-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
IGP Commerce Private Limited | IGP | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹600.00 | 10.00%
Katyayani Organics | a__katyani-organics | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Katyayani Organics | a__katyani-organics | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | May-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund (UAT) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹7,200.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,200.00 | ₹0.00 | ₹8,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹8,000.00 | ₹800.00 | 10.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Living Media India Ltd | Indiatoday - Magazine | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Magicbricks Realty Services Limited | magicbricks_bot__magicbricks_uat_11june_2 | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Manash Lifestyle Pvt. Ltd. | purple__purple_chatbot | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Apr-26 | 2026-27 | ₹100,000.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹130,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | -₹95,500.00 | -276.81%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | May-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | Nuvama Finance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹34,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,500.00 | ₹4,500.00 | 13.04%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__meeting_feedback | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama__nuvama-feedback-bot | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Nuvama Wealth Finance Limited | nuvama_newpanel__nuvama_chatbot_autoresponses | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Oona Insurance Pte. Ltd. | Oona Insurance 2 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,000.00 | 0.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | May-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360 - 4 Instagram Accounts | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹28,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹28,800.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹1,200.00 | 4.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 2 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 3 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 4 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹6,000.00 | 40.00%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 5 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Pathfinder Publishing Pvt. Ltd | Career 360- 6 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹5,000.00 | 33.33%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Buyer) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (CP) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Porch Technologies Private Limited | Truva (Seller) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹6,300.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,300.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹700.00 | 10.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Relaxo Footwears Ltd. | relaxo__relaxofootwear | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹13,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,000.00 | ₹13,000.00 | 100.00%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | May-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reliance General Insurance Co. Ltd | Reliance General Insurance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 3.00 | ₹1,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,900.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 3.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹100.00 | 1.43%
Reserve Bank of India | RBI | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Reserve Bank of India | RBI | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram Asset Management Company Limited | Shriram Finance Limtied (Lead Generation) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | May-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹23,000.00 | -328.57%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Shriram General Insurance Company Limited | Shriram General Insurance (WL) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹500.00 | 2.00 | ₹1,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,000.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | May-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | ₹180,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹180,000.00 | ₹155,000.00 | 86.11%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance (Staging) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Apr-26 | 2026-27 | ₹16,000.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹26,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹16,000.00 | -160.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Finance Web (UAT) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | May-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
Sundaram Asset Management Company Limited | Sundaram Web bot (Prod) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | -₹5,000.00 | -50.00%
SustLabs Private Limited | Sustlabs | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | May-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
SustLabs Private Limited | Sustlabs | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | ₹1,000.00 | 14.29%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aaj Tak - New Bot | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | Aajtak - Sudhir Chawdhary | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TAMIL | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | ZEE - TV | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | May-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Bangla | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹5,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,400.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹4,600.00 | 46.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | May-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | Zee Telegu | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,000.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹1,000.00 | 10.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zee_kannada | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetelugu | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zee Entertainment Enterprises Limited | a__zeetvcarouselchatbot | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹3,333.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,333.00 | ₹3,333.00 | 100.00%
Zydus Wellness Products Limited | Zydus | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | May-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
Zydus Wellness Products Limited | Zydus | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹11,250.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹11,250.00 | ₹0.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,000.00 | -₹4,250.00 | -60.71%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | May-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
T.V. TODAY NETWORK LIMITED | GNT | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹5,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | -₹5,000.00 | -100.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Apr-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | May-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Jun-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
Netcore Private Limited | Netcore Internal Bot | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹4,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,000.00 | 9.00 | ₹9,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 9.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹13,500.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| curtis__curtisagentchatbot | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
| default_goodness | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Netcore Private Limited | Netcore__cspl | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Plaza Premium Lounge Management Limited | PPG_bot__ppg_production | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Apr-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | May-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Jun-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Rooter Sports Technologies Pvt Ltd | rooter__rooter_support | Internal | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas | Kevit | Aug-26 | 2026-27 | ₹140,000.00 | ₹14,516.13 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹154,516.13 | ₹284,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹284,709.00 | ₹130,192.87 | 45.73%
Equitas Small Finance Bank Limited | Equitas | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Equitas Small Finance Bank Limited | Equitas | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals | Kevit | Jun-26 | 2026-27 | ₹200,000.00 | ₹14,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹214,000.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹647,709.00 | 75.17%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹18,666.67 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,666.67 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹18,666.67 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Jul-26 | 2026-27 | ₹150,000.00 | ₹58,064.52 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹208,064.52 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹653,644.48 | 75.85%
Credila Financial Services Limited | Credila | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Credila Financial Services Limited | Credila | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Apr-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | May-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Jun-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Jul-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Aug-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Sep-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Oct-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Nov-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Dec-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Jan-27 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Feb-27 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
EXPLOR42 SPORTS TRAVEL LLP | Explor42 - Live Agent | Limechat | Mar-27 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Aug-26 | 2026-27 | ₹75,000.00 | ₹16,451.61 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹91,451.61 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹770,257.39 | 89.39%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Skoda Auto Volkswagen India Private Limited | Skoda | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Apr-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | May-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Jun-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Jul-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Aug-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Sep-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Oct-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Nov-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Dec-26 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Jan-27 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Feb-27 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | Bookchor - CRM | Limechat | Mar-27 | 2026-27 | ₹0.00 | ₹2,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | ₹0.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,000.00 | ₹500.00 | 16.67%
Sun TV Network Limited | Sun Bangla | Limechat | Jul-26 | 2026-27 | ₹27,000.00 | ₹7,403.23 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹34,403.23 | ₹30,000.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹45,000.00 | ₹10,596.77 | 23.55%
Sun TV Network Limited | Sun Bangla | Limechat | Aug-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Sun TV Network Limited | Sun Bangla | Limechat | Sep-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Sun TV Network Limited | Sun Bangla | Limechat | Oct-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Sun TV Network Limited | Sun Bangla | Limechat | Nov-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Sun TV Network Limited | Sun Bangla | Limechat | Dec-26 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Sun TV Network Limited | Sun Bangla | Limechat | Jan-27 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Sun TV Network Limited | Sun Bangla | Limechat | Feb-27 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Sun TV Network Limited | Sun Bangla | Limechat | Mar-27 | 2026-27 | ₹0.00 | ₹13,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹13,500.00 | ₹0.00 | ₹15,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹15,000.00 | ₹1,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Jun-26 | 2026-27 | ₹0.00 | ₹750.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹750.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹24,250.00 | 97.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Jul-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Aug-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Sep-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Oct-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Nov-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Dec-26 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Jan-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Feb-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Emergent Labs Inc | Emergent - CRM | Limechat | Mar-27 | 2026-27 | ₹0.00 | ₹22,500.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,500.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹22,500.00 | ₹0.00 | ₹25,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹25,000.00 | ₹2,500.00 | 10.00%
Asian Paints Limited | Asian Paints (RCS) | Kevit | Sep-26 | 2026-27 | ₹5,000.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,000.00 | ₹12,000.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹7,000.00 | 58.33%
Asian Paints Limited | Asian Paints (RCS) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints (RCS) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints (RCS) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints (RCS) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints (RCS) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints (RCS) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints | Kevit | Sep-26 | 2026-27 | ₹40,000.00 | ₹24,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹64,000.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹797,709.00 | 92.57%
Asian Paints Limited | Asian Paints | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Asian Paints Limited | Asian Paints | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Asian Paints Limited | Asian Paints | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Asian Paints Limited | Asian Paints | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Asian Paints Limited | Asian Paints | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Aug-26 | 2026-27 | ₹50,000.00 | ₹19,354.84 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹69,354.84 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹792,354.16 | 91.95%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
PUMA Sports India Pvt Ltd. | Puma | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Kevit | Sep-26 | 2026-27 | ₹150,000.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹190,000.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹671,709.00 | 77.95%
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
Hero MotoCorp Limited | Hero Motocrop - Harley Davidson | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹20,000.00 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹0.00 | ₹40,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹40,000.00 | ₹4,000.00 | 10.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹5,090.40 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,090.40 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹5,090.40 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹7,272.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,272.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹7,272.00 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹7,272.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,272.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹7,272.00 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹7,272.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,272.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹7,272.00 | 0.00%
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | Kotak Mutual Fund(UAT) | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹7,272.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹7,272.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹7,272.00 | 0.00%
Anjali Mukerjee Health Total Private Limited | Health Total | Kevit | Sep-26 | 2026-27 | ₹50,000.00 | ₹3,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹53,000.00 | ₹60,000.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹72,000.00 | ₹19,000.00 | 26.39%
Anjali Mukerjee Health Total Private Limited | Health Total | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹2,000.00 | 16.67%
Anjali Mukerjee Health Total Private Limited | Health Total | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹2,000.00 | 16.67%
Anjali Mukerjee Health Total Private Limited | Health Total | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹2,000.00 | 16.67%
Anjali Mukerjee Health Total Private Limited | Health Total | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹2,000.00 | 16.67%
Anjali Mukerjee Health Total Private Limited | Health Total | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹2,000.00 | 16.67%
Anjali Mukerjee Health Total Private Limited | Health Total | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹2,000.00 | 16.67%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Jul-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Aug-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Zee Entertainment Enterprises Limited | Zee Entertainment (Dadagiri) | Consense | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Aug-26 | 2026-27 | ₹80,000.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹80,000.00 | ₹100,000.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹112,000.00 | ₹32,000.00 | 28.57%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹12,000.00 | 100.00%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹12,000.00 | 100.00%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹12,000.00 | 100.00%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹12,000.00 | 100.00%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹12,000.00 | 100.00%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹12,000.00 | 100.00%
Credila Financial Services Limited | Credila - USA SUD - 1st 2 Flows | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹12,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹12,000.00 | ₹12,000.00 | 100.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹5,161.29 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹5,161.29 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹29,838.71 | 85.25%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP Prod - 9600096021 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Aug-26 | 2026-27 | ₹90,000.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹90,000.00 | ₹100,000.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹100,000.00 | ₹10,000.00 | 10.00%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Nuvama Wealth Finance Limited | Nuvama Finance Chatbot – Sub brokers Onboarding Journey | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹3,225.81 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,225.81 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹31,774.19 | 90.78%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance HL - 9150510505 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹3,225.81 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹3,225.81 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹31,774.19 | 90.78%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - Finance SME - 9150821010 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Jul-26 | 2026-27 | ₹0.00 | ₹645.16 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹645.16 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹34,354.84 | 98.16%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Aug-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | Chola - New No onboarding - LAP UAT – 6385680808 | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹20,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹20,000.00 | ₹0.00 | ₹35,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹15,000.00 | 42.86%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Aug-26 | 2026-27 | ₹16,000.00 | ₹5,419.35 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹21,419.35 | ₹30,000.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹36,000.00 | ₹14,580.65 | 40.50%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00%
Zydus Wellness Products Limited | Zydus Wellness - Sugarfree - Survey Chatbot/QR Implemetation | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹6,000.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Aug-26 | 2026-27 | ₹31,500.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹31,500.00 | ₹35,000.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹35,000.00 | ₹3,500.00 | 10.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Sep-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Sundaram Asset Management Company Limited | Sundaram Mutual Fund - SIP, Purchase, and SOA | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
HSBC Asset Management India Private Limited | HSBC MF | Kevit | Sep-26 | 2026-27 | ₹54,000.00 | ₹14,850.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹68,850.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹792,859.00 | 92.01%
HSBC Asset Management India Private Limited | HSBC MF | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
HSBC Asset Management India Private Limited | HSBC MF | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
HSBC Asset Management India Private Limited | HSBC MF | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
HSBC Asset Management India Private Limited | HSBC MF | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
HSBC Asset Management India Private Limited | HSBC MF | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
HSBC Asset Management India Private Limited | HSBC MF | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | Kevit | Sep-26 | 2026-27 | ₹60,000.00 | ₹7,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹67,000.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹794,709.00 | 92.22%
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
MOTILAL OSWAL FINANCIAL SERVICES LTD | MOSL | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,000.00 | 0.00%
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | Kevit | Sep-26 | 2026-27 | ₹45,000.00 | ₹21,600.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹66,600.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹795,109.00 | 92.27%
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹10,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,800.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,800.00 | 0.00%
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹10,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,800.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,800.00 | 0.00%
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹10,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,800.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,800.00 | 0.00%
Bajaj Allianz Life Insurance Company Ltd | Bajaj Life Insurance | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹10,800.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹10,800.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹10,800.00 | 0.00%
Bajaj Finserv Direct Ltd | BFDL | Kevit | Sep-26 | 2026-27 | ₹180,000.00 | ₹36,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹216,000.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹645,709.00 | 74.93%
Bajaj Finserv Direct Ltd | BFDL | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Finserv Direct Ltd | BFDL | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Bajaj Finserv Direct Ltd | BFDL | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹18,000.00 | 0.00%
Bajaj Finserv Direct Ltd | BFDL | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹18,000.00 | 0.00%
Bajaj Finserv Direct Ltd | BFDL | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹18,000.00 | 0.00%
Bajaj Finserv Direct Ltd | BFDL | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹18,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹18,000.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹18,000.00 | 0.00%
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Kevit | Sep-26 | 2026-27 | ₹45,000.00 | ₹6,930.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,000.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹51,930.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹809,779.00 | 93.97%
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,000.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,000.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,000.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,000.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,000.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
Škoda Auto Volkswagen India Pvt. Ltd | Volkswagen | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹9,900.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,000.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹9,900.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹9,900.00 | 0.00%
InCred Financial Services Limited | InCred | Kevit | Sep-26 | 2026-27 | ₹45,000.00 | ₹756.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹45,756.00 | ₹861,709.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹861,709.00 | ₹815,953.00 | 94.69%
InCred Financial Services Limited | InCred | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
InCred Financial Services Limited | InCred | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00%
InCred Financial Services Limited | InCred | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹1,080.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,080.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,080.00 | 0.00%
InCred Financial Services Limited | InCred | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹1,080.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,080.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,080.00 | 0.00%
InCred Financial Services Limited | InCred | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹1,080.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,080.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,080.00 | 0.00%
InCred Financial Services Limited | InCred | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹1,080.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹1,080.00 | ₹0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | -₹1,080.00 | 0.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals - Template Configuration for Appointment Booking Flow | Kevit | Oct-26 | 2026-27 | ₹0.00 | ₹2,787.10 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹2,787.10 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹27,212.90 | 90.71%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals - Template Configuration for Appointment Booking Flow | Kevit | Nov-26 | 2026-27 | ₹0.00 | ₹14,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹14,400.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹15,600.00 | 52.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals - Template Configuration for Appointment Booking Flow | Kevit | Dec-26 | 2026-27 | ₹0.00 | ₹14,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹14,400.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹15,600.00 | 52.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals - Template Configuration for Appointment Booking Flow | Kevit | Jan-27 | 2026-27 | ₹0.00 | ₹14,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹14,400.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹15,600.00 | 52.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals - Template Configuration for Appointment Booking Flow | Kevit | Feb-27 | 2026-27 | ₹0.00 | ₹14,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹14,400.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹15,600.00 | 52.00%
Apollo Hospitals Enterprise Ltd | Apollo Hospitals - Template Configuration for Appointment Booking Flow | Kevit | Mar-27 | 2026-27 | ₹0.00 | ₹14,400.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹14,400.00 | ₹0.00 | ₹30,000.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹0.00 | 0.00 | ₹0.00 | ₹30,000.00 | ₹15,600.00 | 52.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%
0.00%

## WA_Consumables
Client | Month | Revenue | Cost | Margin | Industry | Sub Industry
1 FINANCE PRIVATE LIMITED | 01/04/2026 | 4,084 | 3,528 | 556 | Other | General
1 FINANCE PRIVATE LIMITED | 01/05/2026 | 7,318 | 6,416 | 902 | IT & Technology | General
1 FINANCE PRIVATE LIMITED | 01/06/2026 | 9,921 | 8,777 | 1,144 | Other | General
1 FINANCE PRIVATE LIMITED | 01/07/2026 | 61,991 | 49,167 | 12,824
3F OIL PALM PRIVATE LIMITED | 01/04/2026 | 2,511 | 2,274 | 237 | Education | General
3F OIL PALM PRIVATE LIMITED | 01/05/2026 | 3,955 | 3,525 | 430 | Other | General
3F OIL PALM PRIVATE LIMITED | 01/06/2026 | 7,547 | 6,716 | 831 | Other | General
3F OIL PALM PRIVATE LIMITED | 01/07/2026 | 13,954 | 12,567 | 1,387
AAKASH EDUCATIONAL SERVICES LIMITED | 01/07/2026 | 799,816 | 841,518 | -41,702
Aaryak Jewellery Private Limited | 01/04/2026 | 11,184 | 10,401 | 783 | IT & Technology | General
Aaryak Jewellery Private Limited | 01/05/2026 | 15,570 | 14,481 | 1,089 | IT & Technology | General
Aaryak Jewellery Private Limited | 01/06/2026 | 4,435 | 4,124 | 311 | Other | General
Aaryak Jewellery Private Limited | 01/07/2026 | 6,367 | 5,921 | 446
Aditya Birla Sun Life AMC Limited | 01/04/2026 | 284,085 | 253,368 | 30,717 | Other | General
Aditya Birla Sun Life AMC Limited | 01/05/2026 | 537,568 | 479,441 | 58,127 | Retail | General
Aditya Birla Sun Life AMC Limited | 01/06/2026 | 889,927 | 793,700 | 96,227 | IT & Technology | General
Aditya Birla Sun Life AMC Limited | 01/07/2026 | 1,154,206 | 1,029,403 | 124,803
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/04/2026 | 919,414 | 817,886 | 101,528 | Agriculture & FMCG | General
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/05/2026 | 970,495 | 862,693 | 107,802 | Other | General
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 2,037,247 | 1,812,490 | 224,757 | Other | General
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 1,428,159 | 1,268,332 | 159,827
Adjetter Media Network Private Limited | 01/04/2026 | 220 | 187 | 33 | BFSI | General
Adjetter Media Network Private Limited | 01/05/2026 | 19 | 16 | 3 | IT & Technology | General
Adjetter Media Network Private Limited | 01/06/2026 | 5 | 4 | 1 | Other | General
Adjetter Media Network Private Limited | 01/07/2026 | 8 | 7 | 1
Agione Technologies Private Limited | 01/04/2026 | 257,518 | 229,671 | 27,847 | IT & Technology | General
Agione Technologies Private Limited | 01/05/2026 | 192,930 | 172,039 | 20,891 | Other | General
Agione Technologies Private Limited | 01/06/2026 | 262,973 | 234,538 | 28,435 | BFSI | General
Agione Technologies Private Limited | 01/07/2026 | 114,627 | 102,232 | 12,395
Ahaguru Education Technology Private Limited | 01/05/2026 | 37,655 | 33,584 | 4,071 | BFSI | General
Ahaguru Education Technology Private Limited | 01/07/2026 | 18,887 | 16,845 | 2,042
Air India Limited | 01/04/2026 | 2,788,869 | 2,555,430 | 233,439 | Other | General
Air India Limited | 01/05/2026 | 2,413,305 | 2,208,470 | 204,835 | Education | General
Air India Limited | 01/06/2026 | 2,037,784 | 2,022,280 | 15,504 | IT & Technology | General
Air India Limited | 01/07/2026 | 2,253,742 | 2,051,711 | 202,031
AIX Connect Private Limited | 01/04/2026 | 68,068 | 65,926 | 2,142 | Retail | General
AIX Connect Private Limited | 01/05/2026 | 140,201 | 136,325 | 3,876 | Real Estate | General
AIX Connect Private Limited | 01/06/2026 | 206,323 | 206,323 | 0 | IT & Technology | General
AIX Connect Private Limited | 01/07/2026 | 210,278 | 202,617 | 7,661
ALEMBIC PHARMACEUTICALS LIMITED | 01/04/2026 | 210,682 | 187,336 | 23,346 | BFSI | General
ALEMBIC PHARMACEUTICALS LIMITED | 01/05/2026 | 91,847 | 80,791 | 11,056 | Other | General
ALEMBIC PHARMACEUTICALS LIMITED | 01/06/2026 | 69,514 | 59,047 | 10,467 | Other | General
ALEMBIC PHARMACEUTICALS LIMITED | 01/07/2026 | 35,766 | 28,106 | 7,660
Alkem Laboratories Limited | 01/05/2026 | 102,703 | 91,598 | 11,105 | Other | General
Alkem Laboratories Limited | 01/06/2026 | 435,872 | 388,741 | 47,131 | Other | General
Alkem Laboratories Limited | 01/07/2026 | 275,621 | 245,818 | 29,803
ALPHAVECTOR (INDIA) PVT LTD | 01/04/2026 | 250 | 201 | 49 | Other | General
ALPHAVECTOR (INDIA) PVT LTD | 01/05/2026 | 325 | 261 | 64 | Retail | General
ALPHAVECTOR (INDIA) PVT LTD | 01/06/2026 | 329 | 269 | 60 | BFSI | General
ALPHAVECTOR (INDIA) PVT LTD | 01/07/2026 | 283 | 227 | 56
Ameyaa Anant Business Private Limited | 01/04/2026 | 64,134 | 57,199 | 6,935 | IT & Technology | General
Ameyaa Anant Business Private Limited | 01/05/2026 | 28,688 | 25,587 | 3,101 | IT & Technology | General
Ameyaa Anant Business Private Limited | 01/06/2026 | 95,166 | 84,876 | 10,290 | Education | General
Ameyaa Anant Business Private Limited | 01/07/2026 | 202,047 | 180,200 | 21,847
Amnex Infotechnologies Private Limited | 01/04/2026 | 72,337 | 69,371 | 2,966 | Agriculture & FMCG | General
Amnex Infotechnologies Private Limited | 01/05/2026 | 11,527 | 11,055 | 472 | Other | General
Amnex Infotechnologies Private Limited | 01/06/2026 | 9,538 | 9,147 | 391 | BFSI | General
Amnex Infotechnologies Private Limited | 01/07/2026 | 52,943 | 50,772 | 2,171
Amrutam Pharmaceuticals Pvt Ltd | 01/04/2026 | 26,287 | 25,133 | 1,154 | Other | General
Amrutam Pharmaceuticals Pvt Ltd | 01/05/2026 | 34,903 | 33,406 | 1,497 | IT & Technology | General
Amrutam Pharmaceuticals Pvt Ltd | 01/06/2026 | 24,647 | 23,180 | 1,467 | Other | General
Amrutam Pharmaceuticals Pvt Ltd | 01/07/2026 | 27,147 | 24,874 | 2,273
ANGEL ONE LIMITED | 01/04/2026 | 5,901,192 | 5,775,501 | 125,691 | BFSI | Life Insurance
ANGEL ONE LIMITED | 01/05/2026 | 1,089,108 | 1,065,196 | 23,912 | Healthcare | General
ANGEL ONE LIMITED | 01/06/2026 | 1,013,388 | 990,931 | 22,457 | Other | General
ANGEL ONE LIMITED | 01/07/2026 | 1,280,974 | 1,253,051 | 27,923
Antara Assisted Care Services Limited | 01/04/2026 | 266,914 | 237,983 | 28,931 | Other | General
Antara Assisted Care Services Limited | 01/05/2026 | 286,933 | 255,897 | 31,036 | Other | General
Antara Assisted Care Services Limited | 01/06/2026 | 517,378 | 461,349 | 56,029 | BFSI | Housing Finance
Antara Assisted Care Services Limited | 01/07/2026 | 427,925 | 381,463 | 46,462
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/04/2026 | 899,864 | 836,909 | 62,955 | BFSI | General
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/05/2026 | 878,146 | 816,890 | 61,256 | Media & Entertainment | General
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 1,007,410 | 936,892 | 70,518 | Agriculture & FMCG | General
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 727,675 | 676,918 | 50,757
Apnarupee Fin India Private Limited | 01/04/2026 | 15,257 | 13,168 | 2,089 | Other | General
Apnarupee Fin India Private Limited | 01/05/2026 | 25,603 | 22,098 | 3,505 | IT & Technology | General
Apnarupee Fin India Private Limited | 01/06/2026 | 29,350 | 25,332 | 4,018 | Other | General
Apnarupee Fin India Private Limited | 01/07/2026 | 32,838 | 28,342 | 4,496
Apollo Hospitals Enterprise Ltd | 01/04/2026 | 1,178,637 | 1,072,925 | 105,712 | Healthcare | Hospitals
Apollo Hospitals Enterprise Ltd | 01/05/2026 | 752,813 | 704,321 | 48,492 | Other | General
Apollo Hospitals Enterprise Ltd | 01/06/2026 | 606,239 | 558,742 | 47,497 | IT & Technology | General
Apollo Hospitals Enterprise Ltd | 01/07/2026 | 706,806 | 647,444 | 59,362
APPFLIX STUDIO LLP | 01/04/2026 | 915,782 | 751,083 | 164,699 | Other | General
APPFLIX STUDIO LLP | 01/05/2026 | 310,850 | 253,214 | 57,636 | Other | General
APPFLIX STUDIO LLP | 01/06/2026 | 255,711 | 208,298 | 47,413 | BFSI | General
APPFLIX STUDIO LLP | 01/07/2026 | 208,045 | 169,470 | 38,575
Aptech Ltd. | 01/04/2026 | 10 | 9 | 1 | Healthcare | General
Aptech Ltd. | 01/05/2026 | 18 | 16 | 2 | IT & Technology | General
Aptech Ltd. | 01/06/2026 | 12 | 10 | 2 | Travel & Aviation | General
Aptech Ltd. | 01/07/2026 | 7 | 6 | 1
ARIES AGRO LIMITED | 01/04/2026 | 84 | 80 | 4 | BFSI | General
ARIES AGRO LIMITED | 01/05/2026 | 89 | 85 | 4 | BFSI | Mutual Fund
ARIES AGRO LIMITED | 01/06/2026 | 25,196 | 24,163 | 1,033 | IT & Technology | General
ARIES AGRO LIMITED | 01/07/2026 | 41,492 | 39,791 | 1,701
ARKA FINCAP LIMITED | 01/04/2026 | 700 | 604 | 96 | Education | General
ARKA FINCAP LIMITED | 01/05/2026 | 51,630 | 44,562 | 7,068 | Retail | General
ARKA FINCAP LIMITED | 01/06/2026 | 98,443 | 86,317 | 12,126 | Other | General
ARKA FINCAP LIMITED | 01/07/2026 | 102 | 90 | 12
Ashika Stock Broking Ltd. | 01/04/2026 | 5,273 | 4,408 | 865 | Ecommerce | General
Ashika Stock Broking Ltd. | 01/05/2026 | 4,552 | 3,773 | 779 | Retail | General
Ashika Stock Broking Ltd. | 01/06/2026 | 41,397 | 35,566 | 5,831 | Education | General
Ashika Stock Broking Ltd. | 01/07/2026 | 6,449 | 5,342 | 1,107
Asian Paints Limited | 01/04/2026 | 6,777 | 6,044 | 733 | Other | General
Asian Paints Limited | 01/05/2026 | 1,835 | 1,637 | 198 | Education | General
Asian Paints Limited | 01/06/2026 | 114,151 | 101,808 | 12,343 | Other | General
Asian Paints Limited | 01/07/2026 | 178,313 | 159,052 | 19,261
Astro Arun Pandit Pvt. Ltd. | 01/04/2026 | 218,014 | 194,457 | 23,557 | Other | General
Astro Arun Pandit Pvt. Ltd. | 01/05/2026 | 157,038 | 140,060 | 16,978 | Other | General
Astroved.com Pvt Ltd | 01/04/2026 | 11 | 9 | 2 | BFSI | General
Astroved.com Pvt Ltd | 01/05/2026 | 14 | 11 | 3 | Healthcare | General
Astroved.com Pvt Ltd | 01/06/2026 | 40 | 35 | 5 | Healthcare | General
Astroved.com Pvt Ltd | 01/07/2026 | 14 | 11 | 3
Astrovision Futuretech Pvt. Ltd. | 01/04/2026 | 1 | 1 | 0 | Retail | General
Astrovision Futuretech Pvt. Ltd. | 01/05/2026 | 392,333 | 357,868 | 34,465 | Other | General
Astrovision Futuretech Pvt. Ltd. | 01/06/2026 | 804,754 | 734,450 | 70,304 | Other | General
Astrovision Futuretech Pvt. Ltd. | 01/07/2026 | 568,243 | 518,245 | 49,998
ATHWISE SERVICES PRIVATE LIMITED | 01/04/2026 | 26 | 25 | 1 | BFSI | Mutual Fund
Atria Convergence Technologies Ltd | 01/04/2026 | 1,061,764 | 990,570 | 71,194 | Media & Entertainment | General
Atria Convergence Technologies Ltd | 01/05/2026 | 783,445 | 717,793 | 65,652 | BFSI | General
Atria Convergence Technologies Ltd | 01/06/2026 | 1,193,135 | 1,082,410 | 110,725 | Other | General
Atria Convergence Technologies Ltd | 01/07/2026 | 1,032,446 | 940,594 | 91,852
Attero Recycling Private Limited | 01/04/2026 | 55,747 | 51,846 | 3,901 | Other | General
Attero Recycling Private Limited | 01/05/2026 | 244,119 | 227,031 | 17,088 | Healthcare | General
Attero Recycling Private Limited | 01/06/2026 | 165,068 | 153,513 | 11,555 | BFSI | General
Attero Recycling Private Limited | 01/07/2026 | 137,958 | 128,301 | 9,657
Avis India Mobility Solutions Private Limited | 01/04/2026 | 63,587 | 53,614 | 9,973 | Other | General
Avis India Mobility Solutions Private Limited | 01/05/2026 | 92,163 | 78,876 | 13,287 | IT & Technology | General
Avis India Mobility Solutions Private Limited | 01/06/2026 | 101,372 | 87,884 | 13,488 | IT & Technology | General
Avis India Mobility Solutions Private Limited | 01/07/2026 | 95,556 | 80,138 | 15,418
Aviva Life Insurance Company India Ltd. | 01/04/2026 | 769 | 664 | 105 | BFSI | General
Aviva Life Insurance Company India Ltd. | 01/05/2026 | 11,410 | 9,848 | 1,562 | IT & Technology | General
Aviva Life Insurance Company India Ltd. | 01/06/2026 | 4,330 | 3,737 | 593 | Other | General
Aviva Life Insurance Company India Ltd. | 01/07/2026 | 1,052 | 908 | 144
Axis Asset Management Company Limited | 01/04/2026 | 790,702 | 725,315 | 65,387 | Other | General
Axis Asset Management Company Limited | 01/05/2026 | 960,646 | 881,791 | 78,855 | Agriculture & FMCG | General
Axis Asset Management Company Limited | 01/06/2026 | 583,810 | 535,493 | 48,317 | BFSI | General
Axis Asset Management Company Limited | 01/07/2026 | 1,307,726 | 1,199,566 | 108,160
Axis Securities Ltd. | 01/04/2026 | 161,382 | 159,874 | 1,508 | IT & Technology | General
Axis Securities Ltd. | 01/05/2026 | 122,324 | 120,920 | 1,404 | BFSI | Small Finance Bank
Axis Securities Ltd. | 01/06/2026 | 137,467 | 135,022 | 2,445 | Healthcare | General
Axis Securities Ltd. | 01/07/2026 | 111,980 | 103,215 | 8,765
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/04/2026 | 82,118 | 76,371 | 5,747 | Other | General
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/05/2026 | 68,965 | 64,138 | 4,827 | Agriculture & FMCG | General
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/06/2026 | 131,646 | 122,431 | 9,215 | Retail | General
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/07/2026 | 93,778 | 87,214 | 6,564
BAJAAO MUSIC PRIVATE LIMITED | 01/04/2026 | 39,375 | 33,985 | 5,390 | BFSI | Life Insurance
BAJAAO MUSIC PRIVATE LIMITED | 01/05/2026 | 21,956 | 18,950 | 3,006 | Other | General
BAJAAO MUSIC PRIVATE LIMITED | 01/06/2026 | 76,691 | 66,192 | 10,499 | Agriculture & FMCG | General
BAJAAO MUSIC PRIVATE LIMITED | 01/07/2026 | 23,336 | 20,141 | 3,195
Bajaj Allianz Life Insurance Company Ltd | 01/04/2026 | 186,329 | 173,771 | 12,558 | IT & Technology | General
Bajaj Allianz Life Insurance Company Ltd | 01/05/2026 | 355,829 | 330,924 | 24,905 | Other | General
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 530,247 | 493,130 | 37,117 | Retail | General
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 1,113,257 | 1,034,934 | 78,323
BAJAJ AUTO CREDIT LIMITED | 01/04/2026 | 261,234 | 242,758 | 18,476 | IT & Technology | General
BAJAJ AUTO CREDIT LIMITED | 01/05/2026 | 104,994 | 97,206 | 7,788 | Education | General
BAJAJ AUTO CREDIT LIMITED | 01/06/2026 | 230,344 | 196,280 | 34,064 | BFSI | General
BAJAJ AUTO CREDIT LIMITED | 01/07/2026 | 205,375 | 190,774 | 14,601
Bajaj Finserv Asset Management Limited | 01/04/2026 | 19 | 18 | 1 | Other | General
Bajaj Finserv Direct Ltd | 01/04/2026 | 1,719,440 | 1,599,215 | 120,225 | Healthcare | General
Bajaj Finserv Direct Ltd | 01/05/2026 | 2,957,262 | 2,750,361 | 206,901 | Other | General
Bajaj Finserv Direct Ltd | 01/06/2026 | 2,189,749 | 2,038,572 | 151,177 | BFSI | Life Insurance
Bajaj Finserv Direct Ltd | 01/07/2026 | 1,952,111 | 1,794,464 | 157,647
Bajaj Housing Finance Limited | 01/04/2026 | 2,172 | 1,937 | 235 | Other | General
Bajaj Housing Finance Limited | 01/05/2026 | 2,444 | 2,180 | 264 | Other | General
Bajaj Housing Finance Limited | 01/06/2026 | 2,075 | 1,851 | 224 | BFSI | General
Bajaj Housing Finance Limited | 01/07/2026 | 1,353 | 1,206 | 147
Bal Raksha Bharat | 01/04/2026 | 7,916 | 6,806 | 1,110 | Education | General
Bal Raksha Bharat | 01/05/2026 | 23,687 | 20,683 | 3,004 | IT & Technology | General
Bal Raksha Bharat | 01/06/2026 | 47,463 | 41,978 | 5,485 | Retail | General
Bal Raksha Bharat | 01/07/2026 | 55,370 | 48,850 | 6,520
Best United India Comforts Pvt. Ltd. | 01/04/2026 | 2,129 | 1,487 | 642 | Other | General
Best United India Comforts Pvt. Ltd. | 01/05/2026 | 2,455 | 1,714 | 741 | Other | General
Best United India Comforts Pvt. Ltd. | 01/06/2026 | 3,311 | 2,311 | 1,000 | IT & Technology | General
Best United India Comforts Pvt. Ltd. | 01/07/2026 | 4,100 | 2,863 | 1,237
Bharat Reinsurance Brokers Private Limited | 01/06/2026 | 229 | 204 | 25 | Travel & Aviation | General
Bharat Reinsurance Brokers Private Limited | 01/07/2026 | 42 | 38 | 4
BigHaat Agro Private Limited | 01/04/2026 | 616,402 | 577,631 | 38,771 | Media & Entertainment | General
BigHaat Agro Private Limited | 01/05/2026 | 478,412 | 439,878 | 38,534 | BFSI | Housing Finance
BigHaat Agro Private Limited | 01/06/2026 | 443,201 | 409,430 | 33,771 | BFSI | Housing Finance
BigHaat Agro Private Limited | 01/07/2026 | 483,253 | 451,785 | 31,468
Billionbrains Garage Ventures Pvt. Ltd. | 01/04/2026 | 5,948 | 5,539 | 409 | Other | General
Billionbrains Garage Ventures Pvt. Ltd. | 01/05/2026 | 2,292,655 | 2,116,861 | 175,794 | Other | General
Billionbrains Garage Ventures Pvt. Ltd. | 01/06/2026 | 8,406,931 | 7,751,718 | 655,213 | Healthcare | General
Billionbrains Garage Ventures Pvt. Ltd. | 01/07/2026 | 5,712,850 | 5,195,732 | 517,118 | Other | General
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | 01/04/2026 | 34,858 | 32,466 | 2,392 | BFSI | General
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | 01/05/2026 | 44,691 | 41,364 | 3,327 | Retail | General
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 67,307 | 62,460 | 4,847 | Retail | General
BOOKCHOR LITERARY SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 80,344 | 74,627 | 5,717
CADD Centre Training Services Pvt. Ltd. | 01/04/2026 | 2,070 | 1,265 | 805 | BFSI | General
CADD Centre Training Services Pvt. Ltd. | 01/05/2026 | 2,304 | 1,408 | 896 | BFSI | General
CADD Centre Training Services Pvt. Ltd. | 01/06/2026 | 2,774 | 1,695 | 1,079 | Other | General
CADD Centre Training Services Pvt. Ltd. | 01/07/2026 | 2,882 | 1,761 | 1,121
Canara HSBC Life Insurance Company Limited | 01/04/2026 | 276,416 | 257,068 | 19,348 | IT & Technology | General
Canara HSBC Life Insurance Company Limited | 01/05/2026 | 103,166 | 95,945 | 7,221 | Other | General
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 102,302 | 95,141 | 7,161 | Other | General
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 89,413 | 83,154 | 6,259
Capfloat Financial Services Pvt. Ltd. | 01/04/2026 | 537,278 | 504,020 | 33,258 | Other | General
Capfloat Financial Services Pvt. Ltd. | 01/05/2026 | 914,533 | 857,545 | 56,988 | Healthcare | Hospitals
Capfloat Financial Services Pvt. Ltd. | 01/06/2026 | 950,328 | 891,066 | 59,262 | Healthcare | Hospitals
Capfloat Financial Services Pvt. Ltd. | 01/07/2026 | 1,154,239 | 1,081,475 | 72,764
CAPRI GLOBAL CAPTIAL LIMITED | 01/04/2026 | 13,456 | 11,826 | 1,630 | BFSI | Mutual Fund
CAPRI GLOBAL CAPTIAL LIMITED | 01/05/2026 | 13,000 | 11,391 | 1,609 | Healthcare | General
CAPRI GLOBAL CAPTIAL LIMITED | 01/06/2026 | 36,114 | 30,395 | 5,719 | Education | General
CAPRI GLOBAL CAPTIAL LIMITED | 01/07/2026 | 27,094 | 22,421 | 4,673
CareerNet Technologies Pvt Ltd | 01/06/2026 | 42,628 | 38,018 | 4,610 | BFSI | General
CareerNet Technologies Pvt Ltd | 01/07/2026 | 63,920 | 57,008 | 6,912
CASHGRAIL PRIVATE LIMITED | 01/04/2026 | 47,622 | 40,617 | 7,005 | BFSI | General
CASHGRAIL PRIVATE LIMITED | 01/05/2026 | 98,912 | 84,075 | 14,837 | IT & Technology | General
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 183,994 | 156,395 | 27,599 | Other | General
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 213,343 | 181,862 | 31,481
Centrum Broking Limited | 01/04/2026 | 19,171 | 17,098 | 2,073 | Other | General
Centrum Broking Limited | 01/05/2026 | 2,420 | 2,158 | 262 | Other | General
Centrum Broking Limited | 01/06/2026 | 10,532 | 9,393 | 1,139 | Other | General
Centrum Broking Limited | 01/07/2026 | 9,677 | 8,631 | 1,046
Chain-N-Chains Jewels Ltd. | 01/04/2026 | 7,720 | 7,404 | 316 | BFSI | General
Chain-N-Chains Jewels Ltd. | 01/07/2026 | 6,957 | 6,672 | 285
Chalet Hotels Limited | 01/04/2026 | 33,666 | 31,311 | 2,355 | Media & Entertainment | General
Chalet Hotels Limited | 01/05/2026 | 48,798 | 45,392 | 3,406 | BFSI | General
Chalet Hotels Limited | 01/06/2026 | 27,914 | 25,960 | 1,954 | BFSI | General
Chalet Hotels Limited | 01/07/2026 | 18,939 | 17,614 | 1,325
CheQ Digital Private limited | 01/04/2026 | 2,028,964 | 1,857,986 | 170,978 | Other | General
CheQ Digital Private limited | 01/05/2026 | 2,789,332 | 2,562,154 | 227,178 | Media & Entertainment | General
CheQ Digital Private limited | 01/06/2026 | 5,351,932 | 4,941,758 | 410,174 | Healthcare | General
CheQ Digital Private limited | 01/07/2026 | 4,282,456 | 3,930,033 | 352,423 | IT & Technology | General
Chipper Consumer Private Limited | 01/05/2026 | 14,063 | 13,254 | 809 | IT & Technology | General
Chipper Consumer Private Limited | 01/06/2026 | 49,411 | 46,159 | 3,252 | Healthcare | General
Chipper Consumer Private Limited | 01/07/2026 | 55,924 | 52,371 | 3,553
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/04/2026 | 1,193 | 933 | 260 | Other | General
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/05/2026 | 1,096 | 857 | 239 | Other | General
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/06/2026 | 2,098 | 1,641 | 457 | BFSI | General
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/07/2026 | 4,607 | 3,602 | 1,005
Cholamandalam MS General Insurance Company Limited | 01/04/2026 | 241,142 | 174,258 | 66,884 | Other | General
Cholamandalam MS General Insurance Company Limited | 01/05/2026 | 335,846 | 247,334 | 88,512 | BFSI | General
Cholamandalam MS General Insurance Company Limited | 01/06/2026 | 415,319 | 314,133 | 101,186 | BFSI | General
Cholamandalam MS General Insurance Company Limited | 01/07/2026 | 960,942 | 687,864 | 273,078
Cinepolis India Pvt. Ltd. | 01/04/2026 | 1,988 | 1,773 | 215 | IT & Technology | General
Cinepolis India Pvt. Ltd. | 01/05/2026 | 1,377 | 1,447 | -70 | Travel & Aviation | General
Cinepolis India Pvt. Ltd. | 01/06/2026 | 3,713 | 4,411 | -698 | Other | General
Cinepolis India Pvt. Ltd. | 01/07/2026 | 28,320 | 26,223 | 2,097
Classic Legends Private Limited | 01/04/2026 | 176 | 125 | 51 | BFSI | General
Classic Legends Private Limited | 01/05/2026 | 360,172 | 321,187 | 38,985 | Other | General
Classic Legends Private Limited | 01/06/2026 | 17,757 | 15,772 | 1,985 | IT & Technology | General
Classic Legends Private Limited | 01/07/2026 | 246,816 | 220,071 | 26,745
Climbing Seeds Private Limited | 01/04/2026 | 16,150 | 14,403 | 1,747 | Other | General
Climbing Seeds Private Limited | 01/05/2026 | 32,512 | 28,996 | 3,516 | Education | General
Climbing Seeds Private Limited | 01/06/2026 | 29,945 | 26,707 | 3,238 | Media & Entertainment | General
Climbing Seeds Private Limited | 01/07/2026 | 17,463 | 15,574 | 1,889
Clinikally Digital Health Pvt Ltd | 01/04/2026 | 611,054 | 539,500 | 71,554 | BFSI | Housing Finance
Clinikally Digital Health Pvt Ltd | 01/05/2026 | 681,102 | 601,969 | 79,133 | IT & Technology | General
Clinikally Digital Health Pvt Ltd | 01/06/2026 | 439,082 | 385,299 | 53,783 | Other | General
Clinikally Digital Health Pvt Ltd | 01/07/2026 | 605,447 | 532,538 | 72,909
Clix Capital Services Pvt. Ltd. | 01/05/2026 | 64 | 55 | 9 | Other | General
Clix Capital Services Pvt. Ltd. | 01/06/2026 | 63 | 54 | 9 | Other | General
Clix Capital Services Pvt. Ltd. | 01/07/2026 | 58 | 50 | 8
CLOUD WELLNESS PRIVATE LIMITED | 01/05/2026 | 146,216 | 134,797 | 11,419 | IT & Technology | General
CLOUD WELLNESS PRIVATE LIMITED | 01/06/2026 | 255,131 | 236,183 | 18,948 | Other | General
CLOUD WELLNESS PRIVATE LIMITED | 01/07/2026 | 393,999 | 364,091 | 29,908
Complinity Technologies Private Limited | 01/04/2026 | 4,268 | 3,684 | 584 | Other | General
Complinity Technologies Private Limited | 01/05/2026 | 3,158 | 2,726 | 432 | Education | General
Complinity Technologies Private Limited | 01/06/2026 | 6,893 | 5,949 | 944 | Other | General
Complinity Technologies Private Limited | 01/07/2026 | 2,690 | 2,322 | 368
COMPUTER AGE MANAGEMENT SERVICES LIMITED | 01/04/2026 | 49,715 | 46,235 | 3,480 | Other | General
Comsense Technologies Private Limited | 01/04/2026 | 805,110 | 718,052 | 87,058 | Other | General
Comsense Technologies Private Limited | 01/05/2026 | 320,621 | 285,900 | 34,721 | BFSI | General
Comsense Technologies Private Limited | 01/06/2026 | 49 | 39 | 10 | IT & Technology | General
Comsense Technologies Private Limited | 01/07/2026 | 3,871 | 3,450 | 421
CONTAGIOUS V | 01/06/2026 | 14,985 | 12,028 | 2,957 | Other | General
CONTAGIOUS V | 01/07/2026 | 70,344 | 56,464 | 13,880
COSMO FIRST LIMITED | 01/04/2026 | 42,569 | 37,919 | 4,650 | Retail | General
COSMO FIRST LIMITED | 01/05/2026 | 80,497 | 71,792 | 8,705 | BFSI | General
COSMO FIRST LIMITED | 01/06/2026 | 26,638 | 23,758 | 2,880 | Other | General
COSMO FIRST LIMITED | 01/07/2026 | 36,241 | 32,322 | 3,919
Cosmofeed Technologies Private Limited | 01/04/2026 | 17 | 15 | 2 | IT & Technology | General
Cosmofeed Technologies Private Limited | 01/05/2026 | 42,843 | 37,170 | 5,673 | BFSI | General
Cosmofeed Technologies Private Limited | 01/06/2026 | 142,818 | 124,964 | 17,854 | Other | General
Cosmofeed Technologies Private Limited | 01/07/2026 | 147,398 | 129,102 | 18,296
CPM India Sales & Marketing Pvt. Ltd. | 01/04/2026 | 351 | 286 | 65 | Education | General
CPM India Sales & Marketing Pvt. Ltd. | 01/05/2026 | 286 | 240 | 46 | IT & Technology | General
CPM India Sales & Marketing Pvt. Ltd. | 01/06/2026 | 1,057 | 952 | 105 | Other | General
CPM India Sales & Marketing Pvt. Ltd. | 01/07/2026 | 4,352 | 4,119 | 233
Credila Financial Services Limited | 01/04/2026 | 408,995 | 364,462 | 44,533 | BFSI | General
Credila Financial Services Limited | 01/05/2026 | 663,946 | 591,962 | 71,984 | Other | General
Credila Financial Services Limited | 01/06/2026 | 352,958 | 314,428 | 38,530 | IT & Technology | General
Credila Financial Services Limited | 01/07/2026 | 369,538 | 312,381 | 57,157
CROCS INDIA PRIVATE LIMITED | 01/04/2026 | 106,668 | 95,295 | 11,373 | Other | General
CROCS INDIA PRIVATE LIMITED | 01/05/2026 | 224,843 | 200,531 | 24,312 | IT & Technology | General
CROCS INDIA PRIVATE LIMITED | 01/06/2026 | 145,000 | 129,321 | 15,679 | IT & Technology | General
CROCS INDIA PRIVATE LIMITED | 01/07/2026 | 236,469 | 210,899 | 25,570
CRY - Child Rights and You | 01/04/2026 | 26 | 24 | 2 | Other | General
CRY - Child Rights and You | 01/05/2026 | 2,440 | 2,269 | 171 | Other | General
CRY - Child Rights and You | 01/06/2026 | 5,515 | 5,129 | 386 | Other | General
CRY - Child Rights and You | 01/07/2026 | 4 | 4 | 0
CUTIS PHARMA | 01/04/2026 | 184,913 | 159,057 | 25,856 | IT & Technology | General
CUTIS PHARMA | 01/05/2026 | 33,026 | 28,104 | 4,922 | IT & Technology | General
CUTIS PHARMA | 01/06/2026 | 22,701 | 19,299 | 3,402 | Other | General
CUTIS PHARMA | 01/07/2026 | 7,555 | 6,023 | 1,532
DA MILANO LEATHERS PVT.LTD. | 01/04/2026 | 130,794 | 116,652 | 14,142 | Education | General
DA MILANO LEATHERS PVT.LTD. | 01/05/2026 | 128,276 | 114,665 | 13,611 | Other | General
DA MILANO LEATHERS PVT.LTD. | 01/06/2026 | 89,081 | 79,449 | 9,632 | Other | General
DA MILANO LEATHERS PVT.LTD. | 01/07/2026 | 141,486 | 126,139 | 15,347
Datasigns Technologies Pvt. Ltd. | 01/04/2026 | 19,293 | 16,970 | 2,323 | IT & Technology | General
Datasigns Technologies Pvt. Ltd. | 01/05/2026 | 3,951 | 2,623 | 1,328 | Other | General
Datasigns Technologies Pvt. Ltd. | 01/06/2026 | 2,764 | 1,868 | 896 | Other | General
Datasigns Technologies Pvt. Ltd. | 01/07/2026 | 2,570 | 1,739 | 831
DCB Bank Ltd. | 01/04/2026 | 194 | 158 | 36 | BFSI | General
DCB Bank Ltd. | 01/05/2026 | 183 | 149 | 34 | Media & Entertainment | General
DCB Bank Ltd. | 01/06/2026 | 139 | 113 | 26 | Other | General
DCB Bank Ltd. | 01/07/2026 | 131 | 107 | 24
DEAR DIARY PRIVATE LIMITED | 01/04/2026 | 16,049 | 14,327 | 1,722 | Other | General
DEAR DIARY PRIVATE LIMITED | 01/05/2026 | 12,982 | 11,578 | 1,404 | Education | General
DEAR DIARY PRIVATE LIMITED | 01/06/2026 | 2,876 | 2,565 | 311 | Other | General
DEAR DIARY PRIVATE LIMITED | 01/07/2026 | 7,773 | 6,933 | 840
Defmacro Software Private Limited | 01/04/2026 | 4 | 4 | 0 | Other | General
Defmacro Software Private Limited | 01/05/2026 | 135,968 | 129,928 | 6,040 | BFSI | General
Defmacro Software Private Limited | 01/06/2026 | 2,057,152 | 1,965,764 | 91,388 | Media & Entertainment | General
Defmacro Software Private Limited | 01/07/2026 | 10,419,704 | 9,588,315 | 831,389 | Other | General
DEXIT GLOBAL LIMITED ( Formerly know as NSEIT Limited ) | 01/04/2026 | 11,632 | 9,261 | 2,371 | Media & Entertainment | General
DEXIT GLOBAL LIMITED ( Formerly know as NSEIT Limited ) | 01/05/2026 | 6,095 | 4,295 | 1,800 | IT & Technology | General
DEXIT GLOBAL LIMITED ( Formerly know as NSEIT Limited ) | 01/06/2026 | 8,439 | 6,176 | 2,263 | Other | General
DEXIT GLOBAL LIMITED ( Formerly know as NSEIT Limited ) | 01/07/2026 | 8,328 | 5,956 | 2,372
Divyastra Health Tech Private Limited | 01/04/2026 | 977 | 597 | 380 | Other | General
Divyastra Health Tech Private Limited | 01/05/2026 | 879 | 537 | 342 | IT & Technology | General
Divyastra Health Tech Private Limited | 01/06/2026 | 910 | 556 | 354 | Other | General
Divyastra Health Tech Private Limited | 01/07/2026 | 1,063 | 649 | 414
Dixit Infotech Services Pvt. Ltd. | 01/04/2026 | 3,586 | 3,095 | 491 | IT & Technology | General
Dixit Infotech Services Pvt. Ltd. | 01/05/2026 | 4,601 | 3,971 | 630 | IT & Technology | General
Dixit Infotech Services Pvt. Ltd. | 01/06/2026 | 8,309 | 7,171 | 1,138 | Other | General
Dixit Infotech Services Pvt. Ltd. | 01/07/2026 | 11,814 | 10,197 | 1,617
Dr B Lal Clinical Laboratory Private Limited | 01/04/2026 | 104,489 | 97,124 | 7,365 | IT & Technology | General
Dr B Lal Clinical Laboratory Private Limited | 01/05/2026 | 176,876 | 162,185 | 14,691 | Other | General
Dr B Lal Clinical Laboratory Private Limited | 01/06/2026 | 200,600 | 183,613 | 16,987 | Other | General
Dr B Lal Clinical Laboratory Private Limited | 01/07/2026 | 255,720 | 234,769 | 20,951
Dr. T. Thimmaiah Institute of Technology | 01/04/2026 | 2,284 | 2,190 | 94 | Other | General
Dr. T. Thimmaiah Institute of Technology | 01/05/2026 | 1 | 1 | 0 | BFSI | General
Dr. T. Thimmaiah Institute of Technology | 01/06/2026 | 1,844 | 1,767 | 77 | Other | General
Dr. T. Thimmaiah Institute of Technology | 01/07/2026 | 387 | 350 | 37
Dressline Fashion | 01/04/2026 | 115 | 75 | 40 | Travel & Aviation | General
Dressline Fashion | 01/05/2026 | 74 | 48 | 26 | Other | General
Dressline Fashion | 01/06/2026 | 102 | 66 | 36 | Other | General
Dressline Fashion | 01/07/2026 | 136 | 89 | 47
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/04/2026 | 25,017 | 22,313 | 2,704 | Media & Entertainment | General
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/05/2026 | 12,998 | 11,592 | 1,406 | Other | General
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 37,874 | 33,779 | 4,095 | BFSI | General
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 66,133 | 58,982 | 7,151
Edelweiss Broking Ltd. | 01/04/2026 | 7,216 | 6,002 | 1,214 | Other | General
Edelweiss Broking Ltd. | 01/05/2026 | 6,037 | 5,107 | 930 | Education | General
Edelweiss Broking Ltd. | 01/06/2026 | 6,342 | 5,345 | 997 | Education | General
Edelweiss Broking Ltd. | 01/07/2026 | 7,135 | 6,065 | 1,070
Edelweiss Mutual Fund | 01/06/2026 | 1,860 | 1,730 | 130 | Travel & Aviation | General
Edelweiss Mutual Fund | 01/07/2026 | 61,208 | 56,930 | 4,278
Emami Ltd | 01/04/2026 | 677,871 | 604,572 | 73,299 | BFSI | Life Insurance
Emami Ltd | 01/05/2026 | 859,403 | 766,410 | 92,993 | Agriculture & FMCG | General
EMMA SLEEP INDIA PRIVATE LIMITED | 01/04/2026 | 215,060 | 199,561 | 15,499 | IT & Technology | General
EMMA SLEEP INDIA PRIVATE LIMITED | 01/05/2026 | 299,607 | 278,105 | 21,502 | BFSI | General
EMMA SLEEP INDIA PRIVATE LIMITED | 01/06/2026 | 338,862 | 314,743 | 24,119 | BFSI | General
EMMA SLEEP INDIA PRIVATE LIMITED | 01/07/2026 | 390,247 | 362,456 | 27,791
ENIGOAL STARTUP ADVISORY PRIVATE LIMITED | 01/04/2026 | 35,609 | 29,007 | 6,602 | BFSI | General
ENIGOAL STARTUP ADVISORY PRIVATE LIMITED | 01/05/2026 | 30,136 | 24,548 | 5,588 | Other | General
ENIGOAL STARTUP ADVISORY PRIVATE LIMITED | 01/06/2026 | 28,195 | 22,967 | 5,228 | Other | General
ENIGOAL STARTUP ADVISORY PRIVATE LIMITED | 01/07/2026 | 39,119 | 31,866 | 7,253
Epifi Technologies Private Limited | 01/05/2026 | 20,212 | 16,259 | 3,953 | Other | General
Epifi Technologies Private Limited | 01/06/2026 | 317 | 255 | 62 | Retail | General
Equitas Small Finance Bank Ltd | 01/04/2026 | 431,536 | 384,883 | 46,653 | Other | General
Equitas Small Finance Bank Ltd | 01/05/2026 | 334,968 | 298,789 | 36,179 | BFSI | General
Equitas Small Finance Bank Ltd | 01/06/2026 | 237,310 | 211,650 | 25,660 | Healthcare | General
Equitas Small Finance Bank Ltd | 01/07/2026 | 320,597 | 285,931 | 34,666
ERULEARNING SOLUTIONS PRIVATE LIMITED | 01/05/2026 | 26,856 | 23,952 | 2,904 | Media & Entertainment | General
ERULEARNING SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 14,357 | 12,805 | 1,552 | IT & Technology | General
ERULEARNING SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 4,075 | 3,635 | 440
Exotic India Art Private Limited | 01/04/2026 | 39,987 | 35,391 | 4,596 | Retail | General
Exotic India Art Private Limited | 01/05/2026 | 121,194 | 107,129 | 14,065 | Education | General
Exotic India Art Private Limited | 01/06/2026 | 134,693 | 122,117 | 12,576 | Healthcare | General
Exotic India Art Private Limited | 01/07/2026 | 67,300 | 59,420 | 7,880
EXPLOR42 SPORTS TRAVEL LLP | 01/07/2026 | 4,141 | 3,766 | 375
Extramarks Education India Pvt. Ltd | 01/04/2026 | 153,968 | 137,195 | 16,773 | Real Estate | General
Extramarks Education India Pvt. Ltd | 01/05/2026 | 125,507 | 111,931 | 13,576 | Other | General
Extramarks Education India Pvt. Ltd | 01/06/2026 | 100,817 | 89,933 | 10,884 | Education | General
Extramarks Education India Pvt. Ltd | 01/07/2026 | 153,299 | 136,712 | 16,587
FABINDIA LIMITED | 01/04/2026 | 383,198 | 356,375 | 26,823 | Other | General
FABINDIA LIMITED | 01/05/2026 | 452,987 | 421,293 | 31,694 | BFSI | Housing Finance
FABINDIA LIMITED | 01/06/2026 | 628,425 | 584,435 | 43,990 | IT & Technology | General
FABINDIA LIMITED | 01/07/2026 | 1,136,010 | 1,056,490 | 79,520
Fashor Lifestyle Private Limited | 01/04/2026 | 2,678 | 2,182 | 496 | BFSI | General
Fashor Lifestyle Private Limited | 01/05/2026 | 2,507 | 2,042 | 465 | IT & Technology | General
Fashor Lifestyle Private Limited | 01/06/2026 | 2,323 | 1,892 | 431 | Other | General
Fashor Lifestyle Private Limited | 01/07/2026 | 1,663 | 1,354 | 309
FastCollab Systems Private Limited | 01/04/2026 | 557 | 419 | 138 | Other | General
FastCollab Systems Private Limited | 01/05/2026 | 317 | 238 | 79 | BFSI | General
FastCollab Systems Private Limited | 01/06/2026 | 393 | 295 | 98 | Other | General
FastCollab Systems Private Limited | 01/07/2026 | 517 | 388 | 129
Ferns N Petals Pvt. Ltd. | 01/04/2026 | 874,702 | 795,938 | 78,764 | Other | General
Ferns N Petals Pvt. Ltd. | 01/05/2026 | 240,188 | 205,694 | 34,494 | IT & Technology | General
Ferns N Petals Pvt. Ltd. | 01/06/2026 | 196,880 | 167,428 | 29,452 | IT & Technology | General
Ferns N Petals Pvt. Ltd. | 01/07/2026 | 205,220 | 174,688 | 30,532
FINO PAYMENTS BANK LIMITED | 01/04/2026 | 545,619 | 541,151 | 4,468 | BFSI | Housing Finance
FINO PAYMENTS BANK LIMITED | 01/05/2026 | 583,242 | 583,209 | 33 | BFSI | General
FINO PAYMENTS BANK LIMITED | 01/06/2026 | 166,104 | 166,104 | 0 | IT & Technology | General
FINO PAYMENTS BANK LIMITED | 01/07/2026 | 118,254 | 103,249 | 15,005
Finwizard Technology Pvt Ltd. (Fisdom) | 01/04/2026 | 710,540 | 660,693 | 49,847 | BFSI | General
Finwizard Technology Pvt Ltd. (Fisdom) | 01/05/2026 | 610,305 | 564,787 | 45,518 | IT & Technology | General
Finwizard Technology Pvt Ltd. (Fisdom) | 01/06/2026 | 653,896 | 606,878 | 47,018 | Manufacturing | Paints & Chemicals
Finwizard Technology Pvt Ltd. (Fisdom) | 01/07/2026 | 1,132,025 | 1,050,538 | 81,487
Flights Mojo Bookings Private Limited | 01/04/2026 | 46,844 | 42,624 | 4,220 | Healthcare | General
Flights Mojo Bookings Private Limited | 01/05/2026 | 59,323 | 53,509 | 5,814 | Healthcare | General
Flights Mojo Bookings Private Limited | 01/06/2026 | 70,604 | 64,282 | 6,322 | BFSI | General
Flights Mojo Bookings Private Limited | 01/07/2026 | 46,086 | 42,062 | 4,024
Fluidi5 Technologies Pvt Ltd | 01/04/2026 | 216 | 186 | 30 | BFSI | General
Fluidi5 Technologies Pvt Ltd | 01/05/2026 | 479 | 413 | 66 | Other | General
Fluidi5 Technologies Pvt Ltd | 01/06/2026 | 6,386 | 5,512 | 874 | Other | General
Fluidi5 Technologies Pvt Ltd | 01/07/2026 | 1,489 | 1,285 | 204
Fossil India Private Limited | 01/04/2026 | 3,005 | 2,449 | 556 | Other | General
Fossil India Private Limited | 01/05/2026 | 2,647 | 2,156 | 491 | Other | General
Fossil India Private Limited | 01/06/2026 | 3,178 | 2,588 | 590 | Other | General
Fossil India Private Limited | 01/07/2026 | 2,969 | 2,418 | 551
FPL TECHNOLOGIES PRIVATE LIMITED | 01/04/2026 | 68 | 60 | 8 | Other | General
FPL TECHNOLOGIES PRIVATE LIMITED | 01/05/2026 | 41 | 37 | 4 | Other | General
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 19 | 17 | 2 | Healthcare | General
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 3 | 2 | 1
FreshToHome Foods Pvt. Ltd. | 01/04/2026 | 503,870 | 439,431 | 64,439 | Agriculture & FMCG | General
FreshToHome Foods Pvt. Ltd. | 01/05/2026 | 515,523 | 449,188 | 66,335 | Media & Entertainment | General
FreshToHome Foods Pvt. Ltd. | 01/06/2026 | 598,051 | 518,831 | 79,220 | IT & Technology | General
FreshToHome Foods Pvt. Ltd. | 01/07/2026 | 520,557 | 454,538 | 66,019
GC Web Ventures Private Limited | 01/06/2026 | 246,247 | 246,879 | -632 | Other | General
GC Web Ventures Private Limited | 01/07/2026 | 685,877 | 687,636 | -1,759
Genxlead Retail Private Ltd | 01/04/2026 | 309,315 | 275,870 | 33,445 | BFSI | Fintech
Genxlead Retail Private Ltd | 01/05/2026 | 276,601 | 246,693 | 29,908 | Other | General
Genxlead Retail Private Ltd | 01/06/2026 | 267,602 | 238,666 | 28,936 | BFSI | Fintech
Genxlead Retail Private Ltd | 01/07/2026 | 47,029 | 41,943 | 5,086
GIM INFO SOLUTIONS PRIVATE LIMITED | 01/04/2026 | 155,257 | 124,172 | 31,085 | Retail | General
GIM INFO SOLUTIONS PRIVATE LIMITED | 01/05/2026 | 150,632 | 120,228 | 30,404 | Healthcare | General
GIM INFO SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 168,893 | 136,142 | 32,751 | Healthcare | General
GIM INFO SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 189,960 | 154,340 | 35,620
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/04/2026 | 358,994 | 320,175 | 38,819 | BFSI | General
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/05/2026 | 420,799 | 375,203 | 45,596 | Other | General
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/06/2026 | 248,572 | 221,694 | 26,878 | Other | General
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/07/2026 | 160,482 | 143,127 | 17,355
GMR AIRPORTS LIMITED | 01/04/2026 | 3,019 | 2,692 | 327 | Other | General
GMR AIRPORTS LIMITED | 01/05/2026 | 6,431 | 5,735 | 696 | Other | General
GMR AIRPORTS LIMITED | 01/06/2026 | 46,777 | 42,981 | 3,796 | Other | General
GMR AIRPORTS LIMITED | 01/07/2026 | 27,330 | 24,068 | 3,262
Goal Corporation Private Limited | 01/05/2026 | 15,742 | 14,040 | 1,702 | Other | General
Goan Football Club Private Limited | 01/04/2026 | 6,521 | 6,254 | 267 | IT & Technology | General
Goan Football Club Private Limited | 01/05/2026 | 3 | 3 | 0 | IT & Technology | General
Godrej & Boyce Mfg.Co.Ltd. | 01/06/2026 | 2,288 | 1,945 | 343 | Other | General
Godrej & Boyce Mfg.Co.Ltd. | 01/07/2026 | 4,061 | 3,492 | 569
Good Folks Fashion Pvt. Ltd. | 01/04/2026 | 16,199 | 14,448 | 1,751 | Other | General
Good Folks Fashion Pvt. Ltd. | 01/05/2026 | 16,827 | 15,014 | 1,813 | BFSI | Mutual Fund
Good Folks Fashion Pvt. Ltd. | 01/06/2026 | 12,947 | 11,577 | 1,370 | Healthcare | General
Good Folks Fashion Pvt. Ltd. | 01/07/2026 | 4,974 | 4,436 | 538
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/04/2026 | 806,654 | 719,461 | 87,193 | IT & Technology | General
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/05/2026 | 815,624 | 727,479 | 88,145 | Other | General
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/06/2026 | 1,003,902 | 895,348 | 108,554 | Other | General
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/07/2026 | 1,090,711 | 972,770 | 117,941
Greytip Software Private Limited | 01/06/2026 | 180 | 140 | 40 | Other | General
Greytip Software Private Limited | 01/07/2026 | 147 | 115 | 32
GRT Jewellers (India) Pvt. Ltd. | 01/04/2026 | 794,727 | 707,915 | 86,812 | IT & Technology | General
GRT Jewellers (India) Pvt. Ltd. | 01/05/2026 | 175,291 | 155,820 | 19,471 | IT & Technology | General
GRT Jewellers (India) Pvt. Ltd. | 01/06/2026 | 514,910 | 478,332 | 36,578 | BFSI | Housing Finance
GRT Jewellers (India) Pvt. Ltd. | 01/07/2026 | 451,115 | 419,101 | 32,014
GUVI Geek Network Private Limited | 01/04/2026 | 722,839 | 642,903 | 79,936 | IT & Technology | General
GUVI Geek Network Private Limited | 01/05/2026 | 767,599 | 678,879 | 88,720 | Manufacturing | Paints & Chemicals
GUVI Geek Network Private Limited | 01/06/2026 | 1,023,466 | 911,200 | 112,266 | Healthcare | General
GUVI Geek Network Private Limited | 01/07/2026 | 1,065,899 | 950,465 | 115,434
Hairdramaco India Private Limited | 01/04/2026 | 1,770 | 1,559 | 211 | Other | General
Hairdramaco India Private Limited | 01/05/2026 | 158 | 136 | 22 | Other | General
Hamilton Sciences Private Limited | 01/04/2026 | 22,280 | 19,871 | 2,409 | Other | General
Hamilton Sciences Private Limited | 01/05/2026 | 8,032 | 7,163 | 869 | Other | General
Hamilton Sciences Private Limited | 01/06/2026 | 4,533 | 4,043 | 490 | Retail | General
Hansa Customer Equity Pvt. Ltd. | 01/04/2026 | 3 | 2 | 1 | Other | General
HDFC Asset Management Company Ltd. | 01/04/2026 | 881,519 | 786,203 | 95,316 | Manufacturing | Paints & Chemicals
HDFC Asset Management Company Ltd. | 01/05/2026 | 688,598 | 614,145 | 74,453 | Other | General
HDFC Asset Management Company Ltd. | 01/06/2026 | 1,258,626 | 1,122,526 | 136,100 | Other | General
HDFC Asset Management Company Ltd. | 01/07/2026 | 1,514,735 | 1,350,941 | 163,794
Healthmug Private Limited | 01/04/2026 | 64,033 | 53,375 | 10,658 | BFSI | General
Healthmug Private Limited | 01/05/2026 | 60,048 | 49,993 | 10,055 | BFSI | General
Healthmug Private Limited | 01/06/2026 | 87,932 | 74,486 | 13,446 | IT & Technology | General
Healthmug Private Limited | 01/07/2026 | 95,300 | 80,790 | 14,510
HeidelbergCement India Limited | 01/04/2026 | 35,991 | 31,033 | 4,958 | Education | General
HeidelbergCement India Limited | 01/05/2026 | 119,422 | 103,069 | 16,353 | Other | General
HeidelbergCement India Limited | 01/06/2026 | 4,286 | 3,694 | 592 | Other | General
HeidelbergCement India Limited | 01/07/2026 | 229,159 | 197,782 | 31,377
Helios Capital Asset Management (India) Private Limited | 01/04/2026 | 3 | 3 | 0 | BFSI | General
Helios Capital Asset Management (India) Private Limited | 01/06/2026 | 4,692 | 4,499 | 193 | Other | General
Helios Capital Asset Management (India) Private Limited | 01/07/2026 | 23,728 | 22,755 | 973
Heydude Footwear Private Limited. | 01/04/2026 | 1,271 | 1,219 | 52 | Other | General
Heydude Footwear Private Limited. | 01/05/2026 | 3,569 | 3,423 | 146 | Other | General
Heydude Footwear Private Limited. | 01/06/2026 | 24,042 | 23,056 | 986 | Other | General
Heydude Footwear Private Limited. | 01/07/2026 | 10,051 | 9,639 | 412
Hicare Services Pvt. Ltd. | 01/04/2026 | 1,533 | 1,323 | 210 | Other | General
Hicare Services Pvt. Ltd. | 01/05/2026 | 28,607 | 24,691 | 3,916 | Education | General
Hicare Services Pvt. Ltd. | 01/06/2026 | 65,446 | 56,486 | 8,960 | IT & Technology | General
Hicare Services Pvt. Ltd. | 01/07/2026 | 38,711 | 33,411 | 5,300
HR ANEXI PRIVATE LIMITED | 01/04/2026 | 14 | 12 | 2 | IT & Technology | General
HR ANEXI PRIVATE LIMITED | 01/06/2026 | 138 | 123 | 15 | Other | General
HR ANEXI PRIVATE LIMITED | 01/07/2026 | 1 | 1 | 0
HSBC Asset Management India Private Limited | 01/04/2026 | 47,609 | 42,462 | 5,147 | BFSI | General
HSBC Asset Management India Private Limited | 01/05/2026 | 151,962 | 135,531 | 16,431 | Other | General
HSBC Asset Management India Private Limited | 01/06/2026 | 36,707 | 32,738 | 3,969 | Other | General
HSBC Asset Management India Private Limited | 01/07/2026 | 216,752 | 193,314 | 23,438
HSS Apparel Private Limited | 01/04/2026 | 4,747 | 4,415 | 332 | Other | General
HSS Apparel Private Limited | 01/05/2026 | 60,638 | 56,397 | 4,241 | Other | General
HSS Apparel Private Limited | 01/06/2026 | 24,749 | 23,016 | 1,733 | BFSI | General
HSS Apparel Private Limited | 01/07/2026 | 34,257 | 31,859 | 2,398
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/05/2026 | 225,536 | 201,192 | 24,344 | Other | General
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/06/2026 | 87,577 | 78,108 | 9,469 | Other | General
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/07/2026 | 10,697 | 9,540 | 1,157
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/04/2026 | 3,990,834 | 3,711,494 | 279,340 | BFSI | Life Insurance
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/05/2026 | 2,806,729 | 2,610,845 | 195,884 | BFSI | Life Insurance
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 2,264,110 | 2,107,473 | 156,637 | BFSI | Life Insurance
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 3,931,938 | 3,623,996 | 307,942 | Other | General
IDFC Asset Management Company Limited | 01/04/2026 | 28,338 | 18,467 | 9,871 | Other | General
IDFC Asset Management Company Limited | 01/05/2026 | 25,789 | 16,806 | 8,983 | BFSI | General
IDFC Asset Management Company Limited | 01/06/2026 | 26,979 | 17,582 | 9,397 | IT & Technology | General
IDFC Asset Management Company Limited | 01/07/2026 | 31,828 | 20,741 | 11,087
IGUIDER LEARNING PRIVATE LIMITED | 01/04/2026 | 25,952 | 23,147 | 2,805 | Education | General
IGUIDER LEARNING PRIVATE LIMITED | 01/05/2026 | 69,863 | 62,310 | 7,553 | Retail | General
IGUIDER LEARNING PRIVATE LIMITED | 01/06/2026 | 44,845 | 39,996 | 4,849 | Retail | General
IGUIDER LEARNING PRIVATE LIMITED | 01/07/2026 | 88,171 | 78,638 | 9,533
IIFL Finance Limited | 01/04/2026 | 163,344 | 131,965 | 31,379 | Healthcare | General
IIFL Finance Limited | 01/05/2026 | 141,149 | 114,304 | 26,845 | Retail | General
IIFL Finance Limited | 01/06/2026 | 128,753 | 104,401 | 24,352 | Real Estate | General
IIFL Finance Limited | 01/07/2026 | 131,962 | 106,498 | 25,464
IIFL Home Finance Limited | 01/04/2026 | 203,864 | 166,606 | 37,258 | Other | General
IIFL Home Finance Limited | 01/05/2026 | 189,032 | 153,638 | 35,394 | Other | General
IIFL Home Finance Limited | 01/06/2026 | 410,094 | 350,404 | 59,690 | Agriculture & FMCG | General
IIFL Home Finance Limited | 01/07/2026 | 620,471 | 537,508 | 82,963
IIFL Securities Limited | 01/04/2026 | 3,137 | 2,744 | 393 | IT & Technology | General
IIFL Securities Limited | 01/05/2026 | 35,592 | 31,694 | 3,898 | Media & Entertainment | General
IIFL Securities Limited | 01/06/2026 | 35,608 | 31,664 | 3,944 | Other | General
IIFL Securities Limited | 01/07/2026 | 20,762 | 18,334 | 2,428
Imagicaaworld Entertainment Limited | 01/04/2026 | 25,895 | 21,544 | 4,351 | IT & Technology | General
Imagicaaworld Entertainment Limited | 01/05/2026 | 5,875 | 4,913 | 962 | Other | General
IMAGITHON TECHNOLOGIES PRIVATE LIMITED | 01/04/2026 | 29,201 | 27,046 | 2,155 | IT & Technology | General
IMAGITHON TECHNOLOGIES PRIVATE LIMITED | 01/05/2026 | 50,555 | 46,550 | 4,005 | Other | General
IMAGITHON TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 43,108 | 39,626 | 3,482 | BFSI | Life Insurance
IMAGITHON TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 70,042 | 64,608 | 5,434
Impact Guru Foundation | 01/04/2026 | 10,093 | 9,013 | 1,080 | Other | General
Impact Guru Foundation | 01/05/2026 | 1,850 | 1,650 | 200 | BFSI | General
Impact Guru Foundation | 01/06/2026 | 374 | 321 | 53 | BFSI | General
Impact Guru Foundation | 01/07/2026 | 1,658 | 1,467 | 191
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/04/2026 | 0 | 0 | 0 | Other | General
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/05/2026 | 0 | 0 | 0 | Retail | General
Impulse Educational Institutions Private Limited | 01/04/2026 | 121 | 79 | 42 | IT & Technology | General
Impulse Educational Institutions Private Limited | 01/05/2026 | 42,039 | 37,471 | 4,568 | BFSI | General
Impulse Educational Institutions Private Limited | 01/06/2026 | 27 | 23 | 4 | Other | General
Impulse Educational Institutions Private Limited | 01/07/2026 | 13,402 | 11,951 | 1,451
IMPULSE INTERNATIONAL PRIVATE LIMITED | 01/04/2026 | 285,054 | 254,123 | 30,931 | Other | General
IMPULSE INTERNATIONAL PRIVATE LIMITED | 01/05/2026 | 323,582 | 288,453 | 35,129 | Other | General
IMPULSE INTERNATIONAL PRIVATE LIMITED | 01/06/2026 | 205,138 | 182,747 | 22,391 | IT & Technology | General
IMPULSE INTERNATIONAL PRIVATE LIMITED | 01/07/2026 | 148,968 | 132,756 | 16,212
IMS Learning Resource Private Limited | 01/04/2026 | 40,286 | 35,740 | 4,546 | BFSI | General
IMS Learning Resource Private Limited | 01/05/2026 | 43,600 | 38,466 | 5,134 | BFSI | General
IMS Learning Resource Private Limited | 01/06/2026 | 22,484 | 19,677 | 2,807 | BFSI | Mutual Fund
IMS Learning Resource Private Limited | 01/07/2026 | 41,649 | 36,675 | 4,974
India Health Action Trust | 01/07/2026 | 19,488 | 15,875 | 3,613
INDIA INTERNATIONAL CENTRE | 01/04/2026 | 3,611 | 3,111 | 500 | Other | General
INDIA INTERNATIONAL CENTRE | 01/05/2026 | 9,841 | 8,243 | 1,598 | Other | General
INDIA INTERNATIONAL CENTRE | 01/06/2026 | 12,184 | 10,508 | 1,676 | Other | General
INDIA INTERNATIONAL CENTRE | 01/07/2026 | 10,137 | 8,749 | 1,388
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/05/2026 | 664,148 | 611,626 | 52,522 | IT & Technology | General
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 602,498 | 554,727 | 47,771 | Other | General
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 892,558 | 821,860 | 70,698
Innovative and Technological Learning Services Pvt Ltd | 01/04/2026 | 3,193 | 2,843 | 350 | Other | General
Innovative and Technological Learning Services Pvt Ltd | 01/05/2026 | 0 | 0 | 0 | Other | General
Innovative and Technological Learning Services Pvt Ltd | 01/07/2026 | 0 | 0 | 0
INNOVITI TECHNOLOGIES PRIVATE LIMITED | 01/04/2026 | 252,393 | 223,812 | 28,581 | Other | General
INNOVITI TECHNOLOGIES PRIVATE LIMITED | 01/05/2026 | 216,492 | 191,718 | 24,774 | Other | General
INNOVITI TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 296,690 | 263,124 | 33,566 | BFSI | General
INNOVITI TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 300,769 | 266,655 | 34,114
Intelligence India.com Limited | 01/04/2026 | 2,566 | 2,288 | 278 | Other | General
Intelligence India.com Limited | 01/05/2026 | 2,899 | 2,586 | 313 | Other | General
Intelligence India.com Limited | 01/06/2026 | 35,092 | 31,154 | 3,938 | Education | General
Intelligence India.com Limited | 01/07/2026 | 5,116 | 4,583 | 533
Internship Studio | 01/04/2026 | 42,619 | 34,343 | 8,276 | BFSI | General
Internship Studio | 01/05/2026 | 60,100 | 49,257 | 10,843 | BFSI | General
Internship Studio | 01/06/2026 | 82,014 | 67,435 | 14,579 | BFSI | Payments Bank
Internship Studio | 01/07/2026 | 64,405 | 53,162 | 11,243
Intracxn Sports Private Limited | 01/06/2026 | 5,912 | 5,670 | 242 | Other | General
Intracxn Sports Private Limited | 01/07/2026 | 19,576 | 18,773 | 803
ISKCON PUNE NVCC | 01/04/2026 | 3,104 | 2,977 | 127 | Other | General
ISKCON PUNE NVCC | 01/05/2026 | 73,805 | 70,779 | 3,026 | Other | General
ISKCON PUNE NVCC | 01/06/2026 | 336,785 | 322,977 | 13,808 | BFSI | General
ISKCON PUNE NVCC | 01/07/2026 | 268,179 | 257,184 | 10,995
JABRA CONNECT INDIA PRIVATE LIMITED | 01/04/2026 | 22,414 | 21,495 | 919 | Other | General
JABRA CONNECT INDIA PRIVATE LIMITED | 01/05/2026 | 26,968 | 25,862 | 1,106 | Other | General
JABRA CONNECT INDIA PRIVATE LIMITED | 01/06/2026 | 39,164 | 37,558 | 1,606 | BFSI | General
JABRA CONNECT INDIA PRIVATE LIMITED | 01/07/2026 | 19,632 | 18,827 | 805
Jagati Publications Limited | 01/04/2026 | 5,567 | 3,628 | 1,939 | Other | General
Jagati Publications Limited | 01/05/2026 | 4,308 | 2,808 | 1,500 | Other | General
Jagati Publications Limited | 01/06/2026 | 3,735 | 2,434 | 1,301 | BFSI | General
Jagati Publications Limited | 01/07/2026 | 4,103 | 2,674 | 1,429
Jainam Broking Limited | 01/05/2026 | 12 | 10 | 2 | Education | General
Jainam Broking Limited | 01/06/2026 | 34 | 31 | 3 | IT & Technology | General
Jainam Broking Limited | 01/07/2026 | 99 | 88 | 11
Jaro Institute of Technology Management and Research Limited | 01/04/2026 | 58,417 | 52,233 | 6,184 | Other | General
Jaro Institute of Technology Management and Research Limited | 01/05/2026 | 17,717 | 15,802 | 1,915 | BFSI | Mutual Fund
Jaro Institute of Technology Management and Research Limited | 01/06/2026 | 1 | 1 | 0 | BFSI | NBFC
JOHN SALT PRIVATE LIMITED | 01/04/2026 | 52,668 | 46,973 | 5,695 | Other | General
JOHN SALT PRIVATE LIMITED | 01/05/2026 | 94,959 | 84,691 | 10,268 | Other | General
JOHN SALT PRIVATE LIMITED | 01/06/2026 | 299,681 | 267,277 | 32,404 | Other | General
JOHN SALT PRIVATE LIMITED | 01/07/2026 | 387,290 | 345,412 | 41,878
Join Ventures Solutions Private Limited | 01/04/2026 | 865,347 | 765,558 | 99,789 | Other | General
Join Ventures Solutions Private Limited | 01/05/2026 | 1,443,005 | 1,278,353 | 164,652 | Other | General
Join Ventures Solutions Private Limited | 01/06/2026 | 1,187,014 | 1,104,343 | 82,671 | IT & Technology | General
Join Ventures Solutions Private Limited | 01/07/2026 | 1,434,294 | 1,233,867 | 200,427
JUST DIAL LIMITED | 01/04/2026 | 41 | 39 | 2 | Other | General
JUST DIAL LIMITED | 01/07/2026 | 1 | 1 | 0
K M Dastur Reinsurance Brokers Pvt Ltd | 01/04/2026 | 11,932 | 10,641 | 1,291 | Other | General
K M Dastur Reinsurance Brokers Pvt Ltd | 01/05/2026 | 2,187 | 1,950 | 237 | Other | General
K M Dastur Reinsurance Brokers Pvt Ltd | 01/06/2026 | 12,710 | 11,335 | 1,375 | Other | General
K M Dastur Reinsurance Brokers Pvt Ltd | 01/07/2026 | 111 | 97 | 14
K7 COMPUTING PRIVATE LIMITED | 01/04/2026 | 29,434 | 26,156 | 3,278 | Other | General
K7 COMPUTING PRIVATE LIMITED | 01/05/2026 | 43,733 | 38,863 | 4,870 | BFSI | Life Insurance
K7 COMPUTING PRIVATE LIMITED | 01/06/2026 | 38,731 | 34,418 | 4,313 | BFSI | General
K7 COMPUTING PRIVATE LIMITED | 01/07/2026 | 56,086 | 49,840 | 6,246
Kaamlo Platform Private Limited | 01/04/2026 | 0 | 0 | 0 | Other | General
Kaamlo Platform Private Limited | 01/05/2026 | 2 | 2 | 0 | Other | General
Kaamlo Platform Private Limited | 01/06/2026 | 6 | 4 | 2 | IT & Technology | General
Kaamlo Platform Private Limited | 01/07/2026 | 2 | 1 | 1
Katyayani Organics | 01/04/2026 | 10,070 | 8,403 | 1,667 | IT & Technology | General
Katyayani Organics | 01/05/2026 | 8,208 | 6,856 | 1,352 | Other | General
Katyayani Organics | 01/06/2026 | 37,775 | 33,056 | 4,719 | IT & Technology | General
Katyayani Organics | 01/07/2026 | 91,201 | 79,713 | 11,488
Khelomore Sports Private Limited | 01/04/2026 | 97,635 | 84,269 | 13,366 | BFSI | Payments Bank
Khelomore Sports Private Limited | 01/05/2026 | 85,296 | 73,619 | 11,677 | Retail | General
Khelomore Sports Private Limited | 01/06/2026 | 46,637 | 40,252 | 6,385 | BFSI | General
Khelomore Sports Private Limited | 01/07/2026 | 43,955 | 37,938 | 6,017
Kirtilal Kalidas Jewellers Pvt Ltd | 01/04/2026 | 101,072 | 90,145 | 10,927 | Other | General
Kirtilal Kalidas Jewellers Pvt Ltd | 01/05/2026 | 915 | 816 | 99 | Other | General
Kirtilal Kalidas Jewellers Pvt Ltd | 01/06/2026 | 100,956 | 90,040 | 10,916 | BFSI | Small Finance Bank
Kirtilal Kalidas Jewellers Pvt Ltd | 01/07/2026 | 70,127 | 62,544 | 7,583
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/04/2026 | 519,671 | 469,205 | 50,466 | Other | General
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/05/2026 | 160,353 | 141,783 | 18,570 | BFSI | General
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/06/2026 | 202,590 | 180,390 | 22,200 | Other | General
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/07/2026 | 500,107 | 450,988 | 49,119
Kotak Mahindra General Insurance Company Limited | 01/04/2026 | 186,176 | 163,832 | 22,344 | Other | General
Kotak Mahindra General Insurance Company Limited | 01/05/2026 | 183,964 | 161,044 | 22,920 | Healthcare | General
Kotak Mahindra General Insurance Company Limited | 01/06/2026 | 114,314 | 100,966 | 13,348 | BFSI | General
Kotak Mahindra General Insurance Company Limited | 01/07/2026 | 123,518 | 107,462 | 16,056
Kotak Securities Limited | 01/04/2026 | 1,557,241 | 1,448,239 | 109,002 | Other | General
Kotak Securities Limited | 01/05/2026 | 1,292,788 | 1,202,233 | 90,555 | IT & Technology | General
Kotak Securities Limited | 01/06/2026 | 3,433,269 | 3,192,940 | 240,329 | Other | General
Kotak Securities Limited | 01/07/2026 | 1,023,021 | 977,574 | 45,447
Limelight Lab Grown Diamonds Limited | 01/04/2026 | 3,062 | 2,627 | 435 | Retail | General
Limelight Lab Grown Diamonds Limited | 01/05/2026 | 2,352 | 2,016 | 336 | Other | General
Limelight Lab Grown Diamonds Limited | 01/06/2026 | 77,038 | 66,475 | 10,563 | Other | General
Limelight Lab Grown Diamonds Limited | 01/07/2026 | 53,646 | 46,280 | 7,366
Living Media India Ltd | 01/04/2026 | 52,536 | 46,773 | 5,763 | Other | General
Living Media India Ltd | 01/05/2026 | 44,347 | 39,391 | 4,956 | BFSI | Life Insurance
Living Media India Ltd | 01/06/2026 | 71,495 | 63,491 | 8,004 | IT & Technology | General
Living Media India Ltd | 01/07/2026 | 72,233 | 63,627 | 8,606
Logic ERP Solutions Pvt. Ltd. | 01/04/2026 | 10,008 | 6,541 | 3,467 | Other | General
Logic ERP Solutions Pvt. Ltd. | 01/05/2026 | 8,955 | 5,846 | 3,109 | Other | General
Logic ERP Solutions Pvt. Ltd. | 01/06/2026 | 7,730 | 5,056 | 2,674 | IT & Technology | General
Logic ERP Solutions Pvt. Ltd. | 01/07/2026 | 8,731 | 5,699 | 3,032
Magicbricks Realty Services Limited | 01/04/2026 | 477,033 | 434,183 | 42,850 | Other | General
Magicbricks Realty Services Limited | 01/05/2026 | 496,875 | 452,368 | 44,507 | BFSI | Housing Finance
Magicbricks Realty Services Limited | 01/06/2026 | 526,279 | 479,262 | 47,017 | Media & Entertainment | General
Magicbricks Realty Services Limited | 01/07/2026 | 532,591 | 484,913 | 47,678
Manash Lifestyle Pvt. Ltd. | 01/04/2026 | 3,669,050 | 3,222,878 | 446,172 | Media & Entertainment | General
Manash Lifestyle Pvt. Ltd. | 01/05/2026 | 4,501,780 | 3,969,512 | 532,268 | Healthcare | General
Manash Lifestyle Pvt. Ltd. | 01/06/2026 | 3,858,316 | 3,372,137 | 486,179 | Media & Entertainment | General
Manash Lifestyle Pvt. Ltd. | 01/07/2026 | 4,060,740 | 3,552,745 | 507,995 | Other | General
Manipal Technologies Limited | 01/04/2026 | 4,444 | 3,103 | 1,341 | Other | General
Manipal Technologies Limited | 01/05/2026 | 1 | 1 | 0 | BFSI | NBFC
Manipal Technologies Limited | 01/06/2026 | 1 | 1 | 0 | BFSI | General
Marks and Spencer Reliance India Private Limited | 01/04/2026 | 5,359 | 5,240 | 119 | BFSI | General
Marks and Spencer Reliance India Private Limited | 01/05/2026 | 6,079 | 5,948 | 131 | Other | General
Marks and Spencer Reliance India Private Limited | 01/06/2026 | 68,207 | 67,643 | 564 | Other | General
Marks and Spencer Reliance India Private Limited | 01/07/2026 | 244,807 | 243,469 | 1,338
Max Life Insurance Co. Ltd. | 01/04/2026 | 9,858,984 | 9,313,570 | 545,414 | Other | General
Max Life Insurance Co. Ltd. | 01/05/2026 | 10,791,575 | 10,414,178 | 377,397 | Healthcare | General
Max Life Insurance Co. Ltd. | 01/06/2026 | 10,914,159 | 10,578,197 | 335,962 | Other | General
Max Life Insurance Co. Ltd. | 01/07/2026 | 10,401,265 | 9,980,898 | 420,367 | Other | General
Metropolis Healthcare Limited | 01/04/2026 | 464,609 | 432,087 | 32,522 | IT & Technology | General
Metropolis Healthcare Limited | 01/05/2026 | 355,932 | 331,017 | 24,915 | IT & Technology | General
Metropolis Healthcare Limited | 01/06/2026 | 555,737 | 516,836 | 38,901 | BFSI | Life Insurance
Metropolis Healthcare Limited | 01/07/2026 | 438,609 | 407,907 | 30,702
Meyer Housewares India Pvt Ltd | 01/06/2026 | 47,432 | 42,303 | 5,129 | Other | General
Meyer Housewares India Pvt Ltd | 01/07/2026 | 24,392 | 21,754 | 2,638
Microgravity Ventures Private Limited | 01/04/2026 | 329 | 284 | 45 | Media & Entertainment | General
Microgravity Ventures Private Limited | 01/05/2026 | 49 | 42 | 7 | Other | General
Microgravity Ventures Private Limited | 01/06/2026 | 52 | 45 | 7 | IT & Technology | General
Microgravity Ventures Private Limited | 01/07/2026 | 77 | 66 | 11
MILES EDUCATION PRIVATE LIMITED | 01/04/2026 | 594,584 | 530,010 | 64,574 | BFSI | Housing Finance
MILES EDUCATION PRIVATE LIMITED | 01/05/2026 | 862,690 | 767,337 | 95,353 | IT & Technology | General
MILES EDUCATION PRIVATE LIMITED | 01/06/2026 | 531,026 | 467,728 | 63,298 | BFSI | Life Insurance
MILES EDUCATION PRIVATE LIMITED | 01/07/2026 | 670,318 | 591,870 | 78,448
MIRAE ASSET FINANCIAL SERVICES (INDIA) PRIVATE LIMITED | 01/04/2026 | 106,139 | 94,449 | 11,690 | Other | General
MIRAE ASSET FINANCIAL SERVICES (INDIA) PRIVATE LIMITED | 01/05/2026 | 78,236 | 68,967 | 9,269 | Other | General
MIRAE ASSET FINANCIAL SERVICES (INDIA) PRIVATE LIMITED | 01/06/2026 | 76,310 | 67,248 | 9,062 | Other | General
MIRAE ASSET FINANCIAL SERVICES (INDIA) PRIVATE LIMITED | 01/07/2026 | 139,272 | 123,444 | 15,828
Miraggio Lifestyles Private Limited | 01/04/2026 | 277,140 | 246,837 | 30,303 | Healthcare | General
Miraggio Lifestyles Private Limited | 01/05/2026 | 18,315 | 15,782 | 2,533 | Other | General
Miraggio Lifestyles Private Limited | 01/06/2026 | 49,580 | 43,837 | 5,743 | BFSI | General
Miraggio Lifestyles Private Limited | 01/07/2026 | 75,600 | 67,145 | 8,455
MO Alternate Investment Advisors Private Limited | 01/04/2026 | 6 | 6 | 0 | Other | General
Mojo Markets Pvt. Ltd. | 01/04/2026 | 19 | 18 | 1 | Other | General
Mojo Markets Pvt. Ltd. | 01/05/2026 | 105 | 101 | 4 | Other | General
Mojo Markets Pvt. Ltd. | 01/06/2026 | 59 | 57 | 2 | Other | General
Mojo Markets Pvt. Ltd. | 01/07/2026 | 12 | 11 | 1
MONEYWISE FINVEST LIMITED | 01/04/2026 | 3,395 | 2,772 | 623 | Other | General
MONEYWISE FINVEST LIMITED | 01/05/2026 | 3,613 | 2,954 | 659 | BFSI | General
MONEYWISE FINVEST LIMITED | 01/06/2026 | 4,920 | 4,128 | 792 | IT & Technology | General
MONEYWISE FINVEST LIMITED | 01/07/2026 | 3,207 | 2,601 | 606
Mountain Valley Springs India Private Limited | 01/04/2026 | 86,122 | 77,324 | 8,798 | IT & Technology | General
Mountain Valley Springs India Private Limited | 01/05/2026 | 262,735 | 234,326 | 28,409 | Healthcare | General
Mountain Valley Springs India Private Limited | 01/06/2026 | 6,676 | 5,954 | 722 | IT & Technology | General
Mountain Valley Springs India Private Limited | 01/07/2026 | 404,285 | 360,569 | 43,716
Mumbai City Football India Private Limited | 01/04/2026 | 15 | 12 | 3 | IT & Technology | General
Muthoot Fincorp Ltd. | 01/04/2026 | 2,690,375 | 2,399,483 | 290,892 | Other | General
Muthoot Fincorp Ltd. | 01/05/2026 | 2,259,089 | 2,014,904 | 244,185 | Other | General
Muthoot Fincorp Ltd. | 01/06/2026 | 2,023,531 | 1,804,727 | 218,804 | Other | General
Muthoot Fincorp Ltd. | 01/07/2026 | 1,979,963 | 1,765,870 | 214,093
My Money Mantra Fintech Pvt Ltd | 01/04/2026 | 18,799 | 15,979 | 2,820 | IT & Technology | General
My Money Mantra Fintech Pvt Ltd | 01/05/2026 | 11,635 | 9,890 | 1,745 | Other | General
My Money Mantra Fintech Pvt Ltd | 01/06/2026 | 403,445 | 342,928 | 60,517 | Other | General
My Money Mantra Fintech Pvt Ltd | 01/07/2026 | 229,226 | 194,842 | 34,384
MYDESIGNATION ONLINE CLOTHING | 01/04/2026 | 59,246 | 55,099 | 4,147 | Agriculture & FMCG | General
MYDESIGNATION ONLINE CLOTHING | 01/05/2026 | 60,250 | 56,032 | 4,218 | Other | General
MYDESIGNATION ONLINE CLOTHING | 01/06/2026 | 2,627 | 2,443 | 184 | BFSI | General
Mysore Saree Udyog LLP | 01/04/2026 | 5,443 | 4,698 | 745 | Other | General
Mysore Saree Udyog LLP | 01/05/2026 | 2,592 | 2,237 | 355 | BFSI | General
Mysore Saree Udyog LLP | 01/06/2026 | 34,903 | 30,125 | 4,778 | Other | General
Mysore Saree Udyog LLP | 01/07/2026 | 37,642 | 32,489 | 5,153
Nalli Silk Sarees Private Limited | 01/04/2026 | 23,936 | 21,348 | 2,588 | Other | General
Nalli Silk Sarees Private Limited | 01/05/2026 | 26,363 | 23,512 | 2,851 | Other | General
Nalli Silk Sarees Private Limited | 01/06/2026 | 18,876 | 16,835 | 2,041 | Media & Entertainment | General
Nalli Silk Sarees Private Limited | 01/07/2026 | 28,585 | 25,445 | 3,140
Navia Markets Limited | 01/04/2026 | 0 | 0 | 0 | Healthcare | General
Navia Markets Limited | 01/05/2026 | 0 | 0 | 0 | Other | General
Navia Markets Limited | 01/07/2026 | 250 | 223 | 27
Navmaya Tech Services Private Limited | 01/05/2026 | 13,221 | 11,791 | 1,430 | Other | General
Navmaya Tech Services Private Limited | 01/06/2026 | 30,192 | 26,928 | 3,264 | Other | General
Navmaya Tech Services Private Limited | 01/07/2026 | 144,720 | 129,071 | 15,649
NCDEX e Markets Limited | 01/04/2026 | 220 | 92 | 128 | BFSI | General
NCDEX e Markets Limited | 01/05/2026 | 267 | 87 | 180 | Travel & Aviation | General
NCDEX e Markets Limited | 01/06/2026 | 620 | 218 | 402 | Education | General
NCDEX e Markets Limited | 01/07/2026 | 702 | 281 | 421
NEARBUY INDIA PRIVATE LIMITED | 01/04/2026 | 2 | 2 | 0 | Other | General
NETWAY INDIA PRIVATE LIMITED | 01/04/2026 | 317,328 | 288,858 | 28,470 | Travel & Aviation | General
NETWAY INDIA PRIVATE LIMITED | 01/05/2026 | 152,627 | 138,745 | 13,882 | IT & Technology | General
NETWAY INDIA PRIVATE LIMITED | 01/06/2026 | 218,831 | 209,171 | 9,660 | Healthcare | General
NETWAY INDIA PRIVATE LIMITED | 01/07/2026 | 194,059 | 175,258 | 18,801
New India Cables Trading Pvt. Ltd. | 01/04/2026 | 677 | 473 | 204 | Other | General
New India Cables Trading Pvt. Ltd. | 01/05/2026 | 646 | 451 | 195 | Education | General
New India Cables Trading Pvt. Ltd. | 01/06/2026 | 657 | 459 | 198 | IT & Technology | General
New India Cables Trading Pvt. Ltd. | 01/07/2026 | 665 | 464 | 201
Nextspeed Technologies Private Limited | 01/04/2026 | 42,771 | 38,716 | 4,055 | Manufacturing | General
Nextspeed Technologies Private Limited | 01/05/2026 | 31,500 | 27,402 | 4,098 | Other | General
Nextspeed Technologies Private Limited | 01/06/2026 | 28,025 | 24,292 | 3,733 | Other | General
Nextspeed Technologies Private Limited | 01/07/2026 | 30,979 | 27,095 | 3,884
Nirmit Bharat - SMS - WhatsApp - SISL | 01/04/2026 | 147,207 | 121,816 | 25,391 | Other | General
Nirmit Bharat - SMS - WhatsApp - SISL | 01/05/2026 | 317,331 | 303,849 | 13,482 | Travel & Aviation | General
Nirmit Bharat - SMS - WhatsApp - SISL | 01/06/2026 | 455,063 | 436,296 | 18,767 | BFSI | Housing Finance
Nirmit Bharat - SMS - WhatsApp - SISL | 01/07/2026 | 596,428 | 550,691 | 45,737
NSE ACADEMY LIMITED | 01/04/2026 | 1 | 0 | 1 | IT & Technology | General
NSE ACADEMY LIMITED | 01/05/2026 | 3 | 2 | 1 | Other | General
NSE ACADEMY LIMITED | 01/06/2026 | 8 | 6 | 2 | Other | General
NSE ACADEMY LIMITED | 01/07/2026 | 1 | 0 | 1
Nuvama Clearing Services Limited | 01/04/2026 | 41,773 | 32,510 | 9,263 | Other | General
Nuvama Clearing Services Limited | 01/05/2026 | 64,497 | 53,995 | 10,502 | Other | General
Nuvama Clearing Services Limited | 01/06/2026 | 167,014 | 149,217 | 17,797 | Other | General
Nuvama Clearing Services Limited | 01/07/2026 | 329,104 | 302,980 | 26,124
Nuvama Wealth and Investment Limited | 01/04/2026 | 287,983 | 256,677 | 31,306 | BFSI | General
Nuvama Wealth and Investment Limited | 01/05/2026 | 268,824 | 239,774 | 29,050 | Other | General
Nuvama Wealth and Investment Limited | 01/06/2026 | 349,510 | 311,203 | 38,307 | Other | General
Nuvama Wealth and Investment Limited | 01/07/2026 | 311,452 | 277,549 | 33,903
NUVAMA WEALTH FINANCE LIMITED | 01/06/2026 | 449 | 338 | 111 | Media & Entertainment | General
NUVAMA WEALTH FINANCE LIMITED | 01/07/2026 | 964 | 725 | 239
NXTAS MOBILITY LLP | 01/04/2026 | 186 | 130 | 56 | Retail | General
NXTAS MOBILITY LLP | 01/05/2026 | 11 | 8 | 3 | Other | General
Octopolis Technologies Private Limited | 01/04/2026 | 25,622 | 21,687 | 3,935 | Other | General
Octopolis Technologies Private Limited | 01/05/2026 | 24,636 | 20,698 | 3,938 | Other | General
Octopolis Technologies Private Limited | 01/06/2026 | 81,145 | 71,301 | 9,844 | IT & Technology | General
Octopolis Technologies Private Limited | 01/07/2026 | 76,555 | 66,983 | 9,572
ODELUS PRIVATE LIMITED | 01/04/2026 | 3,526 | 3,238 | 288 | Other | General
ODELUS PRIVATE LIMITED | 01/05/2026 | 4,559 | 4,184 | 375 | Other | General
ODELUS PRIVATE LIMITED | 01/06/2026 | 4,031 | 3,686 | 345 | Other | General
ODELUS PRIVATE LIMITED | 01/07/2026 | 4,423 | 4,031 | 392
Only Retail Pvt. Ltd. | 01/04/2026 | 857 | 599 | 258 | Retail | General
Only Retail Pvt. Ltd. | 01/05/2026 | 842 | 588 | 254 | Other | General
Only Retail Pvt. Ltd. | 01/06/2026 | 1,526 | 1,066 | 460 | Other | General
Only Retail Pvt. Ltd. | 01/07/2026 | 1,714 | 1,197 | 517
OOGE INNOVATIONS PRIVATE LIMITED | 01/04/2026 | 100 | 82 | 18 | BFSI | General
OOGE INNOVATIONS PRIVATE LIMITED | 01/05/2026 | 220 | 195 | 25 | Other | General
OOGE INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 293 | 260 | 33 | BFSI | General
OOGE INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 2,432 | 2,314 | 118
P M SHAH AND CO JEWELLERS PRIVATE LIMITED | 01/04/2026 | 22 | 20 | 2 | Other | General
P M SHAH AND CO JEWELLERS PRIVATE LIMITED | 01/05/2026 | 13 | 10 | 3 | IT & Technology | General
P M SHAH AND CO JEWELLERS PRIVATE LIMITED | 01/06/2026 | 7 | 5 | 2 | Other | General
P M SHAH AND CO JEWELLERS PRIVATE LIMITED | 01/07/2026 | 10 | 9 | 1
PARINAAM FOUNDATION | 01/07/2026 | 1,103 | 1,107 | -4
Pathfinder Publishing Pvt. Ltd | 01/04/2026 | 1,717 | 1,597 | 120 | Other | General
Pathfinder Publishing Pvt. Ltd | 01/05/2026 | 1 | 1 | 0 | Media & Entertainment | General
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 22,260 | 20,705 | 1,555 | BFSI | Mutual Fund
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 6,815 | 6,339 | 476
Pavers England Ltd | 01/04/2026 | 98 | 68 | 30 | Other | General
Pavers England Ltd | 01/05/2026 | 114 | 80 | 34 | Other | General
Pavers England Ltd | 01/06/2026 | 87 | 61 | 26 | BFSI | Mutual Fund
Pavers England Ltd | 01/07/2026 | 103 | 72 | 31
PAYU PAYMENTS PRIVATE LIMITED | 01/04/2026 | 83,157 | 77,336 | 5,821 | IT & Technology | General
PAYU PAYMENTS PRIVATE LIMITED | 01/05/2026 | 89,543 | 83,283 | 6,260 | Other | General
PAYU PAYMENTS PRIVATE LIMITED | 01/06/2026 | 135,315 | 125,893 | 9,422 | IT & Technology | General
PAYU PAYMENTS PRIVATE LIMITED | 01/07/2026 | 101,933 | 94,798 | 7,135
Pepe Jeans India Ltd. | 01/04/2026 | 278,545 | 240,412 | 38,133 | Other | General
Pepe Jeans India Ltd. | 01/05/2026 | 8,443 | 7,287 | 1,156 | Ecommerce | General
PMMUE Eduservices Private Limited | 01/04/2026 | 1,731,052 | 1,315,123 | 415,929 | IT & Technology | General
PMMUE Eduservices Private Limited | 01/05/2026 | 3,144,025 | 2,379,803 | 764,222 | Other | General
PMMUE Eduservices Private Limited | 01/06/2026 | 2,478,214 | 2,476,743 | 1,471 | Other | General
PMMUE Eduservices Private Limited | 01/07/2026 | 1,222,948 | 929,309 | 293,639
POCHEMUCHKA KIDS PRIVATE LIMITED | 01/04/2026 | 0 | 0 | 0 | Other | General
POCHEMUCHKA KIDS PRIVATE LIMITED | 01/05/2026 | 0 | 0 | 0 | BFSI | General
POCHEMUCHKA KIDS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
POLY PIPES INDIA (P) LTD. | 01/04/2026 | 2,912 | 2,033 | 879 | Other | General
POLY PIPES INDIA (P) LTD. | 01/05/2026 | 3,104 | 2,167 | 937 | Other | General
POLY PIPES INDIA (P) LTD. | 01/06/2026 | 3,717 | 2,595 | 1,122 | Education | General
POLY PIPES INDIA (P) LTD. | 01/07/2026 | 4,145 | 2,894 | 1,251
POONAWALLA FINCORP LIMITED | 01/04/2026 | 10,161,038 | 9,444,667 | 716,371 | BFSI | General
POONAWALLA FINCORP LIMITED | 01/05/2026 | 10,695,787 | 9,921,402 | 774,385 | Media & Entertainment | General
POONAWALLA FINCORP LIMITED | 01/06/2026 | 10,324,282 | 9,601,956 | 722,326 | BFSI | General
POONAWALLA FINCORP LIMITED | 01/07/2026 | 14,007,555 | 13,027,031 | 980,524 | Other | General
POONAWALLA HOUSING FINANCE LIMITED | 01/04/2026 | 63,622 | 47,892 | 15,730 | Other | General
POONAWALLA HOUSING FINANCE LIMITED | 01/05/2026 | 30,145 | 21,191 | 8,954 | Education | General
POONAWALLA HOUSING FINANCE LIMITED | 01/06/2026 | 47,892 | 38,204 | 9,688 | BFSI | General
POONAWALLA HOUSING FINANCE LIMITED | 01/07/2026 | 65,715 | 49,737 | 15,978
Porch Technologies Private Limited | 01/04/2026 | 28,583 | 25,337 | 3,246 | Education | General
Porch Technologies Private Limited | 01/05/2026 | 26,194 | 23,181 | 3,013 | Other | General
Porch Technologies Private Limited | 01/06/2026 | 28,632 | 25,477 | 3,155 | Other | General
Porch Technologies Private Limited | 01/07/2026 | 23,325 | 20,788 | 2,537
PRESTIGE ESTATES PROJECTS LIMITED | 01/04/2026 | 85,769 | 77,355 | 8,414 | Other | General
PRESTIGE ESTATES PROJECTS LIMITED | 01/05/2026 | 240,902 | 217,267 | 23,635 | IT & Technology | General
PRESTIGE ESTATES PROJECTS LIMITED | 01/06/2026 | 278,010 | 252,406 | 25,604 | Travel & Aviation | General
PRESTIGE ESTATES PROJECTS LIMITED | 01/07/2026 | 400,715 | 361,333 | 39,382
PROSPERR.IO PRIVATE LIMITED | 01/04/2026 | 4,874 | 4,352 | 522 | Other | General
PROSPERR.IO PRIVATE LIMITED | 01/05/2026 | 20,379 | 18,475 | 1,904 | Other | General
PROSPERR.IO PRIVATE LIMITED | 01/06/2026 | 43,590 | 38,737 | 4,853 | BFSI | Life Insurance
PROSPERR.IO PRIVATE LIMITED | 01/07/2026 | 88,323 | 78,487 | 9,836
Public Clothing Private Limited | 01/04/2026 | 0 | 0 | 0 | BFSI | General
Public Clothing Private Limited | 01/05/2026 | 26,520 | 23,653 | 2,867 | Other | General
Public Clothing Private Limited | 01/06/2026 | 722 | 644 | 78 | Other | General
Public Clothing Private Limited | 01/07/2026 | 14,698 | 13,106 | 1,592
Puravankara Limited | 01/04/2026 | 1,402,345 | 1,304,806 | 97,539 | Agriculture & FMCG | General
Puravankara Limited | 01/05/2026 | 920,072 | 855,679 | 64,393 | Other | General
Puravankara Limited | 01/06/2026 | 911,854 | 848,025 | 63,829 | Media & Entertainment | General
Puravankara Limited | 01/07/2026 | 403,840 | 375,572 | 28,268
Pureplay Skin Sciences India Pvt Ltd | 01/04/2026 | 1,460,704 | 1,358,622 | 102,082 | Other | General
Pureplay Skin Sciences India Pvt Ltd | 01/05/2026 | 1,593,328 | 1,482,311 | 111,017 | Other | General
Pureplay Skin Sciences India Pvt Ltd | 01/06/2026 | 863,072 | 802,750 | 60,322 | Agriculture & FMCG | General
Pureplay Skin Sciences India Pvt Ltd | 01/07/2026 | 3,214,314 | 2,989,662 | 224,652 | BFSI | General
Quantum Asset Management Company Private Limited. | 01/04/2026 | 30,425 | 27,137 | 3,288 | IT & Technology | General
Quantum Asset Management Company Private Limited. | 01/05/2026 | 8,613 | 7,723 | 890 | BFSI | General
Quantum Asset Management Company Private Limited. | 01/06/2026 | 22,127 | 19,734 | 2,393 | BFSI | Mutual Fund
Quantum Asset Management Company Private Limited. | 01/07/2026 | 11,204 | 9,993 | 1,211
Rekhta Foundation | 01/04/2026 | 16 | 14 | 2 | IT & Technology | General
Rekhta Foundation | 01/06/2026 | 3,258 | 2,906 | 352 | Other | General
Rekhta Foundation | 01/07/2026 | 1,490 | 1,328 | 162
Relaxo Footwears Ltd. | 01/04/2026 | 257,967 | 222,180 | 35,787 | Other | General
Relaxo Footwears Ltd. | 01/05/2026 | 84,319 | 79,832 | 4,487 | IT & Technology | General
Relaxo Footwears Ltd. | 01/06/2026 | 77,737 | 73,573 | 4,164 | IT & Technology | General
Relaxo Footwears Ltd. | 01/07/2026 | 191,385 | 182,588 | 8,797
Reliance General Insurance Co. Ltd | 01/04/2026 | 596,926 | 536,710 | 60,216 | BFSI | Housing Finance
Reliance General Insurance Co. Ltd | 01/05/2026 | 1,081,988 | 962,615 | 119,373 | Other | General
Reliance General Insurance Co. Ltd | 01/06/2026 | 1,015,362 | 901,109 | 114,253 | Other | General
Reliance General Insurance Co. Ltd | 01/07/2026 | 1,419,736 | 1,265,320 | 154,416
Reserve Bank of India | 01/06/2026 | 49,738,991 | 42,278,142 | 7,460,849 | Other | General
Reserve Bank of India | 01/07/2026 | 50,000,000 | 42,500,047 | 7,499,953 | BFSI | General
RITNAND BALVED EDUCATION FOUNDATION NOIDA | 01/04/2026 | 9,279 | 8,009 | 1,270 | Healthcare | General
RITNAND BALVED EDUCATION FOUNDATION NOIDA | 01/05/2026 | 15,064 | 13,002 | 2,062 | Real Estate | Property Portal
RITNAND BALVED EDUCATION FOUNDATION NOIDA | 01/06/2026 | 1,832 | 1,581 | 251 | Other | General
RITNAND BALVED EDUCATION FOUNDATION NOIDA | 01/07/2026 | 1,767 | 1,525 | 242
Riya Travel & Tours (I) Pvt. Ltd. | 01/04/2026 | 247 | 220 | 27 | Other | General
Riya Travel & Tours (I) Pvt. Ltd. | 01/05/2026 | 262 | 234 | 28 | BFSI | General
Riya Travel & Tours (I) Pvt. Ltd. | 01/06/2026 | 70 | 63 | 7 | Other | General
RJ CORP LTD | 01/04/2026 | 50,568 | 43,645 | 6,923 | Other | General
RJ CORP LTD | 01/05/2026 | 15,670 | 13,525 | 2,145 | Media & Entertainment | General
RJ CORP LTD | 01/06/2026 | 65,139 | 57,811 | 7,328 | Other | General
RJ CORP LTD | 01/07/2026 | 7,911 | 7,056 | 855
ROSSO BRUNELLO LEATHERS PRIVATE LIMITED | 01/04/2026 | 2,944 | 2,823 | 121 | Other | General
ROSSO BRUNELLO LEATHERS PRIVATE LIMITED | 01/05/2026 | 14,194 | 13,612 | 582 | Other | General
ROSSO BRUNELLO LEATHERS PRIVATE LIMITED | 01/06/2026 | 31,243 | 29,962 | 1,281 | IT & Technology | General
ROSSO BRUNELLO LEATHERS PRIVATE LIMITED | 01/07/2026 | 54,862 | 52,613 | 2,249
Savaari Car Rentals Pvt Ltd | 01/04/2026 | 218,640 | 202,447 | 16,193 | Healthcare | General
Savaari Car Rentals Pvt Ltd | 01/05/2026 | 133,883 | 123,638 | 10,245 | Other | General
Savaari Car Rentals Pvt Ltd | 01/06/2026 | 165,271 | 153,497 | 11,774 | IT & Technology | General
Savaari Car Rentals Pvt Ltd | 01/07/2026 | 133,542 | 123,183 | 10,359
Savesage Solutions Private Limited | 01/04/2026 | 139,426 | 106,222 | 33,204 | Other | General
Savesage Solutions Private Limited | 01/05/2026 | 362,142 | 317,864 | 44,278 | Agriculture & FMCG | General
Savesage Solutions Private Limited | 01/06/2026 | 320,038 | 290,213 | 29,825 | Other | General
Savesage Solutions Private Limited | 01/07/2026 | 255,619 | 222,224 | 33,395
Selfanimate Private Limited | 01/04/2026 | 365 | 255 | 110 | IT & Technology | General
Selfanimate Private Limited | 01/05/2026 | 164 | 115 | 49 | BFSI | General
Selfanimate Private Limited | 01/06/2026 | 166 | 116 | 50 | BFSI | General
Selfanimate Private Limited | 01/07/2026 | 105 | 73 | 32
Senco Gold Limited | 01/04/2026 | 584,748 | 543,817 | 40,931 | BFSI | Housing Finance
Senco Gold Limited | 01/05/2026 | 68,687 | 63,885 | 4,802 | Other | General
Senco Gold Limited | 01/06/2026 | 174,407 | 162,198 | 12,209 | Other | General
Senco Gold Limited | 01/07/2026 | 532,260 | 495,002 | 37,258
Sewells Group India Private Limited | 01/06/2026 | 63,420 | 57,848 | 5,572 | Other | General
Sewells Group India Private Limited | 01/07/2026 | 102,945 | 93,900 | 9,045
Shadowfax Technologies Private Limited | 01/04/2026 | 1,301,928 | 1,253,804 | 48,124 | Other | General
Shadowfax Technologies Private Limited | 01/05/2026 | 2,799,122 | 2,696,225 | 102,897 | BFSI | Life Insurance
Shadowfax Technologies Private Limited | 01/06/2026 | 2,850,033 | 2,751,246 | 98,787 | Healthcare | General
Shadowfax Technologies Private Limited | 01/07/2026 | 2,784,676 | 2,694,926 | 89,750 | Healthcare | General
SHARDA EDUCATIONAL TRUST | 01/04/2026 | 148,297 | 142,216 | 6,081 | BFSI | General
SHARDA EDUCATIONAL TRUST | 01/05/2026 | 42,871 | 41,113 | 1,758 | Education | General
SHARDA EDUCATIONAL TRUST | 01/06/2026 | 78,073 | 74,872 | 3,201 | Other | General
SHARDA EDUCATIONAL TRUST | 01/07/2026 | 249,704 | 237,647 | 12,057
Sharekhan Ltd | 01/06/2026 | 74,997 | 66,888 | 8,109 | Retail | General
Sharekhan Ltd | 01/07/2026 | 14,519 | 12,949 | 1,570
Shemaroo Entertainment Ltd. | 01/04/2026 | 407,372 | 370,725 | 36,647 | BFSI | General
Shemaroo Entertainment Ltd. | 01/05/2026 | 570,461 | 519,871 | 50,590 | BFSI | Life Insurance
Shemaroo Entertainment Ltd. | 01/06/2026 | 716,417 | 655,790 | 60,627 | BFSI | General
Shemaroo Entertainment Ltd. | 01/07/2026 | 913,951 | 837,356 | 76,595
Shiamak Davars Institute For Performing Arts Private Limited | 01/04/2026 | 7 | 6 | 1 | Other | General
Shiamak Davars Institute For Performing Arts Private Limited | 01/07/2026 | 376 | 336 | 40
Shoppers Stop Ltd | 01/04/2026 | 35,312 | 29,021 | 6,291 | BFSI | General
Shoppers Stop Ltd | 01/05/2026 | 34,472 | 27,772 | 6,700 | Other | General
Shoppers Stop Ltd | 01/06/2026 | 30,897 | 24,000 | 6,897 | IT & Technology | General
Shoppers Stop Ltd | 01/07/2026 | 30,035 | 23,209 | 6,826
Shriram Asset Management Company Limited | 01/04/2026 | 15,643 | 12,462 | 3,181 | Other | General
Shriram Asset Management Company Limited | 01/05/2026 | 12,235 | 9,636 | 2,599 | BFSI | General
Shriram Asset Management Company Limited | 01/06/2026 | 21,371 | 16,827 | 4,544 | Other | General
Shriram Asset Management Company Limited | 01/07/2026 | 18,810 | 14,820 | 3,990
Shriram General Insurance Company Ltd | 01/04/2026 | 132,212 | 111,640 | 20,572 | Other | General
Shriram General Insurance Company Ltd | 01/05/2026 | 122,571 | 102,159 | 20,412 | IT & Technology | General
Shriram General Insurance Company Ltd | 01/06/2026 | 126,819 | 105,241 | 21,578 | BFSI | General
Shriram General Insurance Company Ltd | 01/07/2026 | 143,574 | 120,504 | 23,070
Shriram Life Insurance Company Limited | 01/04/2026 | 330,982 | 295,196 | 35,786 | Other | General
Shriram Life Insurance Company Limited | 01/05/2026 | 289,985 | 258,645 | 31,340 | BFSI | General
Shriram Life Insurance Company Limited | 01/06/2026 | 88,319 | 78,769 | 9,550 | Other | General
Shriram Life Insurance Company Limited | 01/07/2026 | 48,298 | 43,075 | 5,223
Shriram Transport Finance Company Ltd | 01/04/2026 | 642,332 | 597,382 | 44,950 | BFSI | Life Insurance
Shriram Transport Finance Company Ltd | 01/05/2026 | 569,927 | 534,182 | 35,745 | BFSI | Life Insurance
Shriram Transport Finance Company Ltd | 01/06/2026 | 651,622 | 611,320 | 40,302 | Other | General
Shriram Transport Finance Company Ltd | 01/07/2026 | 751,628 | 701,657 | 49,971
SMARTCONNECT TECHNOLOGIES PVT LTD | 01/04/2026 | 383 | 250 | 133 | Other | General
SMARTCONNECT TECHNOLOGIES PVT LTD | 01/05/2026 | 971 | 633 | 338 | Other | General
SMARTCONNECT TECHNOLOGIES PVT LTD | 01/06/2026 | 1,179 | 769 | 410 | IT & Technology | General
SMARTCONNECT TECHNOLOGIES PVT LTD | 01/07/2026 | 1,569 | 1,023 | 546
SMC Global Securities Ltd. | 01/04/2026 | 16,867 | 14,794 | 2,073 | Other | General
SMC Global Securities Ltd. | 01/05/2026 | 18,176 | 15,195 | 2,981 | BFSI | Mutual Fund
SMC Global Securities Ltd. | 01/06/2026 | 13,177 | 10,395 | 2,782 | Other | General
SMC Global Securities Ltd. | 01/07/2026 | 10,144 | 7,652 | 2,492
Sorting Hat Technologies Pvt. Ltd. | 01/04/2026 | 3,401,216 | 3,287,185 | 114,031 | IT & Technology | General
Sorting Hat Technologies Pvt. Ltd. | 01/05/2026 | 3,166,616 | 3,063,907 | 102,709 | BFSI | General
Sorting Hat Technologies Pvt. Ltd. | 01/06/2026 | 2,587,636 | 2,499,682 | 87,954 | BFSI | General
Sorting Hat Technologies Pvt. Ltd. | 01/07/2026 | 2,602,131 | 2,516,753 | 85,378 | Other | General
SOTC Travel Limited | 01/04/2026 | 3,375 | 2,950 | 425 | Other | General
SOTC Travel Limited | 01/05/2026 | 4,719 | 4,151 | 568 | Other | General
SOTC Travel Limited | 01/06/2026 | 3,345 | 2,932 | 413 | BFSI | General
SOTC Travel Limited | 01/07/2026 | 2,066 | 1,794 | 272
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/04/2026 | 3 | 3 | 0 | BFSI | NBFC
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/05/2026 | 6 | 6 | 0 | Healthcare | General
SPICE MONEY LIMITED | 01/04/2026 | 186,157 | 166,028 | 20,129 | Healthcare | General
SPICE MONEY LIMITED | 01/05/2026 | 149,967 | 133,760 | 16,207 | IT & Technology | General
SPICE MONEY LIMITED | 01/06/2026 | 172,230 | 153,607 | 18,623 | Other | General
SPICE MONEY LIMITED | 01/07/2026 | 373,074 | 332,734 | 40,340
Sri Sri Publications and Media Pvt Ltd | 01/05/2026 | 253,185 | 228,838 | 24,347 | BFSI | General
Sri Sri Publications and Media Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Sriyah Insurance Brokers Pvt. Ltd. | 01/04/2026 | 79,138 | 68,268 | 10,870 | IT & Technology | General
Sriyah Insurance Brokers Pvt. Ltd. | 01/05/2026 | 1,960 | 1,651 | 309 | Retail | General
Sriyah Insurance Brokers Pvt. Ltd. | 01/06/2026 | 2,250 | 1,901 | 349 | Retail | General
Sriyah Insurance Brokers Pvt. Ltd. | 01/07/2026 | 2,306 | 1,936 | 370
Sterling Holiday Resorts Ltd. | 01/04/2026 | 42,514 | 42,436 | 78 | Other | General
Sterling Holiday Resorts Ltd. | 01/05/2026 | 94,914 | 94,799 | 115 | BFSI | Payments Bank
Sterling Holiday Resorts Ltd. | 01/06/2026 | 58,694 | 58,615 | 79 | Other | General
Sterling Holiday Resorts Ltd. | 01/07/2026 | 157,614 | 157,605 | 9
STEW INDIA AD INNOVATIONS | 01/04/2026 | 222,204 | 195,950 | 26,254 | Other | General
STEW INDIA AD INNOVATIONS | 01/05/2026 | 88,597 | 76,706 | 11,891 | IT & Technology | General
STEW INDIA AD INNOVATIONS | 01/06/2026 | 76,742 | 66,922 | 9,820 | IT & Technology | General
STEW INDIA AD INNOVATIONS | 01/07/2026 | 115,739 | 99,894 | 15,845
SUCCESS GYAN INDIA LLP | 01/05/2026 | 8,204 | 7,025 | 1,179 | Other | General
SUCCESS GYAN INDIA LLP | 01/06/2026 | 12,021 | 9,836 | 2,185 | BFSI | General
Sundaram Asset Management Company Limited | 01/04/2026 | 36,381 | 32,448 | 3,933 | BFSI | General
Sundaram Asset Management Company Limited | 01/05/2026 | 86,917 | 77,531 | 9,386 | Agriculture & FMCG | General
Sundaram Asset Management Company Limited | 01/06/2026 | 66,017 | 58,879 | 7,138 | Agriculture & FMCG | General
Sundaram Asset Management Company Limited | 01/07/2026 | 92,611 | 82,597 | 10,014
Sunshine Teahouse Private Limited | 01/04/2026 | 59,474 | 55,311 | 4,163 | Retail | General
Sunshine Teahouse Private Limited | 01/05/2026 | 56,275 | 52,336 | 3,939 | Manufacturing | General
Sunshine Teahouse Private Limited | 01/06/2026 | 48,035 | 44,673 | 3,362 | Manufacturing | General
Sunshine Teahouse Private Limited | 01/07/2026 | 41,328 | 38,435 | 2,893
SYNGENE INTERNATIONAL LIMITED | 01/04/2026 | 9,688 | 9,283 | 405 | BFSI | General
SYNGENE INTERNATIONAL LIMITED | 01/05/2026 | 797 | 557 | 240 | IT & Technology | General
SYNGENE INTERNATIONAL LIMITED | 01/06/2026 | 13,054 | 12,105 | 949 | BFSI | General
SYNGENE INTERNATIONAL LIMITED | 01/07/2026 | 17,459 | 16,733 | 726
T.V. TODAY NETWORK LIMITED | 01/04/2026 | 637,051 | 498,650 | 138,401 | Retail | General
T.V. TODAY NETWORK LIMITED | 01/05/2026 | 452,123 | 359,511 | 92,612 | BFSI | Housing Finance
T.V. TODAY NETWORK LIMITED | 01/06/2026 | 304,756 | 242,366 | 62,390 | IT & Technology | General
T.V. TODAY NETWORK LIMITED | 01/07/2026 | 245,359 | 195,448 | 49,911
Tally Education Pvt Ltd | 01/04/2026 | 16,228 | 14,005 | 2,223 | BFSI | General
Tally Education Pvt Ltd | 01/05/2026 | 9,011 | 7,777 | 1,234 | Other | General
Tally Education Pvt Ltd | 01/06/2026 | 11,062 | 9,547 | 1,515 | Other | General
Tally Education Pvt Ltd | 01/07/2026 | 15,372 | 13,267 | 2,105
Tally Solutions Pvt. Ltd. | 01/04/2026 | 137,801 | 122,902 | 14,899 | Other | General
Tally Solutions Pvt. Ltd. | 01/05/2026 | 21,740 | 19,390 | 2,350 | Other | General
Tally Solutions Pvt. Ltd. | 01/06/2026 | 55,916 | 49,870 | 6,046 | Other | General
Tally Solutions Pvt. Ltd. | 01/07/2026 | 26,195 | 23,363 | 2,832
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/04/2026 | 3,480 | 3,237 | 243 | Education | General
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/05/2026 | 314,207 | 292,216 | 21,991 | BFSI | Fintech
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 22,580 | 20,999 | 1,581 | Other | General
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 330,968 | 307,800 | 23,168
TECH7 PHYLL PRIVATE LIMITED | 01/04/2026 | 6 | 6 | 0 | IT & Technology | General
Techmash Solution Pvt. Ltd.- Playo | 01/04/2026 | 386 | 344 | 42 | Other | General
Techmash Solution Pvt. Ltd.- Playo | 01/05/2026 | 849 | 757 | 92 | Other | General
Techmash Solution Pvt. Ltd.- Playo | 01/06/2026 | 257 | 229 | 28 | IT & Technology | General
TESTBOOK EDU SOLUTIONS PRIVATE LIMITED | 01/04/2026 | 213,577 | 219,712 | -6,135 | IT & Technology | General
TESTBOOK EDU SOLUTIONS PRIVATE LIMITED | 01/05/2026 | 464 | 477 | -13 | BFSI | General
Texzone Information Services Pvt.Ltd. | 01/04/2026 | 13 | 12 | 1 | Education | General
Texzone Information Services Pvt.Ltd. | 01/05/2026 | 2 | 2 | 0 | Other | General
Texzone Information Services Pvt.Ltd. | 01/06/2026 | 1,861 | 1,299 | 562 | Education | General
Texzone Information Services Pvt.Ltd. | 01/07/2026 | 1,780 | 1,243 | 537
THE ANDHRA PRADESH STATE CO-OPERATIVE BANK LTD | 01/04/2026 | 11 | 9 | 2 | Other | General
THE ANDHRA PRADESH STATE CO-OPERATIVE BANK LTD | 01/05/2026 | 4 | 3 | 1 | Other | General
THE ANDHRA PRADESH STATE CO-OPERATIVE BANK LTD | 01/07/2026 | 1 | 1 | 0
The Calcutta Medical Research Institute | 01/04/2026 | 136,768 | 121,964 | 14,804 | BFSI | Small Finance Bank
The Calcutta Medical Research Institute | 01/05/2026 | 166,779 | 148,725 | 18,054 | IT & Technology | General
The Calcutta Medical Research Institute | 01/06/2026 | 134,167 | 119,640 | 14,527 | IT & Technology | General
The Calcutta Medical Research Institute | 01/07/2026 | 142,199 | 126,803 | 15,396
The Indian Hotels Company Limited | 01/04/2026 | 361,771 | 336,469 | 25,302 | Other | General
The Indian Hotels Company Limited | 01/05/2026 | 149,069 | 138,634 | 10,435 | Healthcare | General
The Indian Hotels Company Limited | 01/06/2026 | 153,321 | 142,594 | 10,727 | Other | General
The Indian Hotels Company Limited | 01/07/2026 | 530,927 | 493,752 | 37,175
The Souled Store Pvt. Ltd. | 01/04/2026 | 2,572,209 | 2,392,191 | 180,018 | Healthcare | General
The Souled Store Pvt. Ltd. | 01/05/2026 | 2,568,227 | 2,388,634 | 179,593 | IT & Technology | General
The Souled Store Pvt. Ltd. | 01/06/2026 | 2,337,845 | 2,174,516 | 163,329 | Other | General
The Souled Store Pvt. Ltd. | 01/07/2026 | 2,555,148 | 2,376,385 | 178,763 | Other | General
Thomas Cook (India) Ltd | 01/04/2026 | 13,967 | 11,764 | 2,203 | BFSI | Mutual Fund
Thomas Cook (India) Ltd | 01/05/2026 | 13,133 | 11,233 | 1,900 | BFSI | General
Thomas Cook (India) Ltd | 01/06/2026 | 11,135 | 9,339 | 1,796 | Other | General
Thomas Cook (India) Ltd | 01/07/2026 | 10,504 | 8,648 | 1,856
Torus Digital Pvt Ltd | 01/04/2026 | 492 | 413 | 79 | IT & Technology | General
Torus Digital Pvt Ltd | 01/05/2026 | 473 | 398 | 75 | BFSI | General
Torus Digital Pvt Ltd | 01/06/2026 | 382 | 321 | 61 | BFSI | General
Torus Digital Pvt Ltd | 01/07/2026 | 381 | 321 | 60
Trawellhr Services Pvt Ltd. | 01/05/2026 | 614 | 530 | 84 | Media & Entertainment | General
TRYLO INTIMATES | 01/04/2026 | 27,085 | 23,860 | 3,225 | Education | General
TRYLO INTIMATES | 01/05/2026 | 23,409 | 20,640 | 2,769 | BFSI | General
TRYLO INTIMATES | 01/06/2026 | 23,970 | 21,144 | 2,826 | Other | General
TRYLO INTIMATES | 01/07/2026 | 26,253 | 23,132 | 3,121
TVS Credit Services Ltd. | 01/04/2026 | 7,757,871 | 7,116,548 | 641,323 | Other | General
TVS Credit Services Ltd. | 01/05/2026 | 8,140,279 | 7,447,189 | 693,090 | Other | General
TVS Credit Services Ltd. | 01/06/2026 | 8,043,403 | 7,378,476 | 664,927 | Other | General
TVS Credit Services Ltd. | 01/07/2026 | 8,794,686 | 8,179,020 | 615,666 | Retail | General
Ujjivan Small Finance Bank Limited | 01/04/2026 | 1,986,834 | 1,743,175 | 243,659 | Other | General
Ujjivan Small Finance Bank Limited | 01/05/2026 | 1,785,414 | 1,592,690 | 192,724 | Other | General
Ujjivan Small Finance Bank Limited | 01/06/2026 | 1,946,139 | 1,734,828 | 211,311 | Healthcare | General
Ujjivan Small Finance Bank Limited | 01/07/2026 | 2,595,396 | 2,313,379 | 282,017 | Healthcare | General
Ultimedia E-Solutions Pvt. Ltd | 01/05/2026 | 0 | 0 | 0 | IT & Technology | General
Union Asset Management Company Private Limited | 01/05/2026 | 76,304 | 70,963 | 5,341 | Other | General
Union Asset Management Company Private Limited | 01/06/2026 | 3,577 | 3,326 | 251 | Other | General
Union Asset Management Company Private Limited | 01/07/2026 | 2,363 | 2,198 | 165
UNITED DISTRIBUTORS INC | 01/04/2026 | 7,333 | 7,033 | 300 | Other | General
UNITED DISTRIBUTORS INC | 01/05/2026 | 3,913 | 3,753 | 160 | Other | General
UNITED DISTRIBUTORS INC | 01/06/2026 | 7,197 | 6,902 | 295 | Other | General
UNITED DISTRIBUTORS INC | 01/07/2026 | 19,748 | 18,938 | 810
Universal Sportsbiz Private Limited | 01/05/2026 | 89,559 | 83,306 | 6,253 | IT & Technology | General
Universal Sportsbiz Private Limited | 01/06/2026 | 54,402 | 50,594 | 3,808 | BFSI | General
Universal Sportsbiz Private Limited | 01/07/2026 | 41,411 | 38,512 | 2,899
Usha Kiran Movies Pvt. Ltd. | 01/04/2026 | 4,303 | 4,126 | 177 | Other | General
Usha Kiran Movies Pvt. Ltd. | 01/05/2026 | 6,226 | 5,971 | 255 | Other | General
Usha Kiran Movies Pvt. Ltd. | 01/06/2026 | 10,633 | 10,197 | 436 | IT & Technology | General
Usha Kiran Movies Pvt. Ltd. | 01/07/2026 | 6 | 6 | 0
VERO MODA RETAIL PRIVATE LIMITED | 01/04/2026 | 509 | 355 | 154 | Other | General
VERO MODA RETAIL PRIVATE LIMITED | 01/05/2026 | 477 | 333 | 144 | BFSI | General
VERO MODA RETAIL PRIVATE LIMITED | 01/06/2026 | 584 | 408 | 176 | BFSI | Broking & Financial Services
VERO MODA RETAIL PRIVATE LIMITED | 01/07/2026 | 941 | 657 | 284
VOLTAS LIMITED | 01/06/2026 | 9,703 | 9,004 | 699 | Other | General
VOLTAS LIMITED | 01/07/2026 | 215,715 | 200,175 | 15,540
Wavicle Technologies Pvt Ltd | 01/04/2026 | 1,012,391 | 939,838 | 72,553 | IT & Technology | General
Wavicle Technologies Pvt Ltd | 01/05/2026 | 2,167,071 | 2,005,028 | 162,043 | Healthcare | General
Wavicle Technologies Pvt Ltd | 01/06/2026 | 1,633,498 | 1,521,330 | 112,168 | Other | General
Wavicle Technologies Pvt Ltd | 01/07/2026 | 2,128,075 | 1,954,242 | 173,833
WEBLINK IN PRIVATE LIMITED | 01/04/2026 | 8,948 | 7,973 | 975 | Other | General
WEBLINK IN PRIVATE LIMITED | 01/05/2026 | 6,650 | 5,926 | 724 | Other | General
WEBLINK IN PRIVATE LIMITED | 01/06/2026 | 9,284 | 8,280 | 1,004 | Ecommerce | General
WEBLINK IN PRIVATE LIMITED | 01/07/2026 | 16,223 | 14,468 | 1,755
West Bengal Electronics Industry Development Cor | 01/04/2026 | 9 | 7 | 2 | Travel & Aviation | General
West Bengal Electronics Industry Development Cor | 01/05/2026 | 0 | 0 | 0 | Other | General
West Bengal Electronics Industry Development Cor | 01/06/2026 | 12,091 | 9,459 | 2,632 | Education | General
West Bengal Electronics Industry Development Cor | 01/07/2026 | 86 | 67 | 19
WHITEOAK CAPITAL ASSET MANAGEMENT LIMITED | 01/04/2026 | 6,180 | 5,504 | 676 | Other | General
WHITEOAK CAPITAL ASSET MANAGEMENT LIMITED | 01/05/2026 | 5,421 | 4,826 | 595 | Other | General
WHITEOAK CAPITAL ASSET MANAGEMENT LIMITED | 01/06/2026 | 5,343 | 4,755 | 588 | BFSI | General
WHITEOAK CAPITAL ASSET MANAGEMENT LIMITED | 01/07/2026 | 5,768 | 5,124 | 644
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/04/2026 | 14,330 | 13,284 | 1,046 | BFSI | Mutual Fund
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/05/2026 | 27,046 | 25,065 | 1,981 | IT & Technology | General
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/06/2026 | 65,015 | 60,056 | 4,959 | Other | General
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/07/2026 | 10,932 | 9,988 | 944
WSFX GLOBAL PAY LIMITED | 01/04/2026 | 10,805 | 9,636 | 1,169 | Real Estate | Property Portal
WSFX GLOBAL PAY LIMITED | 01/05/2026 | 61,102 | 54,569 | 6,533 | Other | General
WSFX GLOBAL PAY LIMITED | 01/06/2026 | 17,058 | 14,991 | 2,067 | Real Estate | Property Portal
WSFX GLOBAL PAY LIMITED | 01/07/2026 | 11,708 | 10,442 | 1,266
YASHODA HEALTHCARE SERVICE PVT. LTD. | 01/04/2026 | 303,192 | 267,924 | 35,268 | BFSI | General
YASHODA HEALTHCARE SERVICE PVT. LTD. | 01/05/2026 | 324,219 | 285,613 | 38,606 | Other | General
YASHODA HEALTHCARE SERVICE PVT. LTD. | 01/06/2026 | 263,442 | 230,341 | 33,101 | Other | General
YASHODA HEALTHCARE SERVICE PVT. LTD. | 01/07/2026 | 324,606 | 284,355 | 40,251
Zee Entertainment Enterprises Limited | 01/04/2026 | 1,013 | 970 | 43 | BFSI | General
Zee Entertainment Enterprises Limited | 01/05/2026 | 5 | 5 | 0 | Travel & Aviation | General
Zee Entertainment Enterprises Limited | 01/07/2026 | 125,271 | 120,135 | 5,136
ZION COLLECTIVE PRIVATE LIMITED | 01/07/2026 | 190 | 167 | 23
ZUQO Corporation India Private Limited | 01/04/2026 | 688 | 607 | 81 | Travel & Aviation | General
ZUQO Corporation India Private Limited | 01/05/2026 | 469 | 381 | 88 | BFSI | General
ZUQO Corporation India Private Limited | 01/06/2026 | 355 | 283 | 72 | BFSI | General
ZUQO Corporation India Private Limited | 01/07/2026 | 924 | 748 | 176
Zydus Wellness Products Limited | 01/04/2026 | 15 | 12 | 3 | Healthcare | General
Zydus Wellness Products Limited | 01/05/2026 | 7 | 6 | 1 | BFSI | General

## RCS_Consumables
Client | Month | Revenue | Cost | Margin | Industry | Sub Industry
Actoserba Active Wholesale Pvt Ltd | 01/05/2026 | 72,636 | 22,699 | 49,937
Actoserba Active Wholesale Pvt Ltd | 01/05/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/06/2026 | 78,976 | 24,680 | 54,296
Actoserba Active Wholesale Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/07/2026 | 49,716 | 15,536 | 34,180
Actoserba Active Wholesale Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Actoserba Active Wholesale Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Capital Digital Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/06/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/06/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/06/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/06/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/07/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/07/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/07/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/07/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/08/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/08/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/08/2026 | 0 | 0 | 0
Aditya Birla Finance Limited | 01/08/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Health Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/06/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/06/2026 | 39,482 | 14,806 | 24,676
Aditya Birla Sun Life AMC Limited | 01/06/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/06/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/07/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/07/2026 | 2,463 | 924 | 1,539
Aditya Birla Sun Life AMC Limited | 01/07/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/07/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/08/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/08/2026 | 9,923 | 3,721 | 6,202
Aditya Birla Sun Life AMC Limited | 01/08/2026 | 0 | 0 | 0
Aditya Birla Sun Life AMC Limited | 01/08/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/05/2026 | 29 | 18 | 11
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 3,544 | 2,215 | 1,329
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 6,693 | 4,183 | 2,510
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 10,132 | 6,333 | 3,799
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/04/2026 | 3,070 | 2,093 | 977
Agione Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/06/2026 | 1,217 | 830 | 387
Agione Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/07/2026 | 1,287 | 878 | 409
Agione Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Agione Technologies Private Limited | 01/08/2026 | 2,160 | 1,473 | 687
Agione Technologies Private Limited | 01/08/2026 | 4 | 2 | 2
Agione Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/04/2026 | 2,719 | 1,457 | 1,262
AIR INDIA EXPRESS LIMITED | 01/06/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/06/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/06/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/06/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/07/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/07/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/07/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/07/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/08/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/08/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/08/2026 | 0 | 0 | 0
AIR INDIA EXPRESS LIMITED | 01/08/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/05/2026 | 1,195 | 598 | 597
Amnex for Karamyogi Bharat | 01/06/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/06/2026 | 2,793 | 1,396 | 1,397
Amnex for Karamyogi Bharat | 01/06/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/06/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/07/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/07/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/07/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/07/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/08/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/08/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/08/2026 | 0 | 0 | 0
Amnex for Karamyogi Bharat | 01/08/2026 | 0 | 0 | 0
Amrutam Pharmaceuticals Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Amrutam Pharmaceuticals Pvt Ltd | 01/07/2026 | 2,805 | 1,627 | 1,178
Amrutam Pharmaceuticals Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Amrutam Pharmaceuticals Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Amrutam Pharmaceuticals Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Amrutam Pharmaceuticals Pvt Ltd | 01/08/2026 | 5,511 | 2,553 | 2,958
Amrutam Pharmaceuticals Pvt Ltd | 01/08/2026 | 6 | 2 | 4
Amrutam Pharmaceuticals Pvt Ltd | 01/08/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/06/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/06/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/06/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/06/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/07/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/07/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/07/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/07/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/08/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/08/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/08/2026 | 0 | 0 | 0
ANGEL ONE LIMITED | 01/08/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/06/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/06/2026 | 319,595 | 252,312 | 67,283
ANI TECHNOLOGIES PVT. LTD. | 01/06/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/06/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/07/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/07/2026 | 1,246,837 | 984,345 | 262,492
ANI TECHNOLOGIES PVT. LTD. | 01/07/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/07/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/08/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/08/2026 | 1,330,810 | 1,050,640 | 280,170
ANI TECHNOLOGIES PVT. LTD. | 01/08/2026 | 0 | 0 | 0
ANI TECHNOLOGIES PVT. LTD. | 01/08/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/04/2026 | 1,415 | 885 | 530
Antara Assisted Care Services Limited | 01/04/2026 | 1,476 | 923 | 553
Antara Assisted Care Services Limited | 01/05/2026 | 966 | 604 | 362
Antara Assisted Care Services Limited | 01/05/2026 | 7,312 | 4,570 | 2,742
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/06/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/07/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/07/2026 | 8,742 | 5,464 | 3,278
Antara Assisted Care Services Limited | 01/07/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/07/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/07/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/07/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/07/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/07/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/08/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/08/2026 | 43 | 27 | 16
Antara Assisted Care Services Limited | 01/08/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/08/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/08/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/08/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/08/2026 | 0 | 0 | 0
Antara Assisted Care Services Limited | 01/08/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/04/2026 | 23,432 | 15,395 | 8,037
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/05/2026 | 31,376 | 20,360 | 11,016
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 56,616 | 36,135 | 20,481
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 27,937 | 18,211 | 9,726
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 22,396 | 14,828 | 7,568
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
ANVESHAN FARM TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/05/2026 | 2 | 1 | 1
Apollo Hospitals Enterprise Ltd | 01/06/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/06/2026 | 104 | 36 | 68
Apollo Hospitals Enterprise Ltd | 01/06/2026 | 2 | 1 | 1
Apollo Hospitals Enterprise Ltd | 01/06/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/07/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/07/2026 | 151 | 51 | 100
Apollo Hospitals Enterprise Ltd | 01/07/2026 | 4 | 2 | 2
Apollo Hospitals Enterprise Ltd | 01/07/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/08/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/08/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/08/2026 | 0 | 0 | 0
Apollo Hospitals Enterprise Ltd | 01/08/2026 | 12 | 10 | 2
APPFLIX STUDIO LLP | 01/06/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/06/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/06/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/06/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/07/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/07/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/07/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/07/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/08/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/08/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/08/2026 | 0 | 0 | 0
APPFLIX STUDIO LLP | 01/08/2026 | 0 | 0 | 0
Aristobrat Retail Private Limited | 01/08/2026 | 0 | 0 | 0
Aristobrat Retail Private Limited | 01/08/2026 | 3,574 | 2,649 | 925
Aristobrat Retail Private Limited | 01/08/2026 | 0 | 0 | 0
Aristobrat Retail Private Limited | 01/08/2026 | 0 | 0 | 0
Asian Paints Limited | 01/04/2026 | 145 | 49 | 96
Asian Paints Limited | 01/04/2026 | 2 | 2 | 0
Asian Paints Limited | 01/05/2026 | 125 | 43 | 82
Asian Paints Limited | 01/05/2026 | 1 | 1 | 0
Asian Paints Limited | 01/06/2026 | 0 | 0 | 0
Asian Paints Limited | 01/06/2026 | 0 | 0 | 0
Asian Paints Limited | 01/06/2026 | 0 | 0 | 0
Asian Paints Limited | 01/06/2026 | 0 | 0 | 0
Asian Paints Limited | 01/06/2026 | 0 | 0 | 0
Asian Paints Limited | 01/06/2026 | 12,136 | 4,137 | 7,999
Asian Paints Limited | 01/06/2026 | 0 | 0 | 0
Asian Paints Limited | 01/06/2026 | 0 | 0 | 0
Asian Paints Limited | 01/07/2026 | 0 | 0 | 0
Asian Paints Limited | 01/07/2026 | 0 | 0 | 0
Asian Paints Limited | 01/07/2026 | 0 | 0 | 0
Asian Paints Limited | 01/07/2026 | 0 | 0 | 0
Asian Paints Limited | 01/07/2026 | 0 | 0 | 0
Asian Paints Limited | 01/07/2026 | 325,939 | 111,115 | 214,824
Asian Paints Limited | 01/07/2026 | 16 | 12 | 4
Asian Paints Limited | 01/07/2026 | 0 | 0 | 0
Asian Paints Limited | 01/08/2026 | 0 | 0 | 0
Asian Paints Limited | 01/08/2026 | 0 | 0 | 0
Asian Paints Limited | 01/08/2026 | 0 | 0 | 0
Asian Paints Limited | 01/08/2026 | 0 | 0 | 0
Asian Paints Limited | 01/08/2026 | 0 | 0 | 0
Asian Paints Limited | 01/08/2026 | 245,003 | 83,524 | 161,479
Asian Paints Limited | 01/08/2026 | 4 | 3 | 1
Asian Paints Limited | 01/08/2026 | 2 | 2 | 0
Astro Arun Pandit Pvt. Ltd. | 01/04/2026 | 8,563 | 5,352 | 3,211
Astro Arun Pandit Pvt. Ltd. | 01/04/2026 | 8 | 5 | 3
Astro Arun Pandit Pvt. Ltd. | 01/05/2026 | 3,814 | 2,384 | 1,430
Astro Arun Pandit Pvt. Ltd. | 01/05/2026 | 5,403 | 3,377 | 2,026
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 1 | 0 | 1
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 1 | 0 | 1
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Astro Arun Pandit Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Astrovision Futuretech Pvt. Ltd. | 01/04/2026 | 2,093 | 1,121 | 972
Astrovision Futuretech Pvt. Ltd. | 01/05/2026 | 2,004 | 1,074 | 930
Astrovision Futuretech Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astrovision Futuretech Pvt. Ltd. | 01/06/2026 | 5,125 | 2,745 | 2,380
Astrovision Futuretech Pvt. Ltd. | 01/06/2026 | 10 | 3 | 7
Astrovision Futuretech Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Astrovision Futuretech Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astrovision Futuretech Pvt. Ltd. | 01/07/2026 | 10,818 | 5,795 | 5,023
Astrovision Futuretech Pvt. Ltd. | 01/07/2026 | 10 | 3 | 7
Astrovision Futuretech Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Astrovision Futuretech Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Astrovision Futuretech Pvt. Ltd. | 01/08/2026 | 3,260 | 1,746 | 1,514
Astrovision Futuretech Pvt. Ltd. | 01/08/2026 | 20 | 6 | 14
Astrovision Futuretech Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/04/2026 | 0 | 2,120 | -2,120
Attero Recycling Private Limited | 01/05/2026 | 8,566 | 8,675 | -109
Attero Recycling Private Limited | 01/06/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/06/2026 | 3,185 | 4,639 | -1,454
Attero Recycling Private Limited | 01/06/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/06/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/07/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/07/2026 | 3,059 | 4,545 | -1,486
Attero Recycling Private Limited | 01/07/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/07/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/08/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/08/2026 | 2,612 | 4,450 | -1,838
Attero Recycling Private Limited | 01/08/2026 | 0 | 0 | 0
Attero Recycling Private Limited | 01/08/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/06/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/06/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/06/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/06/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/07/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/07/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/07/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/07/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/08/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/08/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/08/2026 | 0 | 0 | 0
Aviva Life Insurance Company India Ltd. | 01/08/2026 | 0 | 0 | 0
Axis Asset Management Company Limited | 01/04/2026 | 82,926 | 25,915 | 57,011
Axis Asset Management Company Limited | 01/04/2026 | 23 | 10 | 13
Axis Asset Management Company Limited | 01/05/2026 | 36,816 | 11,505 | 25,311
Axis Asset Management Company Limited | 01/05/2026 | 5 | 2 | 3
Axis Asset Management Company Limited | 01/06/2026 | 0 | 0 | 0
Axis Asset Management Company Limited | 01/06/2026 | 28,917 | 9,037 | 19,880
Axis Asset Management Company Limited | 01/06/2026 | 1 | 0 | 1
Axis Asset Management Company Limited | 01/06/2026 | 0 | 0 | 0
Axis Asset Management Company Limited | 01/07/2026 | 0 | 0 | 0
Axis Asset Management Company Limited | 01/07/2026 | 56,167 | 17,552 | 38,615
Axis Asset Management Company Limited | 01/07/2026 | 6 | 3 | 3
Axis Asset Management Company Limited | 01/07/2026 | 0 | 0 | 0
Axis Asset Management Company Limited | 01/08/2026 | 0 | 0 | 0
Axis Asset Management Company Limited | 01/08/2026 | 49,192 | 15,372 | 33,820
Axis Asset Management Company Limited | 01/08/2026 | 3 | 1 | 2
Axis Asset Management Company Limited | 01/08/2026 | 1 | 1 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/04/2026 | 14,407 | 9,754 | 4,653
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/05/2026 | 14,802 | 10,001 | 4,801
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/06/2026 | 70,608 | 44,880 | 25,728
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/07/2026 | 18,272 | 12,170 | 6,102
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/08/2026 | 55,837 | 35,729 | 20,108
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
BACCA BUCCI FASHIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/04/2026 | 303,862 | 103,589 | 200,273
Bajaj Allianz General Insurance Company Ltd. | 01/04/2026 | 91 | 44 | 47
Bajaj Allianz General Insurance Company Ltd. | 01/04/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/05/2026 | 298,273 | 101,684 | 196,589
Bajaj Allianz General Insurance Company Ltd. | 01/05/2026 | 31 | 15 | 16
Bajaj Allianz General Insurance Company Ltd. | 01/05/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 298,890 | 101,894 | 196,996
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 36 | 17 | 19
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 314,082 | 107,074 | 207,008
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 25 | 12 | 13
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 64,309 | 34,451 | 29,858
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 286,633 | 97,716 | 188,917
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 12 | 7 | 5
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz General Insurance Company Ltd. | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/04/2026 | 345,288 | 107,902 | 237,386
Bajaj Allianz Life Insurance Company Ltd | 01/05/2026 | 129,393 | 40,435 | 88,958
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 23,470 | 7,334 | 16,136
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Allianz Life Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
BAJAJ AUTO CREDIT LIMITED | 01/07/2026 | 0 | 0 | 0
BAJAJ AUTO CREDIT LIMITED | 01/07/2026 | 7,456 | 4,660 | 2,796
BAJAJ AUTO CREDIT LIMITED | 01/07/2026 | 0 | 0 | 0
BAJAJ AUTO CREDIT LIMITED | 01/07/2026 | 0 | 0 | 0
BAJAJ AUTO CREDIT LIMITED | 01/08/2026 | 0 | 0 | 0
BAJAJ AUTO CREDIT LIMITED | 01/08/2026 | 16,164 | 10,102 | 6,062
BAJAJ AUTO CREDIT LIMITED | 01/08/2026 | 39 | 17 | 22
BAJAJ AUTO CREDIT LIMITED | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/04/2026 | 861,417 | 587,330 | 274,087
Bajaj Finserv Direct Ltd | 01/04/2026 | 28,186 | 15,502 | 12,684
Bajaj Finserv Direct Ltd | 01/05/2026 | 5,892,184 | 4,469,933 | 1,422,251
Bajaj Finserv Direct Ltd | 01/05/2026 | 1,581 | 669 | 912
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 5,005,378 | 3,797,183 | 1,208,195
Bajaj Finserv Direct Ltd | 01/06/2026 | 1 | 0 | 1
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 543,332 | 412,183 | 131,149
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 2 | 2 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 1,646,732 | 1,249,245 | 397,487
Bajaj Finserv Direct Ltd | 01/08/2026 | 1,345 | 569 | 776
Bajaj Finserv Direct Ltd | 01/08/2026 | 2 | 2 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Direct Ltd | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/08/2026 | 0 | 0 | 0
Bajaj Finserv Health Limited | 01/08/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/06/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/07/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/08/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/08/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/08/2026 | 0 | 0 | 0
Bajaj Housing Finance Limited | 01/08/2026 | 0 | 0 | 0
BigHaat Agro Private Limited | 01/04/2026 | 45,654 | 17,120 | 28,534
BigHaat Agro Private Limited | 01/04/2026 | 41 | 19 | 22
BigHaat Agro Private Limited | 01/05/2026 | 31,633 | 11,862 | 19,771
BigHaat Agro Private Limited | 01/05/2026 | 35 | 16 | 19
BigHaat Agro Private Limited | 01/06/2026 | 0 | 0 | 0
BigHaat Agro Private Limited | 01/06/2026 | 29,044 | 10,892 | 18,152
BigHaat Agro Private Limited | 01/06/2026 | 60 | 28 | 32
BigHaat Agro Private Limited | 01/06/2026 | 0 | 0 | 0
BigHaat Agro Private Limited | 01/07/2026 | 0 | 0 | 0
BigHaat Agro Private Limited | 01/07/2026 | 57,325 | 21,497 | 35,828
BigHaat Agro Private Limited | 01/07/2026 | 85 | 40 | 45
BigHaat Agro Private Limited | 01/07/2026 | 0 | 0 | 0
BigHaat Agro Private Limited | 01/08/2026 | 0 | 0 | 0
BigHaat Agro Private Limited | 01/08/2026 | 65,686 | 24,632 | 41,054
BigHaat Agro Private Limited | 01/08/2026 | 94 | 44 | 50
BigHaat Agro Private Limited | 01/08/2026 | 7 | 5 | 2
BRAMHACORP LIMITED | 01/06/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/06/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/06/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/06/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/07/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/07/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/07/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/07/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/08/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/08/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/08/2026 | 0 | 0 | 0
BRAMHACORP LIMITED | 01/08/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Brand Studio Lifestyle Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/04/2026 | 68,114 | 56,762 | 11,352
Bright Lifecare Pvt. Ltd | 01/04/2026 | 37 | 60 | -23
Bright Lifecare Pvt. Ltd | 01/04/2026 | 71,087 | 59,239 | 11,848
Bright Lifecare Pvt. Ltd | 01/04/2026 | 29 | 48 | -19
Bright Lifecare Pvt. Ltd | 01/05/2026 | 37,656 | 31,380 | 6,276
Bright Lifecare Pvt. Ltd | 01/05/2026 | 10 | 17 | -7
Bright Lifecare Pvt. Ltd | 01/05/2026 | 39,695 | 33,079 | 6,616
Bright Lifecare Pvt. Ltd | 01/05/2026 | 19 | 32 | -13
Bright Lifecare Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/06/2026 | 32,217 | 26,848 | 5,369
Bright Lifecare Pvt. Ltd | 01/06/2026 | 23 | 39 | -16
Bright Lifecare Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/06/2026 | 87,345 | 72,787 | 14,558
Bright Lifecare Pvt. Ltd | 01/06/2026 | 51 | 84 | -33
Bright Lifecare Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/07/2026 | 40,679 | 33,899 | 6,780
Bright Lifecare Pvt. Ltd | 01/07/2026 | 6 | 11 | -5
Bright Lifecare Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/07/2026 | 91,952 | 76,626 | 15,326
Bright Lifecare Pvt. Ltd | 01/07/2026 | 65 | 107 | -42
Bright Lifecare Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/08/2026 | 21,362 | 17,801 | 3,561
Bright Lifecare Pvt. Ltd | 01/08/2026 | 11 | 18 | -7
Bright Lifecare Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Bright Lifecare Pvt. Ltd | 01/08/2026 | 81,279 | 67,733 | 13,546
Bright Lifecare Pvt. Ltd | 01/08/2026 | 45 | 74 | -29
Bright Lifecare Pvt. Ltd | 01/08/2026 | 3 | 2 | 1
Canara HSBC Life Insurance Company Limited | 01/04/2026 | 34,666 | 13,866 | 20,800
Canara HSBC Life Insurance Company Limited | 01/04/2026 | 29,462 | 11,785 | 17,677
Canara HSBC Life Insurance Company Limited | 01/05/2026 | 13,243 | 5,297 | 7,946
Canara HSBC Life Insurance Company Limited | 01/05/2026 | 30,977 | 12,391 | 18,586
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 13,436 | 5,375 | 8,061
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 14,916 | 5,966 | 8,950
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 5,630 | 2,252 | 3,378
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 12,638 | 5,055 | 7,583
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 13,024 | 5,210 | 7,814
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Canara HSBC Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/04/2026 | 59,360 | 37,100 | 22,260
Capfloat Financial Services Pvt. Ltd. | 01/04/2026 | 1 | 0 | 1
Capfloat Financial Services Pvt. Ltd. | 01/05/2026 | 83,190 | 51,994 | 31,196
Capfloat Financial Services Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/06/2026 | 97,893 | 61,183 | 36,710
Capfloat Financial Services Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/07/2026 | 201,316 | 125,822 | 75,494
Capfloat Financial Services Pvt. Ltd. | 01/07/2026 | 1 | 1 | 0
Capfloat Financial Services Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/08/2026 | 286,496 | 179,060 | 107,436
Capfloat Financial Services Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Capfloat Financial Services Pvt. Ltd. | 01/08/2026 | 2 | 2 | 0
CASHGRAIL PRIVATE LIMITED | 01/04/2026 | 6,241 | 3,120 | 3,121
CASHGRAIL PRIVATE LIMITED | 01/05/2026 | 7,020 | 3,510 | 3,510
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 6,954 | 3,477 | 3,477
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 2,022 | 1,011 | 1,011
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 1,881 | 940 | 941
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 9 | 4 | 5
CASHGRAIL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/05/2026 | 10,818 | 8,126 | 2,692
Chipper Consumer Private Limited | 01/06/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/06/2026 | 194 | 882 | -688
Chipper Consumer Private Limited | 01/06/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/06/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/07/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/07/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/07/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/07/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/08/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/08/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/08/2026 | 0 | 0 | 0
Chipper Consumer Private Limited | 01/08/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/04/2026 | 10 | 3 | 7
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/04/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/05/2026 | 4 | 1 | 3
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/05/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/06/2026 | 13 | 4 | 9
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/07/2026 | 4 | 1 | 3
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
CHOLAMANDALAM INVESTMENT AND FINANCE COMPANY LIMITED | 01/08/2026 | 1 | 1 | 0
Cinepolis India Pvt. Ltd. | 01/04/2026 | 28,935 | 21,701 | 7,234
Cinepolis India Pvt. Ltd. | 01/05/2026 | 217 | 163 | 54
Cinepolis India Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/06/2026 | 8,220 | 6,165 | 2,055
Cinepolis India Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/07/2026 | 8,682 | 6,511 | 2,171
Cinepolis India Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/08/2026 | 282 | 212 | 70
Cinepolis India Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Cinepolis India Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/04/2026 | 38,189 | 13,769 | 24,420
Clinikally Digital Health Pvt Ltd | 01/05/2026 | 37,701 | 13,603 | 24,098
Clinikally Digital Health Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/06/2026 | 39,448 | 14,198 | 25,250
Clinikally Digital Health Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/07/2026 | 43,197 | 15,476 | 27,721
Clinikally Digital Health Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/08/2026 | 43,666 | 15,717 | 27,949
Clinikally Digital Health Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Clinikally Digital Health Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/04/2026 | 433,521 | 295,583 | 137,938
Comsense Technologies Private Limited | 01/05/2026 | 367,002 | 250,229 | 116,773
Comsense Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/06/2026 | 455,618 | 310,648 | 144,970
Comsense Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/07/2026 | 281,918 | 192,217 | 89,701
Comsense Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Comsense Technologies Private Limited | 01/08/2026 | 82,731 | 56,407 | 26,324
Comsense Technologies Private Limited | 01/08/2026 | 187,069 | 127,547 | 59,522
Comsense Technologies Private Limited | 01/08/2026 | 89 | 44 | 45
Comsense Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/04/2026 | 99,198 | 30,999 | 68,199
CONCEPT COMMUNICATION LTD | 01/04/2026 | 4 | 1 | 3
CONCEPT COMMUNICATION LTD | 01/05/2026 | 114,358 | 35,737 | 78,621
CONCEPT COMMUNICATION LTD | 01/06/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/06/2026 | 58,702 | 18,344 | 40,358
CONCEPT COMMUNICATION LTD | 01/06/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/06/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/07/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/07/2026 | 30,157 | 9,424 | 20,733
CONCEPT COMMUNICATION LTD | 01/07/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/07/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/08/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/08/2026 | 2 | 1 | 1
CONCEPT COMMUNICATION LTD | 01/08/2026 | 0 | 0 | 0
CONCEPT COMMUNICATION LTD | 01/08/2026 | 0 | 0 | 0
CONTAGIOUS V | 01/07/2026 | 0 | 0 | 0
CONTAGIOUS V | 01/07/2026 | 1,446 | 1,202 | 244
CONTAGIOUS V | 01/07/2026 | 0 | 0 | 0
CONTAGIOUS V | 01/07/2026 | 0 | 0 | 0
CONTAGIOUS V | 01/08/2026 | 0 | 0 | 0
CONTAGIOUS V | 01/08/2026 | 0 | 0 | 0
CONTAGIOUS V | 01/08/2026 | 2 | 1 | 1
CONTAGIOUS V | 01/08/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/06/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/06/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/06/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/06/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/07/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/07/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/07/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/07/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/08/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/08/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/08/2026 | 0 | 0 | 0
COSMO FIRST LIMITED | 01/08/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
COUPL SOFTWARE INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/06/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/06/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/06/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/06/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/07/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/07/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/07/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/07/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/08/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/08/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/08/2026 | 0 | 0 | 0
Credify Technologies Pvt Ltd. | 01/08/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/04/2026 | 105,038 | 56,270 | 48,768
CROCS INDIA PRIVATE LIMITED | 01/05/2026 | 214,342 | 114,826 | 99,516
CROCS INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/06/2026 | 186,811 | 100,077 | 86,734
CROCS INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/07/2026 | 213,741 | 114,504 | 99,237
CROCS INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/08/2026 | 181,769 | 97,376 | 84,393
CROCS INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
CROCS INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/06/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/06/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/06/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/06/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/07/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/07/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/07/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/07/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/08/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/08/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/08/2026 | 0 | 0 | 0
Defmacro Software Private Limited | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DFINKARD HUB PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/04/2026 | 0 | 231 | -231
DOCTORVAHINI PRIVATE LIMITED | 01/05/2026 | 0 | 245 | -245
DOCTORVAHINI PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/08/2026 | 35,836 | 25,264 | 10,572
DOCTORVAHINI PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
DOCTORVAHINI PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/05/2026 | 29,319 | 20,199 | 9,120
Dr B Lal Clinical Laboratory Private Limited | 01/06/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/06/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/06/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/06/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/07/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/07/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/07/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/07/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/08/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/08/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/08/2026 | 0 | 0 | 0
Dr B Lal Clinical Laboratory Private Limited | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/04/2026 | 891 | 393 | 498
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/05/2026 | 247 | 109 | 138
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 263 | 116 | 147
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EDELWEISS ASSET RECONSTRUCTION COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
EGNIOL FINANCIAL SERVICES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Emami Ltd | 01/04/2026 | 38,317 | 28,737 | 9,580
Emami Ltd | 01/05/2026 | 38,727 | 29,046 | 9,681
Emami Ltd | 01/06/2026 | 0 | 0 | 0
Emami Ltd | 01/06/2026 | 2,200 | 1,650 | 550
Emami Ltd | 01/06/2026 | 0 | 0 | 0
Emami Ltd | 01/06/2026 | 0 | 0 | 0
Emami Ltd | 01/07/2026 | 0 | 0 | 0
Emami Ltd | 01/07/2026 | 2,200 | 1,650 | 550
Emami Ltd | 01/07/2026 | 0 | 0 | 0
Emami Ltd | 01/07/2026 | 0 | 0 | 0
Emami Ltd | 01/08/2026 | 0 | 0 | 0
Emami Ltd | 01/08/2026 | 2,436 | 1,827 | 609
Emami Ltd | 01/08/2026 | 0 | 0 | 0
Emami Ltd | 01/08/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/04/2026 | 931 | 1,067 | -136
EMMA SLEEP INDIA PRIVATE LIMITED | 01/05/2026 | 2,341 | 1,548 | 793
EMMA SLEEP INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/06/2026 | 3,759 | 2,032 | 1,727
EMMA SLEEP INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/07/2026 | 4,320 | 2,223 | 2,097
EMMA SLEEP INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/08/2026 | 4,876 | 2,493 | 2,383
EMMA SLEEP INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
EMMA SLEEP INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/08/2026 | 15 | 11 | 4
Epifi Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Epifi Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/04/2026 | 50,632 | 15,190 | 35,442
Equitas Small Finance Bank Ltd | 01/04/2026 | 7 | 3 | 4
Equitas Small Finance Bank Ltd | 01/04/2026 | 2,143 | 643 | 1,500
Equitas Small Finance Bank Ltd | 01/04/2026 | 4,894 | 1,468 | 3,426
Equitas Small Finance Bank Ltd | 01/05/2026 | 94,210 | 28,263 | 65,947
Equitas Small Finance Bank Ltd | 01/05/2026 | 13 | 6 | 7
Equitas Small Finance Bank Ltd | 01/05/2026 | 9,446 | 2,834 | 6,612
Equitas Small Finance Bank Ltd | 01/05/2026 | 4,560 | 1,368 | 3,192
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/06/2026 | 58,430 | 17,529 | 40,901
Equitas Small Finance Bank Ltd | 01/06/2026 | 17 | 8 | 9
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/06/2026 | 21,944 | 6,583 | 15,361
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/06/2026 | 5,404 | 1,621 | 3,783
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/06/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 94,185 | 28,255 | 65,930
Equitas Small Finance Bank Ltd | 01/07/2026 | 26 | 12 | 14
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 7,515 | 2,255 | 5,260
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/07/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 123,590 | 37,077 | 86,513
Equitas Small Finance Bank Ltd | 01/08/2026 | 71 | 34 | 37
Equitas Small Finance Bank Ltd | 01/08/2026 | 10 | 8 | 2
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Equitas Small Finance Bank Ltd | 01/08/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/04/2026 | 6,848 | 5,886 | 962
Exotic India Art Private Limited | 01/05/2026 | 19,750 | 15,563 | 4,187
Exotic India Art Private Limited | 01/06/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/06/2026 | 13,525 | 10,894 | 2,631
Exotic India Art Private Limited | 01/06/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/06/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/07/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/07/2026 | 8,658 | 7,244 | 1,414
Exotic India Art Private Limited | 01/07/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/07/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/08/2026 | 0 | 0 | 0
Exotic India Art Private Limited | 01/08/2026 | 50,255 | 38,522 | 11,733
Exotic India Art Private Limited | 01/08/2026 | 15 | 22 | -7
Exotic India Art Private Limited | 01/08/2026 | 9 | 8 | 1
Extramarks Education India Pvt. Ltd | 01/04/2026 | 6,112 | 1,993 | 4,119
Extramarks Education India Pvt. Ltd | 01/05/2026 | 12,454 | 4,061 | 8,393
Extramarks Education India Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Extramarks Education India Pvt. Ltd | 01/06/2026 | 11,816 | 3,853 | 7,963
Extramarks Education India Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Extramarks Education India Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Extramarks Education India Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Extramarks Education India Pvt. Ltd | 01/07/2026 | 7,874 | 2,567 | 5,307
Extramarks Education India Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Extramarks Education India Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Extramarks Education India Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Extramarks Education India Pvt. Ltd | 01/08/2026 | 4,996 | 1,629 | 3,367
Extramarks Education India Pvt. Ltd | 01/08/2026 | 7 | 3 | 4
Extramarks Education India Pvt. Ltd | 01/08/2026 | 1 | 1 | 0
FABINDIA LIMITED | 01/04/2026 | 60,717 | 41,398 | 19,319
FABINDIA LIMITED | 01/05/2026 | 10,245 | 6,985 | 3,260
FABINDIA LIMITED | 01/06/2026 | 0 | 0 | 0
FABINDIA LIMITED | 01/06/2026 | 50,887 | 34,696 | 16,191
FABINDIA LIMITED | 01/06/2026 | 0 | 0 | 0
FABINDIA LIMITED | 01/06/2026 | 0 | 0 | 0
FABINDIA LIMITED | 01/07/2026 | 0 | 0 | 0
FABINDIA LIMITED | 01/07/2026 | 21,365 | 14,567 | 6,798
FABINDIA LIMITED | 01/07/2026 | 0 | 0 | 0
FABINDIA LIMITED | 01/07/2026 | 0 | 0 | 0
FABINDIA LIMITED | 01/08/2026 | 0 | 0 | 0
FABINDIA LIMITED | 01/08/2026 | 17,643 | 12,029 | 5,614
FABINDIA LIMITED | 01/08/2026 | 5 | 4 | 1
FABINDIA LIMITED | 01/08/2026 | 1 | 1 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FPL TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
FreshToHome Foods Pvt. Ltd. | 01/04/2026 | 114,988 | 78,401 | 36,587
FreshToHome Foods Pvt. Ltd. | 01/04/2026 | 83 | 43 | 40
FreshToHome Foods Pvt. Ltd. | 01/05/2026 | 99,226 | 67,654 | 31,572
FreshToHome Foods Pvt. Ltd. | 01/05/2026 | 102 | 52 | 50
FreshToHome Foods Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
FreshToHome Foods Pvt. Ltd. | 01/06/2026 | 200,072 | 136,413 | 63,659
FreshToHome Foods Pvt. Ltd. | 01/06/2026 | 88 | 46 | 42
FreshToHome Foods Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
FreshToHome Foods Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
FreshToHome Foods Pvt. Ltd. | 01/07/2026 | 106,638 | 72,707 | 33,931
FreshToHome Foods Pvt. Ltd. | 01/07/2026 | 108 | 56 | 52
FreshToHome Foods Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
FreshToHome Foods Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
FreshToHome Foods Pvt. Ltd. | 01/08/2026 | 108,486 | 73,968 | 34,518
FreshToHome Foods Pvt. Ltd. | 01/08/2026 | 95 | 49 | 46
FreshToHome Foods Pvt. Ltd. | 01/08/2026 | 3 | 3 | 0
Future Generali India Life Insurance Co. Ltd. | 01/05/2026 | 3,767 | 1,413 | 2,354
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Future Generali India Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/04/2026 | 33,837 | 16,918 | 16,919
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/05/2026 | 85,202 | 42,601 | 42,601
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/06/2026 | 39,788 | 19,894 | 19,894
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/07/2026 | 22,368 | 11,184 | 11,184
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/08/2026 | 25,648 | 12,824 | 12,824
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
GIRNAR INSURANCE BROKERS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/06/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/06/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/06/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/06/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/07/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/07/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/07/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/07/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/08/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/08/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/08/2026 | 0 | 0 | 0
GLOBAL HEALTHFIT RETAIL INDIA LLP | 01/08/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/04/2026 | 1,606 | 502 | 1,104
Good Folks Fashion Pvt. Ltd. | 01/05/2026 | 976 | 305 | 671
Good Folks Fashion Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/06/2026 | 466 | 146 | 320
Good Folks Fashion Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/07/2026 | 43 | 13 | 30
Good Folks Fashion Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Good Folks Fashion Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/04/2026 | 13,510 | 5,629 | 7,881
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/05/2026 | 16,096 | 6,707 | 9,389
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/06/2026 | 24,746 | 10,311 | 14,435
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/07/2026 | 27,490 | 11,454 | 16,036
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/08/2026 | 26,201 | 10,917 | 15,284
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/08/2026 | 398 | 365 | 33
GRAMSTRONG E-SERVICES PRIVATE LIMITED | 01/08/2026 | 10 | 5 | 5
Groom India Salon & Spa Private Limited | 01/06/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/06/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/06/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/06/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/07/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/07/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/07/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/07/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/08/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/08/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/08/2026 | 0 | 0 | 0
Groom India Salon & Spa Private Limited | 01/08/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/04/2026 | 56,135 | 42,851 | 13,284
GRT Jewellers (India) Pvt. Ltd. | 01/05/2026 | 43,527 | 33,395 | 10,132
GRT Jewellers (India) Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/06/2026 | 78,896 | 59,922 | 18,974
GRT Jewellers (India) Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/07/2026 | 62,375 | 47,532 | 14,843
GRT Jewellers (India) Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
GRT Jewellers (India) Pvt. Ltd. | 01/08/2026 | 214,867 | 161,981 | 52,886
GRT Jewellers (India) Pvt. Ltd. | 01/08/2026 | 153 | 53 | 100
GRT Jewellers (India) Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/04/2026 | 1,098 | 412 | 686
GUVI Geek Network Private Limited | 01/05/2026 | 489 | 183 | 306
GUVI Geek Network Private Limited | 01/06/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/06/2026 | 3,795 | 1,423 | 2,372
GUVI Geek Network Private Limited | 01/06/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/06/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/07/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/07/2026 | 4,725 | 1,772 | 2,953
GUVI Geek Network Private Limited | 01/07/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/07/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/08/2026 | 0 | 0 | 0
GUVI Geek Network Private Limited | 01/08/2026 | 3,141 | 1,178 | 1,963
GUVI Geek Network Private Limited | 01/08/2026 | 17 | 9 | 8
GUVI Geek Network Private Limited | 01/08/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/06/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/06/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/06/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/06/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/07/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/07/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/07/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/07/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/08/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/08/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/08/2026 | 0 | 0 | 0
Hamilton Sciences Private Limited | 01/08/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/04/2026 | 39,361 | 24,601 | 14,760
Hansa Customer Equity Pvt. Ltd. | 01/04/2026 | 1 | 0 | 1
Hansa Customer Equity Pvt. Ltd. | 01/05/2026 | 27,313 | 17,071 | 10,242
Hansa Customer Equity Pvt. Ltd. | 01/05/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Hansa Customer Equity Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/04/2026 | 242,639 | 121,319 | 121,320
HDFC Asset Management Company Ltd. | 01/05/2026 | 105,730 | 33,041 | 72,689
HDFC Asset Management Company Ltd. | 01/06/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/06/2026 | 209,812 | 65,566 | 144,246
HDFC Asset Management Company Ltd. | 01/06/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/06/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/07/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/07/2026 | 50,592 | 15,810 | 34,782
HDFC Asset Management Company Ltd. | 01/07/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/07/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/08/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/08/2026 | 2 | 1 | 1
HDFC Asset Management Company Ltd. | 01/08/2026 | 0 | 0 | 0
HDFC Asset Management Company Ltd. | 01/08/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/04/2026 | 22,188 | 6,656 | 15,532
Credila Financial Services Limited | 01/05/2026 | 74 | 22 | 52
Credila Financial Services Limited | 01/06/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/06/2026 | 120 | 36 | 84
Credila Financial Services Limited | 01/06/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/06/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/07/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/07/2026 | 103 | 31 | 72
Credila Financial Services Limited | 01/07/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/07/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/08/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/08/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/08/2026 | 0 | 0 | 0
Credila Financial Services Limited | 01/08/2026 | 3 | 3 | 0
Hinaya technologies (OPC) Private Limited | 01/06/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/06/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/06/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/06/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/07/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/07/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/07/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/07/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/08/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/08/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/08/2026 | 0 | 0 | 0
Hinaya technologies (OPC) Private Limited | 01/08/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/06/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/06/2026 | 74,627 | 55,970 | 18,657
ICICI Bank Limited | 01/06/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/06/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/07/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/07/2026 | 76,864 | 57,648 | 19,216
ICICI Bank Limited | 01/07/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/07/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/08/2026 | 0 | 0 | 0
ICICI Bank Limited | 01/08/2026 | 264,523 | 198,392 | 66,131
ICICI Bank Limited | 01/08/2026 | 251 | 77 | 174
ICICI Bank Limited | 01/08/2026 | 1 | 0 | 1
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/04/2026 | 2 | 2 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/05/2026 | 1,705 | 1,279 | 426
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/06/2026 | 0 | 0 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/06/2026 | 4 | 3 | 1
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/06/2026 | 0 | 0 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/06/2026 | 0 | 0 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/07/2026 | 0 | 0 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/07/2026 | 4 | 3 | 1
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/07/2026 | 0 | 0 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/07/2026 | 0 | 0 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/08/2026 | 0 | 0 | 0
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/08/2026 | 198 | 149 | 49
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/08/2026 | 1 | 0 | 1
ICICI PRUDENTIAL ASSET MANAGEMENT COMPANY LTD. | 01/08/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/04/2026 | 191,952 | 84,685 | 107,267
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/05/2026 | 127,028 | 56,042 | 70,986
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 13,641 | 6,018 | 7,623
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 482,083 | 212,684 | 269,399
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 394,472 | 174,032 | 220,440
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 61 | 37 | 24
ICICI PRUDENTIAL LIFE INSURANCE COMPANY LIMITED | 01/08/2026 | 5 | 4 | 1
IDAHO INTERNATIONAL | 01/06/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/06/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/06/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/06/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/07/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/07/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/07/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/07/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/08/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/08/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/08/2026 | 0 | 0 | 0
IDAHO INTERNATIONAL | 01/08/2026 | 0 | 0 | 0
IGUIDER LEARNING PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
IGUIDER LEARNING PRIVATE LIMITED | 01/07/2026 | 5,046 | 1,514 | 3,532
IGUIDER LEARNING PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
IGUIDER LEARNING PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
IGUIDER LEARNING PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
IGUIDER LEARNING PRIVATE LIMITED | 01/08/2026 | 9 | 3 | 6
IGUIDER LEARNING PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
IGUIDER LEARNING PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/06/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/06/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/06/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/06/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/07/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/07/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/07/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/07/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/08/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/08/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/08/2026 | 0 | 0 | 0
IMPACT GURU TECHNOLOGY VENTURES PVT LTD | 01/08/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/04/2026 | 160 | 60 | 100
IMS Learning Resource Private Limited | 01/05/2026 | 5,451 | 2,044 | 3,407
IMS Learning Resource Private Limited | 01/06/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/06/2026 | 127 | 48 | 79
IMS Learning Resource Private Limited | 01/06/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/06/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/07/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/07/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/07/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/07/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/08/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/08/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/08/2026 | 0 | 0 | 0
IMS Learning Resource Private Limited | 01/08/2026 | 0 | 0 | 0
Indian Bank | 01/05/2026 | 24,407 | 20,339 | 4,068
Indian Bank | 01/06/2026 | 0 | 0 | 0
Indian Bank | 01/06/2026 | 55,498 | 46,248 | 9,250
Indian Bank | 01/06/2026 | 0 | 0 | 0
Indian Bank | 01/06/2026 | 0 | 0 | 0
Indian Bank | 01/07/2026 | 0 | 0 | 0
Indian Bank | 01/07/2026 | 694,465 | 578,721 | 115,744
Indian Bank | 01/07/2026 | 0 | 0 | 0
Indian Bank | 01/07/2026 | 0 | 0 | 0
Indian Bank | 01/08/2026 | 0 | 0 | 0
Indian Bank | 01/08/2026 | 176,056 | 146,713 | 29,343
Indian Bank | 01/08/2026 | 784 | 270 | 514
Indian Bank | 01/08/2026 | 1 | 1 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/04/2026 | 1,801 | 965 | 836
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/05/2026 | 63,573 | 34,057 | 29,516
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 94,697 | 50,731 | 43,966
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 89,843 | 48,130 | 41,713
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 181,640 | 97,307 | 84,333
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 39 | 31 | 8
INDIFI TECHNOLOGIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/04/2026 | 23,398 | 7,312 | 16,086
Indusind Bank Limited | 01/05/2026 | 22 | 7 | 15
Indusind Bank Limited | 01/06/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/06/2026 | 80 | 60 | 20
Indusind Bank Limited | 01/06/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/06/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/07/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/07/2026 | 16,183 | 12,137 | 4,046
Indusind Bank Limited | 01/07/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/07/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/08/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/08/2026 | 51,059 | 38,295 | 12,764
Indusind Bank Limited | 01/08/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/08/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/08/2026 | 0 | 0 | 0
Indusind Bank Limited | 01/08/2026 | 20,145 | 15,108 | 5,037
Indusind Bank Limited | 01/08/2026 | 12 | 7 | 5
Indusind Bank Limited | 01/08/2026 | 0 | 0 | 0
Internship Studio | 01/06/2026 | 0 | 0 | 0
Internship Studio | 01/06/2026 | 0 | 0 | 0
Internship Studio | 01/06/2026 | 0 | 0 | 0
Internship Studio | 01/06/2026 | 0 | 0 | 0
Internship Studio | 01/07/2026 | 0 | 0 | 0
Internship Studio | 01/07/2026 | 0 | 0 | 0
Internship Studio | 01/07/2026 | 0 | 0 | 0
Internship Studio | 01/07/2026 | 0 | 0 | 0
Internship Studio | 01/08/2026 | 0 | 0 | 0
Internship Studio | 01/08/2026 | 0 | 0 | 0
Internship Studio | 01/08/2026 | 0 | 0 | 0
Internship Studio | 01/08/2026 | 0 | 0 | 0
ION Exchange | 01/04/2026 | 8,351 | 4,175 | 4,176
ION Exchange | 01/05/2026 | 349 | 174 | 175
ION Exchange | 01/06/2026 | 0 | 0 | 0
ION Exchange | 01/06/2026 | 5,216 | 2,608 | 2,608
ION Exchange | 01/06/2026 | 0 | 0 | 0
ION Exchange | 01/06/2026 | 0 | 0 | 0
ION Exchange | 01/07/2026 | 0 | 0 | 0
ION Exchange | 01/07/2026 | 104 | 52 | 52
ION Exchange | 01/07/2026 | 0 | 0 | 0
ION Exchange | 01/07/2026 | 0 | 0 | 0
ION Exchange | 01/08/2026 | 0 | 0 | 0
ION Exchange | 01/08/2026 | 7,298 | 3,649 | 3,649
ION Exchange | 01/08/2026 | 12 | 4 | 8
ION Exchange | 01/08/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/04/2026 | 1,042 | 279 | 763
JOHN SALT PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
JOHN SALT PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Join Ventures Solutions Private Limited | 01/05/2026 | 332 | 104 | 228
Join Ventures Solutions Private Limited | 01/05/2026 | 1 | 1 | 0
Join Ventures Solutions Private Limited | 01/06/2026 | 0 | 0 | 0
Join Ventures Solutions Private Limited | 01/06/2026 | 1,148 | 359 | 789
Join Ventures Solutions Private Limited | 01/06/2026 | 1 | 0 | 1
Join Ventures Solutions Private Limited | 01/06/2026 | 0 | 0 | 0
Join Ventures Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Join Ventures Solutions Private Limited | 01/07/2026 | 1,309 | 409 | 900
Join Ventures Solutions Private Limited | 01/07/2026 | 1 | 0 | 1
Join Ventures Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Join Ventures Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Join Ventures Solutions Private Limited | 01/08/2026 | 3,224 | 1,008 | 2,216
Join Ventures Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Join Ventures Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Katyayani Organics | 01/04/2026 | 4,906 | 1,533 | 3,373
Katyayani Organics | 01/04/2026 | 41 | 13 | 28
Katyayani Organics | 01/05/2026 | 4,623 | 1,445 | 3,178
Katyayani Organics | 01/05/2026 | 48 | 15 | 33
Katyayani Organics | 01/06/2026 | 0 | 0 | 0
Katyayani Organics | 01/06/2026 | 3,929 | 1,228 | 2,701
Katyayani Organics | 01/06/2026 | 27 | 8 | 19
Katyayani Organics | 01/06/2026 | 0 | 0 | 0
Katyayani Organics | 01/07/2026 | 0 | 0 | 0
Katyayani Organics | 01/07/2026 | 6,768 | 2,115 | 4,653
Katyayani Organics | 01/07/2026 | 33 | 10 | 23
Katyayani Organics | 01/07/2026 | 0 | 0 | 0
Katyayani Organics | 01/08/2026 | 0 | 0 | 0
Katyayani Organics | 01/08/2026 | 11,793 | 3,685 | 8,108
Katyayani Organics | 01/08/2026 | 73 | 22 | 51
Katyayani Organics | 01/08/2026 | 0 | 0 | 0
Khelomore Sports Private Limited | 01/07/2026 | 0 | 0 | 0
Khelomore Sports Private Limited | 01/07/2026 | 4,405 | 1,377 | 3,028
Khelomore Sports Private Limited | 01/07/2026 | 0 | 0 | 0
Khelomore Sports Private Limited | 01/07/2026 | 0 | 0 | 0
Khelomore Sports Private Limited | 01/08/2026 | 0 | 0 | 0
Khelomore Sports Private Limited | 01/08/2026 | 2,706 | 845 | 1,861
Khelomore Sports Private Limited | 01/08/2026 | 0 | 0 | 0
Khelomore Sports Private Limited | 01/08/2026 | 0 | 0 | 0
Kirtilal Kalidas Jewellers Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Kirtilal Kalidas Jewellers Pvt Ltd | 01/07/2026 | 260 | 831 | -571
Kirtilal Kalidas Jewellers Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Kirtilal Kalidas Jewellers Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Kirtilal Kalidas Jewellers Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Kirtilal Kalidas Jewellers Pvt Ltd | 01/08/2026 | 3,207 | 1,833 | 1,374
Kirtilal Kalidas Jewellers Pvt Ltd | 01/08/2026 | 2 | 1 | 1
Kirtilal Kalidas Jewellers Pvt Ltd | 01/08/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/04/2026 | 6,230 | 4,672 | 1,558
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/06/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/07/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/08/2026 | 21,948 | 16,461 | 5,487
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/08/2026 | 8 | 7 | 1
KOTAK MAHINDRA ASSET MANAGEMENT COMPANY LIMITED | 01/08/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Kotak Mahindra General Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
LIQUIDE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
LIQUIDE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 4,765 | 3,249 | 1,516
LIQUIDE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 13 | 5 | 8
LIQUIDE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/04/2026 | 80,209 | 48,875 | 31,334
Magicbricks Realty Services Limited | 01/04/2026 | 3,274 | 2,401 | 873
Magicbricks Realty Services Limited | 01/04/2026 | 5 | 3 | 2
Magicbricks Realty Services Limited | 01/05/2026 | 73,920 | 45,102 | 28,818
Magicbricks Realty Services Limited | 01/05/2026 | 3,412 | 2,502 | 910
Magicbricks Realty Services Limited | 01/05/2026 | 7 | 4 | 3
Magicbricks Realty Services Limited | 01/06/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/06/2026 | 77,400 | 47,190 | 30,210
Magicbricks Realty Services Limited | 01/06/2026 | 4,082 | 2,994 | 1,088
Magicbricks Realty Services Limited | 01/06/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/06/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/06/2026 | 4 | 3 | 1
Magicbricks Realty Services Limited | 01/06/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/06/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/07/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/07/2026 | 76,680 | 46,758 | 29,922
Magicbricks Realty Services Limited | 01/07/2026 | 4,190 | 3,072 | 1,118
Magicbricks Realty Services Limited | 01/07/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/07/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/07/2026 | 6 | 4 | 2
Magicbricks Realty Services Limited | 01/07/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/07/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/08/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/08/2026 | 74,157 | 45,325 | 28,832
Magicbricks Realty Services Limited | 01/08/2026 | 2,840 | 2,083 | 757
Magicbricks Realty Services Limited | 01/08/2026 | 63 | 63 | 0
Magicbricks Realty Services Limited | 01/08/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/08/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/08/2026 | 0 | 0 | 0
Magicbricks Realty Services Limited | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/04/2026 | 120,535 | 43,048 | 77,487
Max Life Insurance Co. Ltd. | 01/04/2026 | 4 | 2 | 2
Max Life Insurance Co. Ltd. | 01/04/2026 | 21,108 | 7,539 | 13,569
Max Life Insurance Co. Ltd. | 01/04/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/05/2026 | 64,924 | 23,187 | 41,737
Max Life Insurance Co. Ltd. | 01/05/2026 | 4 | 2 | 2
Max Life Insurance Co. Ltd. | 01/05/2026 | 14,223 | 5,080 | 9,143
Max Life Insurance Co. Ltd. | 01/05/2026 | 1 | 0 | 1
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 109,260 | 39,021 | 70,239
Max Life Insurance Co. Ltd. | 01/06/2026 | 2 | 1 | 1
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 9,047 | 3,231 | 5,816
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 85,191 | 30,425 | 54,766
Max Life Insurance Co. Ltd. | 01/07/2026 | 4 | 2 | 2
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 20,590 | 7,353 | 13,237
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 83,320 | 29,757 | 53,563
Max Life Insurance Co. Ltd. | 01/08/2026 | 7 | 4 | 3
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 21,428 | 7,653 | 13,775
Max Life Insurance Co. Ltd. | 01/08/2026 | 1 | 1 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Max Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/06/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/06/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/06/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/06/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/07/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/07/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/07/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/07/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/08/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/08/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/08/2026 | 0 | 0 | 0
Maybright Ventures Private | 01/08/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
MCCOY DIGITAL PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/04/2026 | 693,943 | 400,352 | 293,591
Metropolis Healthcare Limited | 01/05/2026 | 818,127 | 471,997 | 346,130
Metropolis Healthcare Limited | 01/06/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/06/2026 | 553,198 | 319,153 | 234,045
Metropolis Healthcare Limited | 01/06/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/06/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/07/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/07/2026 | 744,135 | 429,309 | 314,826
Metropolis Healthcare Limited | 01/07/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/07/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/08/2026 | 0 | 0 | 0
Metropolis Healthcare Limited | 01/08/2026 | 807,241 | 465,716 | 341,525
Metropolis Healthcare Limited | 01/08/2026 | 200 | 132 | 68
Metropolis Healthcare Limited | 01/08/2026 | 19 | 16 | 3
Meyer Housewares India Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/06/2026 | 1,311 | 1,007 | 304
Meyer Housewares India Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/08/2026 | 1,082 | 884 | 198
Meyer Housewares India Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Meyer Housewares India Pvt Ltd | 01/08/2026 | 0 | 0 | 0
MOI Technology Private Limited | 01/07/2026 | 0 | 0 | 0
MOI Technology Private Limited | 01/07/2026 | 58,168 | 49,858 | 8,310
MOI Technology Private Limited | 01/07/2026 | 0 | 0 | 0
MOI Technology Private Limited | 01/07/2026 | 0 | 0 | 0
MOI Technology Private Limited | 01/08/2026 | 0 | 0 | 0
MOI Technology Private Limited | 01/08/2026 | 57,921 | 49,646 | 8,275
MOI Technology Private Limited | 01/08/2026 | 74 | 27 | 47
MOI Technology Private Limited | 01/08/2026 | 0 | 0 | 0
Munchmart Technologies Private Limited (Swish) | 01/07/2026 | 0 | 0 | 0
Munchmart Technologies Private Limited (Swish) | 01/07/2026 | 101,600 | 72,572 | 29,028
Munchmart Technologies Private Limited (Swish) | 01/07/2026 | 0 | 0 | 0
Munchmart Technologies Private Limited (Swish) | 01/07/2026 | 0 | 0 | 0
Munchmart Technologies Private Limited (Swish) | 01/08/2026 | 0 | 0 | 0
Munchmart Technologies Private Limited (Swish) | 01/08/2026 | 110,687 | 79,062 | 31,625
Munchmart Technologies Private Limited (Swish) | 01/08/2026 | 270 | 93 | 177
Munchmart Technologies Private Limited (Swish) | 01/08/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/04/2026 | 125,340 | 47,003 | 78,337
Muthoot Fincorp Ltd. | 01/05/2026 | 126,901 | 47,588 | 79,313
Muthoot Fincorp Ltd. | 01/06/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/06/2026 | 93,258 | 34,972 | 58,286
Muthoot Fincorp Ltd. | 01/06/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/06/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/07/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/07/2026 | 101,362 | 38,011 | 63,351
Muthoot Fincorp Ltd. | 01/07/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/07/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/08/2026 | 0 | 0 | 0
Muthoot Fincorp Ltd. | 01/08/2026 | 166,442 | 62,416 | 104,026
Muthoot Fincorp Ltd. | 01/08/2026 | 45 | 21 | 24
Muthoot Fincorp Ltd. | 01/08/2026 | 11 | 8 | 3
MWYN TECH PRIVATE LIMITED | 01/04/2026 | 1 | 0 | 1
MWYN TECH PRIVATE LIMITED | 01/05/2026 | 42,687 | 37,665 | 5,022
MWYN TECH PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/06/2026 | 386 | 340 | 46
MWYN TECH PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/08/2026 | 6 | 5 | 1
MWYN TECH PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
MWYN TECH PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/04/2026 | 9,421 | 5,435 | 3,986
My Money Mantra Fintech Pvt Ltd | 01/04/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/05/2026 | 53,734 | 31,001 | 22,733
My Money Mantra Fintech Pvt Ltd | 01/05/2026 | 2 | 2 | 0
My Money Mantra Fintech Pvt Ltd | 01/06/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/06/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/06/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/06/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/07/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/07/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/07/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/07/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/08/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/08/2026 | 3 | 2 | 1
My Money Mantra Fintech Pvt Ltd | 01/08/2026 | 0 | 0 | 0
My Money Mantra Fintech Pvt Ltd | 01/08/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/04/2026 | 306 | 191 | 115
MYDESIGNATION ONLINE CLOTHING | 01/06/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/06/2026 | 99 | 62 | 37
MYDESIGNATION ONLINE CLOTHING | 01/06/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/06/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/07/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/07/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/07/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/07/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/08/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/08/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/08/2026 | 0 | 0 | 0
MYDESIGNATION ONLINE CLOTHING | 01/08/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/06/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/06/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/06/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/06/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/07/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/07/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/07/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/07/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/08/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/08/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/08/2026 | 0 | 0 | 0
Myfinflow Consultancy Private Limited | 01/08/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/04/2026 | 1,463 | 548 | 915
Mysore Saree Udyog LLP | 01/05/2026 | 1,229 | 461 | 768
Mysore Saree Udyog LLP | 01/06/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/06/2026 | 2,044 | 767 | 1,277
Mysore Saree Udyog LLP | 01/06/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/06/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/07/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/07/2026 | 3,658 | 1,372 | 2,286
Mysore Saree Udyog LLP | 01/07/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/07/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/08/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/08/2026 | 7,666 | 2,875 | 4,791
Mysore Saree Udyog LLP | 01/08/2026 | 0 | 0 | 0
Mysore Saree Udyog LLP | 01/08/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
MyTeam11 Fantasy Sports Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/04/2026 | 763 | 409 | 354
Nalli Silk Sarees Private Limited | 01/05/2026 | 820 | 439 | 381
Nalli Silk Sarees Private Limited | 01/06/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/06/2026 | 1,693 | 907 | 786
Nalli Silk Sarees Private Limited | 01/06/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/06/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/07/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/07/2026 | 1,211 | 649 | 562
Nalli Silk Sarees Private Limited | 01/07/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/07/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/08/2026 | 0 | 0 | 0
Nalli Silk Sarees Private Limited | 01/08/2026 | 1,598 | 856 | 742
Nalli Silk Sarees Private Limited | 01/08/2026 | 2 | 1 | 1
Nalli Silk Sarees Private Limited | 01/08/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/04/2026 | 1,127 | 604 | 523
NARAYANA HRUDAYALAYA LIMITED | 01/06/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/06/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/06/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/06/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/07/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/07/2026 | 281 | 151 | 130
NARAYANA HRUDAYALAYA LIMITED | 01/07/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/07/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/08/2026 | 0 | 0 | 0
NARAYANA HRUDAYALAYA LIMITED | 01/08/2026 | 2,260 | 1,211 | 1,049
NARAYANA HRUDAYALAYA LIMITED | 01/08/2026 | 2 | 1 | 1
NARAYANA HRUDAYALAYA LIMITED | 01/08/2026 | 0 | 0 | 0
Navia Markets Limited | 01/04/2026 | 0 | 392 | -392
Navia Markets Limited | 01/05/2026 | 0 | 396 | -396
Navia Markets Limited | 01/06/2026 | 0 | 0 | 0
Navia Markets Limited | 01/06/2026 | 0 | 0 | 0
Navia Markets Limited | 01/06/2026 | 0 | 0 | 0
Navia Markets Limited | 01/06/2026 | 0 | 0 | 0
Navia Markets Limited | 01/07/2026 | 0 | 0 | 0
Navia Markets Limited | 01/07/2026 | 0 | 0 | 0
Navia Markets Limited | 01/07/2026 | 0 | 0 | 0
Navia Markets Limited | 01/07/2026 | 0 | 0 | 0
Navia Markets Limited | 01/08/2026 | 0 | 0 | 0
Navia Markets Limited | 01/08/2026 | 0 | 0 | 0
Navia Markets Limited | 01/08/2026 | 0 | 0 | 0
Navia Markets Limited | 01/08/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/04/2026 | 30,588 | 21,849 | 8,739
Navmaya Tech Services Private Limited | 01/05/2026 | 40,409 | 28,864 | 11,545
Navmaya Tech Services Private Limited | 01/06/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/06/2026 | 23,982 | 17,130 | 6,852
Navmaya Tech Services Private Limited | 01/06/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/06/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/07/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/07/2026 | 24,850 | 17,750 | 7,100
Navmaya Tech Services Private Limited | 01/07/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/07/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/08/2026 | 0 | 0 | 0
Navmaya Tech Services Private Limited | 01/08/2026 | 54,292 | 38,780 | 15,512
Navmaya Tech Services Private Limited | 01/08/2026 | 53 | 19 | 34
Navmaya Tech Services Private Limited | 01/08/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/06/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/06/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/06/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/06/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/07/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/07/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/07/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/07/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/08/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/08/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/08/2026 | 0 | 0 | 0
NeoDove Technologies Pvt Ltd | 01/08/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/04/2026 | 64,065 | 41,782 | 22,283
NETWAY INDIA PRIVATE LIMITED | 01/05/2026 | 133,443 | 87,028 | 46,415
NETWAY INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/06/2026 | 77,953 | 50,839 | 27,114
NETWAY INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/07/2026 | 27,361 | 17,844 | 9,517
NETWAY INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
NETWAY INDIA PRIVATE LIMITED | 01/08/2026 | 11,433 | 7,456 | 3,977
NETWAY INDIA PRIVATE LIMITED | 01/08/2026 | 12 | 6 | 6
NETWAY INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/04/2026 | 225 | 68 | 157
Nextspeed Technologies Private Limited | 01/05/2026 | 161 | 48 | 113
Nextspeed Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/06/2026 | 26 | 8 | 18
Nextspeed Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/07/2026 | 3 | 1 | 2
Nextspeed Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/08/2026 | 8 | 2 | 6
Nextspeed Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Nextspeed Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/05/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 2,890 | 1,806 | 1,084
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/06/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/07/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 49,196 | 30,748 | 18,448
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 47 | 22 | 25
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NIPPON LIFE INDIA ASSET MANAGEMENT LIMITED | 01/08/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/06/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/06/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/06/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/06/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/07/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/07/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/07/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/07/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/08/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/08/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/08/2026 | 0 | 0 | 0
NutroActive Industries Private Limited | 01/08/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/05/2026 | 0 | 635 | -635
Octopolis Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/06/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/07/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
Octopolis Technologies Private Limited | 01/08/2026 | 1 | 0 | 1
Octopolis Technologies Private Limited | 01/08/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/04/2026 | 1,786,212 | 1,623,829 | 162,383
One97 Communications Ltd | 01/05/2026 | 805,793 | 710,994 | 94,799
One97 Communications Ltd | 01/06/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/06/2026 | 726,702 | 641,208 | 85,494
One97 Communications Ltd | 01/06/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/06/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/06/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/06/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/06/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/06/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/07/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/07/2026 | 1,058,738 | 962,489 | 96,249
One97 Communications Ltd | 01/07/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/07/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/07/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/07/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/07/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/07/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/08/2026 | 1 | 1 | 0
One97 Communications Ltd | 01/08/2026 | 640,311 | 564,980 | 75,331
One97 Communications Ltd | 01/08/2026 | 799 | 851 | -52
One97 Communications Ltd | 01/08/2026 | 38 | 54 | -16
One97 Communications Ltd | 01/08/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/08/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/08/2026 | 0 | 0 | 0
One97 Communications Ltd | 01/08/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/04/2026 | 9 | 6 | 3
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 8 | 5 | 3
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/06/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 6 | 4 | 2
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/07/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 6 | 4 | 2
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
Paisabazaar Marketing and Consulting Pvt. Ltd. | 01/08/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PASSION GAMING PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/04/2026 | 62,478 | 31,239 | 31,239
Pathfinder Publishing Pvt. Ltd | 01/04/2026 | 9,690 | 4,038 | 5,652
Pathfinder Publishing Pvt. Ltd | 01/04/2026 | 22 | 8 | 14
Pathfinder Publishing Pvt. Ltd | 01/04/2026 | 115,271 | 48,030 | 67,241
Pathfinder Publishing Pvt. Ltd | 01/05/2026 | 77,817 | 38,908 | 38,909
Pathfinder Publishing Pvt. Ltd | 01/05/2026 | 13,708 | 5,712 | 7,996
Pathfinder Publishing Pvt. Ltd | 01/05/2026 | 15 | 6 | 9
Pathfinder Publishing Pvt. Ltd | 01/05/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/05/2026 | 52,410 | 21,838 | 30,572
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 103,879 | 51,939 | 51,940
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 4,456 | 1,856 | 2,600
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 25 | 9 | 16
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 99,277 | 41,365 | 57,912
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/06/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 135,131 | 67,565 | 67,566
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 2,220 | 925 | 1,295
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 42 | 16 | 26
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 111,763 | 46,568 | 65,195
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/07/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 29,667 | 13,845 | 15,822
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 40,921 | 17,050 | 23,871
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 9 | 5 | 4
Pathfinder Publishing Pvt. Ltd | 01/08/2026 | 1 | 1 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/04/2026 | 0 | 1,484 | -1,484
PAYU PAYMENTS PRIVATE LIMITED | 01/04/2026 | 74 | 37 | 37
PAYU PAYMENTS PRIVATE LIMITED | 01/05/2026 | 0 | 1,559 | -1,559
PAYU PAYMENTS PRIVATE LIMITED | 01/05/2026 | 80 | 40 | 40
PAYU PAYMENTS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/06/2026 | 85 | 43 | 42
PAYU PAYMENTS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/07/2026 | 114 | 57 | 57
PAYU PAYMENTS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PAYU PAYMENTS PRIVATE LIMITED | 01/08/2026 | 142 | 71 | 71
PAYU PAYMENTS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
POONAWALLA FINCORP LIMITED | 01/04/2026 | 125,403 | 47,026 | 78,377
POONAWALLA FINCORP LIMITED | 01/04/2026 | 274 | 86 | 188
POONAWALLA FINCORP LIMITED | 01/05/2026 | 103,778 | 38,917 | 64,861
POONAWALLA FINCORP LIMITED | 01/05/2026 | 208 | 65 | 143
POONAWALLA FINCORP LIMITED | 01/06/2026 | 0 | 0 | 0
POONAWALLA FINCORP LIMITED | 01/06/2026 | 131,993 | 49,497 | 82,496
POONAWALLA FINCORP LIMITED | 01/06/2026 | 77 | 24 | 53
POONAWALLA FINCORP LIMITED | 01/06/2026 | 0 | 0 | 0
POONAWALLA FINCORP LIMITED | 01/07/2026 | 0 | 0 | 0
POONAWALLA FINCORP LIMITED | 01/07/2026 | 116,763 | 43,786 | 72,977
POONAWALLA FINCORP LIMITED | 01/07/2026 | 1 | 0 | 1
POONAWALLA FINCORP LIMITED | 01/07/2026 | 0 | 0 | 0
POONAWALLA FINCORP LIMITED | 01/08/2026 | 0 | 0 | 0
POONAWALLA FINCORP LIMITED | 01/08/2026 | 141,653 | 53,120 | 88,533
POONAWALLA FINCORP LIMITED | 01/08/2026 | 164 | 51 | 113
POONAWALLA FINCORP LIMITED | 01/08/2026 | 2 | 1 | 1
Poptech Growth Private Limited | 01/06/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/06/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/06/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/06/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/07/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/07/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/07/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/07/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/08/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/08/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/08/2026 | 0 | 0 | 0
Poptech Growth Private Limited | 01/08/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/04/2026 | 746 | 509 | 237
PRANALI SANDEEP BORSE | 01/04/2026 | 1 | 1 | 0
PRANALI SANDEEP BORSE | 01/05/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/06/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/06/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/06/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/06/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/07/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/07/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/07/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/07/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/08/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/08/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/08/2026 | 0 | 0 | 0
PRANALI SANDEEP BORSE | 01/08/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
PROSPERR.IO PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/04/2026 | 4,807 | 2,467 | 2,340
Public Clothing Private Limited | 01/05/2026 | 762 | 1,022 | -260
Public Clothing Private Limited | 01/06/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/06/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/06/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/06/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/07/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/07/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/07/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/07/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/08/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/08/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/08/2026 | 0 | 0 | 0
Public Clothing Private Limited | 01/08/2026 | 0 | 0 | 0
Puravankara Limited | 01/04/2026 | 37,970 | 12,616 | 25,354
Puravankara Limited | 01/05/2026 | 35,334 | 11,792 | 23,542
Puravankara Limited | 01/05/2026 | 25,668 | 8,021 | 17,647
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/06/2026 | 0 | 0 | 0
Puravankara Limited | 01/07/2026 | 0 | 0 | 0
Puravankara Limited | 01/07/2026 | 2,821 | 1,632 | 1,189
Puravankara Limited | 01/07/2026 | 0 | 0 | 0
Puravankara Limited | 01/07/2026 | 0 | 0 | 0
Puravankara Limited | 01/07/2026 | 0 | 0 | 0
Puravankara Limited | 01/07/2026 | 0 | 0 | 0
Puravankara Limited | 01/07/2026 | 0 | 0 | 0
Puravankara Limited | 01/07/2026 | 0 | 0 | 0
Puravankara Limited | 01/08/2026 | 0 | 0 | 0
Puravankara Limited | 01/08/2026 | 0 | 0 | 0
Puravankara Limited | 01/08/2026 | 1 | 0 | 1
Puravankara Limited | 01/08/2026 | 0 | 0 | 0
Puravankara Limited | 01/08/2026 | 0 | 0 | 0
Puravankara Limited | 01/08/2026 | 1 | 0 | 1
Puravankara Limited | 01/08/2026 | 0 | 0 | 0
Puravankara Limited | 01/08/2026 | 0 | 0 | 0
Pureplay Skin Sciences India Pvt Ltd | 01/04/2026 | 11,828 | 6,336 | 5,492
Pureplay Skin Sciences India Pvt Ltd | 01/04/2026 | 2 | 1 | 1
Pureplay Skin Sciences India Pvt Ltd | 01/05/2026 | 34,009 | 18,219 | 15,790
Pureplay Skin Sciences India Pvt Ltd | 01/05/2026 | 1 | 0 | 1
Pureplay Skin Sciences India Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Pureplay Skin Sciences India Pvt Ltd | 01/06/2026 | 39,830 | 21,338 | 18,492
Pureplay Skin Sciences India Pvt Ltd | 01/06/2026 | 12 | 8 | 4
Pureplay Skin Sciences India Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Pureplay Skin Sciences India Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Pureplay Skin Sciences India Pvt Ltd | 01/07/2026 | 107,123 | 57,387 | 49,736
Pureplay Skin Sciences India Pvt Ltd | 01/07/2026 | 52 | 33 | 19
Pureplay Skin Sciences India Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Pureplay Skin Sciences India Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Pureplay Skin Sciences India Pvt Ltd | 01/08/2026 | 44,966 | 24,089 | 20,877
Pureplay Skin Sciences India Pvt Ltd | 01/08/2026 | 3 | 2 | 1
Pureplay Skin Sciences India Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/06/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/06/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/06/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/06/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/07/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/07/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/07/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/07/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/08/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/08/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/08/2026 | 0 | 0 | 0
Quantum Asset Management Company Private Limited. | 01/08/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
QUID INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/06/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/06/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/06/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/06/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/07/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/07/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/07/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/07/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/08/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/08/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/08/2026 | 0 | 0 | 0
Rabbit RA Private Limited | 01/08/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/05/2026 | 539 | 426 | 113
Relaxo Footwears Ltd. | 01/06/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/06/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/06/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/06/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/07/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/07/2026 | 14,068 | 11,106 | 2,962
Relaxo Footwears Ltd. | 01/07/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/07/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/08/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/08/2026 | 61,952 | 48,910 | 13,042
Relaxo Footwears Ltd. | 01/08/2026 | 0 | 0 | 0
Relaxo Footwears Ltd. | 01/08/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/04/2026 | 21,977 | 6,593 | 15,384
Reliance General Insurance Co.Ltd. | 01/05/2026 | 29,857 | 8,957 | 20,900
Reliance General Insurance Co.Ltd. | 01/06/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/06/2026 | 32,503 | 9,751 | 22,752
Reliance General Insurance Co.Ltd. | 01/06/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/06/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/07/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/07/2026 | 57,498 | 17,249 | 40,249
Reliance General Insurance Co.Ltd. | 01/07/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/07/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/08/2026 | 0 | 0 | 0
Reliance General Insurance Co.Ltd. | 01/08/2026 | 37,316 | 11,195 | 26,121
Reliance General Insurance Co.Ltd. | 01/08/2026 | 15 | 7 | 8
Reliance General Insurance Co.Ltd. | 01/08/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/06/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/07/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Reliance Nippon Life Insurance Co. Ltd. | 01/08/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/06/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/06/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/06/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/06/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/07/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/07/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/07/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/07/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/08/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/08/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/08/2026 | 0 | 0 | 0
Renaissance Smart Tech Private Limited | 01/08/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/04/2026 | 2,428 | 1,656 | 772
Savaari Car Rentals Pvt Ltd | 01/05/2026 | 2,462 | 1,679 | 783
Savaari Car Rentals Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/06/2026 | 2,641 | 1,801 | 840
Savaari Car Rentals Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/06/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/07/2026 | 1,144 | 780 | 364
Savaari Car Rentals Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/07/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Savaari Car Rentals Pvt Ltd | 01/08/2026 | 1,613 | 1,100 | 513
Savaari Car Rentals Pvt Ltd | 01/08/2026 | 5 | 5 | 0
Savaari Car Rentals Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/04/2026 | 26,271 | 8,210 | 18,061
Savesage Solutions Private Limited | 01/05/2026 | 17,205 | 5,377 | 11,828
Savesage Solutions Private Limited | 01/06/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/06/2026 | 5,597 | 1,749 | 3,848
Savesage Solutions Private Limited | 01/06/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/06/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/08/2026 | 1 | 0 | 1
Savesage Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Savesage Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
SBI Funds Management Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
SBI Funds Management Pvt. Ltd | 01/08/2026 | 160,628 | 86,051 | 74,577
SBI Funds Management Pvt. Ltd | 01/08/2026 | 100 | 42 | 58
SBI Funds Management Pvt. Ltd | 01/08/2026 | 0 | 0 | 0
Senco Gold Limited | 01/04/2026 | 235,936 | 88,476 | 147,460
Senco Gold Limited | 01/05/2026 | 98,449 | 36,918 | 61,531
Senco Gold Limited | 01/05/2026 | 6,765 | 2,537 | 4,228
Senco Gold Limited | 01/06/2026 | 0 | 0 | 0
Senco Gold Limited | 01/06/2026 | 40,994 | 15,373 | 25,621
Senco Gold Limited | 01/06/2026 | 0 | 0 | 0
Senco Gold Limited | 01/06/2026 | 0 | 0 | 0
Senco Gold Limited | 01/06/2026 | 0 | 0 | 0
Senco Gold Limited | 01/06/2026 | 6,899 | 2,587 | 4,312
Senco Gold Limited | 01/06/2026 | 0 | 0 | 0
Senco Gold Limited | 01/06/2026 | 0 | 0 | 0
Senco Gold Limited | 01/07/2026 | 0 | 0 | 0
Senco Gold Limited | 01/07/2026 | 112,978 | 42,367 | 70,611
Senco Gold Limited | 01/07/2026 | 0 | 0 | 0
Senco Gold Limited | 01/07/2026 | 0 | 0 | 0
Senco Gold Limited | 01/07/2026 | 0 | 0 | 0
Senco Gold Limited | 01/07/2026 | 3,324 | 1,246 | 2,078
Senco Gold Limited | 01/07/2026 | 0 | 0 | 0
Senco Gold Limited | 01/07/2026 | 0 | 0 | 0
Senco Gold Limited | 01/08/2026 | 0 | 0 | 0
Senco Gold Limited | 01/08/2026 | 86,785 | 32,544 | 54,241
Senco Gold Limited | 01/08/2026 | 1 | 1 | 0
Senco Gold Limited | 01/08/2026 | 2 | 2 | 0
Senco Gold Limited | 01/08/2026 | 0 | 0 | 0
Senco Gold Limited | 01/08/2026 | 1 | 0 | 1
Senco Gold Limited | 01/08/2026 | 0 | 0 | 0
Senco Gold Limited | 01/08/2026 | 0 | 0 | 0
Sharda University | 01/04/2026 | 0 | 0 | 0
Sharda University | 01/05/2026 | 1 | 0 | 1
Sharda University | 01/06/2026 | 0 | 0 | 0
Sharda University | 01/06/2026 | 0 | 0 | 0
Sharda University | 01/06/2026 | 0 | 0 | 0
Sharda University | 01/06/2026 | 0 | 0 | 0
Sharda University | 01/07/2026 | 0 | 0 | 0
Sharda University | 01/07/2026 | 0 | 0 | 0
Sharda University | 01/07/2026 | 0 | 0 | 0
Sharda University | 01/07/2026 | 0 | 0 | 0
Sharda University | 01/08/2026 | 0 | 0 | 0
Sharda University | 01/08/2026 | 0 | 0 | 0
Sharda University | 01/08/2026 | 0 | 0 | 0
Sharda University | 01/08/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/04/2026 | 201,652 | 100,826 | 100,826
Shemaroo Entertainment Ltd. | 01/05/2026 | 137,068 | 68,534 | 68,534
Shemaroo Entertainment Ltd. | 01/06/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/06/2026 | 197,084 | 98,542 | 98,542
Shemaroo Entertainment Ltd. | 01/06/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/06/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/07/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/07/2026 | 239,743 | 119,871 | 119,872
Shemaroo Entertainment Ltd. | 01/07/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/07/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/08/2026 | 0 | 0 | 0
Shemaroo Entertainment Ltd. | 01/08/2026 | 200,897 | 100,448 | 100,449
Shemaroo Entertainment Ltd. | 01/08/2026 | 55 | 23 | 32
Shemaroo Entertainment Ltd. | 01/08/2026 | 0 | 0 | 0
Shriram Asset Management Company Limited | 01/07/2026 | 0 | 0 | 0
Shriram Asset Management Company Limited | 01/07/2026 | 2,063 | 1,547 | 516
Shriram Asset Management Company Limited | 01/07/2026 | 0 | 0 | 0
Shriram Asset Management Company Limited | 01/07/2026 | 0 | 0 | 0
Shriram Asset Management Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram Asset Management Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram Asset Management Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram Asset Management Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/04/2026 | 36,587 | 19,600 | 16,987
Shriram General Insurance Company Ltd | 01/05/2026 | 22,839 | 12,235 | 10,604
Shriram General Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/06/2026 | 13,288 | 7,118 | 6,170
Shriram General Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/06/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/07/2026 | 11,134 | 5,965 | 5,169
Shriram General Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/07/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/08/2026 | 15,101 | 8,090 | 7,011
Shriram General Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Shriram General Insurance Company Ltd | 01/08/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/04/2026 | 6,623 | 2,258 | 4,365
Shriram Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/06/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/07/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram Life Insurance Company Limited | 01/08/2026 | 0 | 0 | 0
Shriram Transport Finance Company Ltd | 01/04/2026 | 282,105 | 211,578 | 70,527
Shriram Transport Finance Company Ltd | 01/04/2026 | 1,263 | 595 | 668
Shriram Transport Finance Company Ltd | 01/05/2026 | 232,658 | 174,493 | 58,165
Shriram Transport Finance Company Ltd | 01/05/2026 | 1,558 | 734 | 824
Shriram Transport Finance Company Ltd | 01/06/2026 | 0 | 0 | 0
Shriram Transport Finance Company Ltd | 01/06/2026 | 211,675 | 158,756 | 52,919
Shriram Transport Finance Company Ltd | 01/06/2026 | 917 | 432 | 485
Shriram Transport Finance Company Ltd | 01/06/2026 | 0 | 0 | 0
Shriram Transport Finance Company Ltd | 01/07/2026 | 0 | 0 | 0
Shriram Transport Finance Company Ltd | 01/07/2026 | 262,038 | 196,528 | 65,510
Shriram Transport Finance Company Ltd | 01/07/2026 | 1,243 | 586 | 657
Shriram Transport Finance Company Ltd | 01/07/2026 | 0 | 0 | 0
Shriram Transport Finance Company Ltd | 01/08/2026 | 0 | 0 | 0
Shriram Transport Finance Company Ltd | 01/08/2026 | 621,449 | 466,087 | 155,362
Shriram Transport Finance Company Ltd | 01/08/2026 | 2,827 | 1,333 | 1,494
Shriram Transport Finance Company Ltd | 01/08/2026 | 98 | 82 | 16
Simplilearn Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Simplilearn Solutions Private Limited | 01/07/2026 | 26,583 | 22,152 | 4,431
Simplilearn Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Simplilearn Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Simplilearn Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Simplilearn Solutions Private Limited | 01/08/2026 | 33,343 | 27,786 | 5,557
Simplilearn Solutions Private Limited | 01/08/2026 | 21 | 7 | 14
Simplilearn Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/06/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/06/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/06/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/06/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/07/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/07/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/07/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/07/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/08/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/08/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/08/2026 | 0 | 0 | 0
SOTC Travel Limited | 01/08/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/04/2026 | 20,794 | 15,595 | 5,199
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/05/2026 | 3,085 | 2,313 | 772
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/08/2026 | 1 | 0 | 1
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
SPEEL FINANCE COMPANY PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/04/2026 | 204,501 | 69,716 | 134,785
SPICE MONEY LIMITED | 01/05/2026 | 222,138 | 75,729 | 146,409
SPICE MONEY LIMITED | 01/06/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/06/2026 | 261,378 | 89,106 | 172,272
SPICE MONEY LIMITED | 01/06/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/06/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/07/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/07/2026 | 392,170 | 133,694 | 258,476
SPICE MONEY LIMITED | 01/07/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/07/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/08/2026 | 0 | 0 | 0
SPICE MONEY LIMITED | 01/08/2026 | 386,991 | 131,929 | 255,062
SPICE MONEY LIMITED | 01/08/2026 | 422 | 205 | 217
SPICE MONEY LIMITED | 01/08/2026 | 40 | 33 | 7
Sri Sri Publications and Media Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Sri Sri Publications and Media Pvt Ltd | 01/08/2026 | 16,528 | 5,995 | 10,533
Sri Sri Publications and Media Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Sri Sri Publications and Media Pvt Ltd | 01/08/2026 | 0 | 0 | 0
Standard chartered Bank | 01/04/2026 | 7 | 2 | 5
Standard chartered Bank | 01/06/2026 | 0 | 0 | 0
Standard chartered Bank | 01/06/2026 | 0 | 0 | 0
Standard chartered Bank | 01/06/2026 | 0 | 0 | 0
Standard chartered Bank | 01/06/2026 | 0 | 0 | 0
Standard chartered Bank | 01/07/2026 | 0 | 0 | 0
Standard chartered Bank | 01/07/2026 | 0 | 0 | 0
Standard chartered Bank | 01/07/2026 | 0 | 0 | 0
Standard chartered Bank | 01/07/2026 | 0 | 0 | 0
Standard chartered Bank | 01/08/2026 | 0 | 0 | 0
Standard chartered Bank | 01/08/2026 | 0 | 0 | 0
Standard chartered Bank | 01/08/2026 | 0 | 0 | 0
Standard chartered Bank | 01/08/2026 | 0 | 0 | 0
Sterling Holiday Resorts Ltd. | 01/04/2026 | 1,747 | 524 | 1,223
Sterling Holiday Resorts Ltd. | 01/04/2026 | 29 | 14 | 15
Sterling Holiday Resorts Ltd. | 01/05/2026 | 3,936 | 1,181 | 2,755
Sterling Holiday Resorts Ltd. | 01/05/2026 | 32 | 15 | 17
Sterling Holiday Resorts Ltd. | 01/06/2026 | 0 | 0 | 0
Sterling Holiday Resorts Ltd. | 01/06/2026 | 1,781 | 534 | 1,247
Sterling Holiday Resorts Ltd. | 01/06/2026 | 30 | 14 | 16
Sterling Holiday Resorts Ltd. | 01/06/2026 | 0 | 0 | 0
Sterling Holiday Resorts Ltd. | 01/07/2026 | 0 | 0 | 0
Sterling Holiday Resorts Ltd. | 01/07/2026 | 8,313 | 2,494 | 5,819
Sterling Holiday Resorts Ltd. | 01/07/2026 | 39 | 18 | 21
Sterling Holiday Resorts Ltd. | 01/07/2026 | 0 | 0 | 0
Sterling Holiday Resorts Ltd. | 01/08/2026 | 0 | 0 | 0
Sterling Holiday Resorts Ltd. | 01/08/2026 | 12,601 | 3,780 | 8,821
Sterling Holiday Resorts Ltd. | 01/08/2026 | 64 | 30 | 34
Sterling Holiday Resorts Ltd. | 01/08/2026 | 3 | 2 | 1
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/05/2026 | 11,082 | 8,525 | 2,557
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 37,185 | 28,604 | 8,581
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 4 | 3 | 1
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 263,178 | 202,445 | 60,733
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
TATA 1MG HEALTHCARE SOLUTIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/06/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/06/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/06/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/06/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/07/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/07/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/07/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/07/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/08/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/08/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/08/2026 | 0 | 0 | 0
Tata Asset Management Limited | 01/08/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/06/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/06/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/06/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/06/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/07/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/07/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/07/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/07/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/08/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/08/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/08/2026 | 0 | 0 | 0
Techmash Solution Pvt. Ltd.- Playo | 01/08/2026 | 0 | 0 | 0
Techslash Solutions Private Limited | 01/05/2026 | 245 | 74 | 171
Techslash Solutions Private Limited | 01/06/2026 | 0 | 0 | 0
Techslash Solutions Private Limited | 01/06/2026 | 2,373 | 712 | 1,661
Techslash Solutions Private Limited | 01/06/2026 | 1 | 0 | 1
Techslash Solutions Private Limited | 01/06/2026 | 0 | 0 | 0
Techslash Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Techslash Solutions Private Limited | 01/07/2026 | 3,441 | 1,032 | 2,409
Techslash Solutions Private Limited | 01/07/2026 | 3 | 1 | 2
Techslash Solutions Private Limited | 01/07/2026 | 0 | 0 | 0
Techslash Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Techslash Solutions Private Limited | 01/08/2026 | 550 | 165 | 385
Techslash Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
Techslash Solutions Private Limited | 01/08/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/06/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/06/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/06/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/06/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/07/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/07/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/07/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/07/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/08/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/08/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/08/2026 | 0 | 0 | 0
The Muthoot Finance Ltd. | 01/08/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/04/2026 | 2,188 | 1,492 | 696
THE SOULED STORE PRIVATE LIMITED | 01/05/2026 | 2,435 | 1,660 | 775
THE SOULED STORE PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/06/2026 | 1,112 | 758 | 354
THE SOULED STORE PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/07/2026 | 976 | 665 | 311
THE SOULED STORE PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/08/2026 | 871 | 594 | 277
THE SOULED STORE PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
THE SOULED STORE PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/06/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/06/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/06/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/06/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/07/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/07/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/07/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/07/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/08/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/08/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/08/2026 | 0 | 0 | 0
Thomas Cook (India) Ltd | 01/08/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/04/2026 | 3,048 | 1,524 | 1,524
TRAVELOGY ONLINE PRIVATE LIMITED | 01/05/2026 | 3,314 | 1,657 | 1,657
TRAVELOGY ONLINE PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/06/2026 | 1,654 | 827 | 827
TRAVELOGY ONLINE PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/07/2026 | 936 | 468 | 468
TRAVELOGY ONLINE PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
TRAVELOGY ONLINE PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/04/2026 | 16,083 | 5,026 | 11,057
TRYLO INTIMATES | 01/05/2026 | 818 | 256 | 562
TRYLO INTIMATES | 01/06/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/06/2026 | 1,954 | 611 | 1,343
TRYLO INTIMATES | 01/06/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/06/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/07/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/07/2026 | 2,047 | 640 | 1,407
TRYLO INTIMATES | 01/07/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/07/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/08/2026 | 0 | 0 | 0
TRYLO INTIMATES | 01/08/2026 | 1,828 | 571 | 1,257
TRYLO INTIMATES | 01/08/2026 | 40 | 12 | 28
TRYLO INTIMATES | 01/08/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/04/2026 | 473,091 | 322,562 | 150,529
TTK Prestige Limited | 01/05/2026 | 682,094 | 465,064 | 217,030
TTK Prestige Limited | 01/06/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/06/2026 | 449,645 | 306,576 | 143,069
TTK Prestige Limited | 01/06/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/06/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/07/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/07/2026 | 677,319 | 461,808 | 215,511
TTK Prestige Limited | 01/07/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/07/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/08/2026 | 0 | 0 | 0
TTK Prestige Limited | 01/08/2026 | 370,879 | 252,872 | 118,007
TTK Prestige Limited | 01/08/2026 | 153 | 53 | 100
TTK Prestige Limited | 01/08/2026 | 1 | 1 | 0
TVS Credit Services Ltd. | 01/04/2026 | 444,268 | 208,250 | 236,018
TVS Credit Services Ltd. | 01/04/2026 | 207 | 107 | 100
TVS Credit Services Ltd. | 01/05/2026 | 786,037 | 368,455 | 417,582
TVS Credit Services Ltd. | 01/05/2026 | 322 | 166 | 156
TVS Credit Services Ltd. | 01/06/2026 | 0 | 0 | 0
TVS Credit Services Ltd. | 01/06/2026 | 669,228 | 313,701 | 355,527
TVS Credit Services Ltd. | 01/06/2026 | 198 | 102 | 96
TVS Credit Services Ltd. | 01/06/2026 | 0 | 0 | 0
TVS Credit Services Ltd. | 01/07/2026 | 0 | 0 | 0
TVS Credit Services Ltd. | 01/07/2026 | 708,863 | 332,280 | 376,583
TVS Credit Services Ltd. | 01/07/2026 | 213 | 110 | 103
TVS Credit Services Ltd. | 01/07/2026 | 0 | 0 | 0
TVS Credit Services Ltd. | 01/08/2026 | 0 | 0 | 0
TVS Credit Services Ltd. | 01/08/2026 | 1,066,013 | 533,006 | 533,007
TVS Credit Services Ltd. | 01/08/2026 | 368 | 190 | 178
TVS Credit Services Ltd. | 01/08/2026 | 54 | 45 | 9
Ujjivan Small Finance Bank Limited | 01/04/2026 | 165,672 | 103,545 | 62,127
Ujjivan Small Finance Bank Limited | 01/04/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/04/2026 | 10,054 | 6,284 | 3,770
Ujjivan Small Finance Bank Limited | 01/05/2026 | 196,340 | 122,713 | 73,627
Ujjivan Small Finance Bank Limited | 01/05/2026 | 7,460 | 4,662 | 2,798
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 211,838 | 132,399 | 79,439
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/06/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 311,176 | 194,485 | 116,691
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 1,289 | 805 | 484
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/07/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 179,874 | 112,421 | 67,453
Ujjivan Small Finance Bank Limited | 01/08/2026 | 215 | 111 | 104
Ujjivan Small Finance Bank Limited | 01/08/2026 | 37 | 31 | 6
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Ujjivan Small Finance Bank Limited | 01/08/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/06/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/06/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/06/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/06/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/07/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/07/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/07/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/07/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/08/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/08/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/08/2026 | 0 | 0 | 0
Universal Sportsbiz Private Limited | 01/08/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/06/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/06/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/06/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/06/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/07/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/07/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/07/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/07/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/08/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/08/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/08/2026 | 0 | 0 | 0
Urban Money Private Limited | 01/08/2026 | 0 | 0 | 0
V4Edu | 01/06/2026 | 0 | 0 | 0
V4Edu | 01/06/2026 | 0 | 0 | 0
V4Edu | 01/06/2026 | 0 | 0 | 0
V4Edu | 01/06/2026 | 0 | 0 | 0
V4Edu | 01/07/2026 | 0 | 0 | 0
V4Edu | 01/07/2026 | 0 | 0 | 0
V4Edu | 01/07/2026 | 0 | 0 | 0
V4Edu | 01/07/2026 | 0 | 0 | 0
V4Edu | 01/08/2026 | 0 | 0 | 0
V4Edu | 01/08/2026 | 0 | 0 | 0
V4Edu | 01/08/2026 | 0 | 0 | 0
V4Edu | 01/08/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/06/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/06/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/06/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/06/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/07/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/07/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/07/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/07/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/08/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/08/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/08/2026 | 0 | 0 | 0
Vasudhaiva Kutumbakam Group Private Limited | 01/08/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/04/2026 | 874 | 328 | 546
Vishwnet India Private Limited | 01/06/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/06/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/06/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/06/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/07/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/07/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/07/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/07/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/08/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/08/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/08/2026 | 0 | 0 | 0
Vishwnet India Private Limited | 01/08/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WAKEFIT INNOVATIONS PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WAY 2 WEALTH SECURITIES PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/04/2026 | 0 | 105 | -105
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/05/2026 | 0 | 156 | -156
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WISELIFE WELLNESS INDIA PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/05/2026 | 2,328 | 1,164 | 1,164
WROGN PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/06/2026 | 13,191 | 6,595 | 6,596
WROGN PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/06/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/07/2026 | 14,150 | 7,075 | 7,075
WROGN PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/07/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WROGN PRIVATE LIMITED | 01/08/2026 | 14,247 | 7,123 | 7,124
WROGN PRIVATE LIMITED | 01/08/2026 | 63 | 28 | 35
WROGN PRIVATE LIMITED | 01/08/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/04/2026 | 268 | 112 | 156
WSFX GLOBAL PAY LIMITED | 01/05/2026 | 2,783 | 1,159 | 1,624
WSFX GLOBAL PAY LIMITED | 01/06/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/06/2026 | 346 | 144 | 202
WSFX GLOBAL PAY LIMITED | 01/06/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/06/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/07/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/07/2026 | 330 | 138 | 192
WSFX GLOBAL PAY LIMITED | 01/07/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/07/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/08/2026 | 0 | 0 | 0
WSFX GLOBAL PAY LIMITED | 01/08/2026 | 663 | 276 | 387
WSFX GLOBAL PAY LIMITED | 01/08/2026 | 2 | 1 | 1
WSFX GLOBAL PAY LIMITED | 01/08/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/06/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/06/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/06/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/06/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/07/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/07/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/07/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/07/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/08/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/08/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/08/2026 | 0 | 0 | 0
XTELIFY LIMITED - Formerly Airtel Digital Limited | 01/08/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/06/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/06/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/06/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/06/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/07/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/07/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/07/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/07/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/08/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/08/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/08/2026 | 0 | 0 | 0
YASHODA HOSPITAL VENTURE-II | 01/08/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/06/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/06/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/06/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/06/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/07/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/07/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/07/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/07/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/08/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/08/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/08/2026 | 0 | 0 | 0
YES SECURITIES (INDIA) LIMITED | 01/08/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/04/2026 | 16 | 10 | 6
ZUNO GENERAL INSURANCE LIMITED | 01/04/2026 | 44,989 | 24,101 | 20,888
ZUNO GENERAL INSURANCE LIMITED | 01/04/2026 | 7 | 3 | 4
ZUNO GENERAL INSURANCE LIMITED | 01/05/2026 | 49 | 31 | 18
ZUNO GENERAL INSURANCE LIMITED | 01/05/2026 | 50,396 | 26,998 | 23,398
ZUNO GENERAL INSURANCE LIMITED | 01/05/2026 | 7 | 3 | 4
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 59 | 37 | 22
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 53,980 | 28,918 | 25,062
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 10 | 4 | 6
ZUNO GENERAL INSURANCE LIMITED | 01/06/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 43 | 27 | 16
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 52,735 | 28,251 | 24,484
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 7 | 3 | 4
ZUNO GENERAL INSURANCE LIMITED | 01/07/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 0 | 0 | 0
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 71 | 44 | 27
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 67,596 | 36,212 | 31,384
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 13 | 5 | 8
ZUNO GENERAL INSURANCE LIMITED | 01/08/2026 | 0 | 0 | 0